## Phases
No | Name | WorkType | EAAct | NumberOfDays | Legislated | Color | Visibility | SortOrder
1 | CEAO's Designation Intake | CEAO's Designation | EA Act (2018) | 14 | FALSE | #3eb1d7 | REGULAR | 1
2 | CEAO's Designation Application Review | CEAO's Designation | EA Act (2018) | 60 | FALSE | #3eb1d7 | REGULAR | 2
3 | CEAO's Designation Decision | CEAO's Designation | EA Act (2018) | 14 | FALSE | #3eb1d7 | REGULAR | 3

## Events
No | Parent | PhaseNo | EventName | Phase | EventType | EventCategory | EventPosition | MultipleDays | StartAt | NumberOfDays | Visibility | SortOrder
1 |  | 1 | Start of Intake (e.g. Initial Meeting, Date Confirmation, or Draft Sharing) | CEAO's Designation Intake | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 1
2 |  | 1 | Submission of CEAO's Designation Application for Screening | CEAO's Designation Intake | Submission | Milestone | INTERMEDIATE | FALSE | 7 | 0 | MANDATORY | 2
3 |  | 1 | Additional Information Submission | CEAO's Designation Intake | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 3
4 |  | 1 | Meeting with Proponent | CEAO's Designation Intake | Meeting | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 4
5 |  | 1 | Document Submitted to EAO for "Initial Review" | CEAO's Designation Intake | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 5
6 | 5 | 1 | EAO's Viewpoint on Submitted Document | CEAO's Designation Intake | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 7 | 0 | OPTIONAL | 6
7 |  | 1 | CEAO's Designation Application Withdrawn | CEAO's Designation Intake | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 7
8 |  | 1 | Other | CEAO's Designation Intake | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 8
9 |  | 1 | CEAO's Designation Screening Decision | CEAO's Designation Intake | PAD (Lead) | Decision | END | FALSE | 14 | 0 | MANDATORY | 9
10 |  | 2 | Start of CEAO's Designation Application Review | CEAO's Designation Application Review | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 10
11 |  | 2 | CEAO's Designation Report Completed | CEAO's Designation Application Review | Report | Milestone | INTERMEDIATE | FALSE | 55 | 0 | SUGGESTED | 11
12 |  | 2 | Additional Information Submission | CEAO's Designation Application Review | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 12
13 |  | 2 | CEAO's Designation Application Withdrawn | CEAO's Designation Application Review | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 13
14 | 13 | 2 | CEAO's Designation Application Withdrawn Milestone Bullet | CEAO's Designation Application Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 14
15 |  | 2 | Other | CEAO's Designation Application Review | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 15
16 |  | 2 | CEAO's Designation Decision Package Referred to CEAO | CEAO's Designation Application Review | Referral | Milestone | END | FALSE | 60 | 0 | MANDATORY | 16
17 |  | 3 | Start of CEAO's Designation Application Decision | CEAO's Designation Decision | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 17
18 |  | 3 | Additional Information Submission | CEAO's Designation Decision | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 18
19 |  | 3 | CEAO's Designation Application Withdrawn | CEAO's Designation Decision | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 19
20 | 19 | 3 | CEAO's Designation Application Withdrawn Milestone Bullet | CEAO's Designation Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 20
21 |  | 3 | Other | CEAO's Designation Decision | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 21
22 |  | 3 | CEAO's Designation Decision | CEAO's Designation Decision | CEAO | Decision | END | FALSE | 14 | 0 | MANDATORY | 22
23 | 22 | 3 | CEAO's Designation Decison Announcement & Tweet (if Reviewable) | CEAO's Designation Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 23
24 | 22 | 3 | CEAO's Designation Decision Milestone Bullet | CEAO's Designation Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 24

## Outcomes
No | TemplateNo | TemplateName | OutcomeName | SortOrder
1 | 6 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is POSITIVE | 1
2 | 6 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is NEGATIVE | 2
3 | 7 | CEAO's Designation Application Withdrawn | Proponent Withdraws Project from the CEAO's Designation Process | 3
4 | 9 | CEAO's Designation Screening Decision | Proponent needs to submit a Revised CEAO's Designation Application | 4
5 | 9 | CEAO's Designation Screening Decision | Submission continues to CEAO's Designation Application Review | 5
6 | 9 | CEAO's Designation Screening Decision | Project submitted triggers Project Notification Process | 6
7 | 9 | CEAO's Designation Screening Decision | Project submitted exceeds RPR threshold(s) | 7
8 | 13 | CEAO's Designation Application Withdrawn | Proponent Withdraws Project from the CEAO's Designation Process | 8
9 | 19 | CEAO's Designation Application Withdrawn | Proponent Withdraws Project from the CEAO's Designation Process | 9
10 | 22 | CEAO's Designation Decision | CEAO Designates Project as Reviewable | 10
11 | 22 | CEAO's Designation Decision | CEAO Declines to Designate Project as Reviewable | 11

## Actions
No | OutcomeNo | OutcomeName | ActionName | ActionDescription | AdditionalParams | SortOrder
1 | 1 | EAO's Viewpoint is POSITIVE | NONE | No Actions Needed | {} | 1
2 | 2 | EAO's Viewpoint is NEGATIVE | NONE | No Actions Needed | {} | 2
3 | 3 | Proponent Withdraws Project from the CEAO's Designation Process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 3
4 | 3 | Proponent Withdraws Project from the CEAO's Designation Process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 4
5 | 3 | Proponent Withdraws Project from the CEAO's Designation Process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 5
6 | 3 | Proponent Withdraws Project from the CEAO's Designation Process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 6
7 | 4 | Proponent needs to submit a Revised CEAO's Designation Application | AddEvent | Add EVENT "CEAO's Designation Intake ¦ Submission of CEAO's Designation Application for Screening" at thisEvent ACTUAL +28,Add EVENT "CEAO's Designation Intake ¦ CEAO's Designation Screening Decision" at thisEvent ACTUAL +35 | [{"phase_name":"CEAO's Designation Intake","work_type_id":3,"ea_act_id":3,"event_name":"Submission of CEAO's Designation Application for Screening","start_at":28},{"phase_name":"CEAO's Designation Intake","work_type_id":3,"ea_act_id":3,"event_name":"CEAO's Designation Screening Decision","start_at":7}] | 7
9 | 4 | Proponent needs to submit a Revised CEAO's Designation Application | ChangePhaseEndEvent | Set (new EVENT) "CEAO's Designation Intake ¦ CEAO's Designation Screening Decision" to PHASE END EVENT | {"phase_name":"CEAO's Designation Intake","work_type_id": 3, "ea_act_id": 3, "event_name": "CEAO's Designation Screening Decision"} | 9
10 | 5 | Submission continues to CEAO's Designation Application Review | LockWorkStartDate | Set the workStartDate to thisEvent ACTUAL +1 | {"start_date_locked": true, "start_at": 1} | 10
11 | 5 | Submission continues to CEAO's Designation Application Review | SetEventDate | Set "CEAO's Designation Application Review ¦ Start of CEAO's Designation Application Review" ANTICIPATED to thisEvent ACTUAL +1 | {"phase_name":"CEAO's Designation Application Review","work_type_id": 3, "ea_act_id": 3, "event_name": "Start of CEAO's Designation Application Review", "start_at": 1 } | 11
12 | 6 | Project submitted triggers Project Notification Process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 12
13 | 6 | Project submitted triggers Project Notification Process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 13
14 | 6 | Project submitted triggers Project Notification Process | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 14
15 | 6 | Project submitted triggers Project Notification Process | CreateWork | createWork: "Project Notification" and link to thisWorkLinkedProject | {"work_type":1} | 15
16 | 7 | Project submitted exceeds RPR threshold(s) | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 16
17 | 7 | Project submitted exceeds RPR threshold(s) | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 17
18 | 7 | Project submitted exceeds RPR threshold(s) | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 18
19 | 7 | Project submitted exceeds RPR threshold(s) | CreateWork | createWork: "EAC Assessment" and link to thisWorkLinkedProject | {"work_type":6} | 19
20 | 8 | Proponent Withdraws Project from the CEAO's Designation Process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 20
21 | 8 | Proponent Withdraws Project from the CEAO's Designation Process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 21
22 | 8 | Proponent Withdraws Project from the CEAO's Designation Process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 22
23 | 8 | Proponent Withdraws Project from the CEAO's Designation Process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 23
24 | 9 | Proponent Withdraws Project from the CEAO's Designation Process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 24
25 | 9 | Proponent Withdraws Project from the CEAO's Designation Process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 25
26 | 9 | Proponent Withdraws Project from the CEAO's Designation Process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 26
27 | 9 | Proponent Withdraws Project from the CEAO's Designation Process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 27
28 | 10 | CEAO Designates Project as Reviewable | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 28
29 | 10 | CEAO Designates Project as Reviewable | CreateWork | createWork: "EAC Assessment" and link to thisWorkLinkedProject | {"work_type":6} | 29
30 | 11 | CEAO Declines to Designate Project as Reviewable | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 30
31 | 11 | CEAO Declines to Designate Project as Reviewable | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 31

## Lookups
WorkType | EA Act | Legislated |  | Event Type | Event Category | Visibility | ActionName | Event Position | Multiple Days | Action Name
Project Notification | EA Act (2018) | TRUE | Milestone | Generic | Milestone | MANDATORY | AllEventsDeactivated | START | TRUE | AddEvent
Minister's Designation | EA Act (2002) | FALSE | Milestone | Meeting | Calendar | SUGGESTED | AllEventsDeleted | INTERMEDIATE | FALSE | AddPhase
CEAO's Designation | EA Act (1996) |  | Milestone | Notification | Decision | OPTIONAL | CloseEverything | END |  | ChangePhaseEndEvent
EAC Assessment |  |  | Milestone | Order | Finance | HIDDEN | CloseWork |  |  | CreateWork
Exemption Request |  |  | Milestone | Referral | PCP |  | CompleteCurrentPhase |  |  | LockWorkStartDate
Dispute Resolution |  |  | Milestone | Report | Extension |  | CreateNewWork |  |  | SetEventDate
EAC/Order Amendment |  |  | Milestone | Request | Suspension |  | DisableWorkStartDate |  |  | SetEventStatus
Document Review |  |  | Milestone | Submission |  |  | DuplicatePhase |  |  | SetFederalInvolvement
EAC Extension |  |  | Milestone | Other | [5 empty] | SetPhaseStatus
Substantial Start Decision |  |  | Milestone | Date Capture | [5 empty] | SetProjectState
EAC/Order Transfer |  |  | Extension | Time Limit Extension | [5 empty] | SetProjectStatus
EAC/Order Suspension |  |  | Extension | PCP Time Limit Extension | [5 empty] | SetWorkDecisionMaker
EAC/Order Cancellation |  |  | Suspension | Time Limit Suspension | [5 empty] | SetWorkState
Other |  |  | Suspension | Time Limit Resumption
|  |  | Decision | EAC Ministers
|  |  | Decision | Minister
|  |  | Decision | CEAO
|  |  | Decision | ADM
|  |  | Decision | EPD
|  |  | Decision | PAD (Lead)
|  |  | Decision | Reviewer
|  |  | Decision | Federal
|  |  | Decision | Other
|  |  | PCP | Comment Period
|  |  | PCP | Open House
|  |  | PCP | Virtual Information Session
|  |  | PCP | Other
|  |  | Calendar | Communications
|  |  | Calendar | Executive
|  |  | Calendar | Financial
|  |  | Calendar | Work
|  |  | Calendar | Other
|  |  | Finance | Capacity Funding
|  |  | Finance | Fee Order
|  |  | Finance | Penalties
|  |  | Finance | Administrative
|  |  | Finance | Other