## Phases
No | Name | WorkType | EAAct | NumberOfDays | Legislated | Color | SortOrder
1 | Notification Review | Project Notification | EA Act (2018) | 50 | TRUE | #ffffff | 1
2 | Notification Decision | Project Notification | EA Act (2018) | 10 | TRUE | #ffffff | 2

## Events
No | Parent | PhaseNo | EventName | Phase | EventType | EventCategory | StartAt | NumberOfDays | Mandatory | SortOrder
1 |  | 1 | Project Notification Submission | Notification Review | Submission | Milestone | 0 | 1 | TRUE | 1
2 | 1 | 1 | PCP Coming Soon Announcement & Tweet | Notification Review | Communications | Calendar | 7 | 1 | TRUE | 2
3 | 1 | 1 | PCP Coming Soon Milestone Bullet | Notification Review | Executive | Calendar | 7 | 1 | TRUE | 3
4 |  | 1 | Comment Period | Notification Review | Comment Period | PCP | 14 | 30 | TRUE | 4
5 | 4 | 1 | PCP Now Open Announcement & Tweet | Notification Review | Communications | Calendar | 0 | 1 | TRUE | 5
6 | 4 | 1 | PCP Ending Soon Announcement & Tweet | Notification Review | Communications | Calendar | number_of_days-2 | 1 | TRUE | 6
7 |  | 1 | Additional Information Submission | Notification Review | Submission | Milestone | 0 | 1 | FALSE | 7
8 | 7 | 1 | PCP Coming Soon Announcement & Tweet | Notification Review | Communications | Calendar | 0 | 1 | FALSE | 8
9 | 7 | 1 | Additional PCP Milestone Bullet | Notification Review | Executive | Calendar | 0 | 1 | FALSE | 9
10 |  | 1 | Additional Comment Period | Notification Review | Comment Period | PCP | 0 | 1 | FALSE | 10
11 | 10 | 1 | PCP Now Open Announcement & Tweet | Notification Review | Communications | Calendar | 0 | 1 | FALSE | 11
12 | 10 | 1 | PCP Ending Soon Announcement & Tweet | Notification Review | Communications | Calendar | 0 | 1 | FALSE | 12
13 |  | 1 | Open House | Notification Review | Open House | PCP | 0 | 1 | FALSE | 13
14 |  | 1 | Virtual Information Session | Notification Review | Virtual Information Session | PCP | 0 | 1 | FALSE | 14
15 |  | 1 | Comment Period Time Limit Extension | Notification Review | PCP Time Limit Extension | Extension | 0 | 1 | FALSE | 15
16 | 15 | 1 | PCP Extended Announcement & Tweet | Notification Review | Communications | Calendar | 0 | 1 | FALSE | 16
17 | 15 | 1 | PCP Extended Milestone Bullet | Notification Review | Executive | Calendar | 0 | 1 | FALSE | 17
18 |  | 1 | s.38 Extension of Time Limit | Notification Review | Time Limit Extension | Extension | 0 | 1 | FALSE | 18
19 | 18 | 1 | Extension Announcement & Tweet | Notification Review | Communications | Calendar | 0 | 1 | FALSE | 19
20 | 18 | 1 | Time Limit Extended Milestone Bullet | Notification Review | Executive | Calendar | 0 | 1 | FALSE | 20
21 |  | 1 | s.45 Suspension of the Notification Process | Notification Review | Time Limit Suspension | Suspension | 0 | 1 | FALSE | 21
22 | 21 | 1 | Suspension Announcement & Tweet | Notification Review | Communications | Calendar | 0 | 1 | FALSE | 22
23 | 21 | 1 | Notification Process Suspended Milestone Bullet | Notification Review | Executive | Calendar | 0 | 1 | FALSE | 23
24 |  | 1 | s.45 Resumption of the Notification Process | Notification Review | Time Limit Suspension | Suspension | 0 | 1 | FALSE | 24
25 | 24 | 1 | Resumption Announcement & Tweet | Notification Review | Communications | Calendar | 0 | 1 | FALSE | 25
26 | 24 | 1 | Notification Process Resumed Milestone Bullet | Notification Review | Executive | Calendar | 0 | 1 | FALSE | 26
27 |  | 1 | Assessment Terminated s.39(d) | Notification Review | CEAO | Decision | 0 | 1 | FALSE | 27
28 | 27 | 1 | Termination Announcement & Tweet | Notification Review | Communications | Calendar | 0 | 1 | FALSE | 28
29 | 27 | 1 | Assessment Terminated Milestone Bullet | Notification Review | Executive | Calendar | 0 | 1 | FALSE | 29
30 |  | 1 | Project Withdrawn | Notification Review | EPD | Decision | 0 | 1 | FALSE | 30
31 | 30 | 1 | Withdrawal Announcement & Tweet | Notification Review | Communications | Calendar | 0 | 1 | FALSE | 31
32 | 30 | 1 | Project Withdrawn Milestone Bullet | Notification Review | Executive | Calendar | 0 | 1 | FALSE | 32
33 |  | 1 | Other | Notification Review | Other | Milestone | 0 | 1 | FALSE | 33
34 |  | 1 | Report Referred to Decision Maker | Notification Review | Report | Milestone | 50 | 1 | TRUE | 34
35 |  | 2 | Draft Notification Decision Milestone Bullets | Notification Decision | Generic | Milestone | 5 | 1 | TRUE | 35
36 | 35 | 2 | Draft Milestone Bullets Due | Notification Decision | Executive | Calendar | 0 | 1 | TRUE | 36
37 |  | 2 | Additional Information Submission | Notification Decision | Submission | Milestone | 0 | 1 | FALSE | 37
38 |  | 2 | s.38 Extension of Time Limit | Notification Decision | Time Limit Extension | Extension | 0 | 1 | FALSE | 38
39 | 38 | 2 | Extension Announcement & Tweet | Notification Decision | Communications | Calendar | 0 | 1 | FALSE | 39
40 | 38 | 2 | Time Limit Extended Milestone Bullet | Notification Decision | Executive | Calendar | 0 | 1 | FALSE | 40
41 |  | 2 | s.45 Suspension of the Notification Process | Notification Decision | Time Limit Suspension | Suspension | 0 | 1 | FALSE | 41
42 | 41 | 2 | Suspension Announcement & Tweet | Notification Decision | Communications | Calendar | 0 | 1 | FALSE | 42
43 | 41 | 2 | Notification Process Suspended Milestone Bullet | Notification Decision | Executive | Calendar | 0 | 1 | FALSE | 43
44 |  | 2 | s.45 Resumption of the Notification Process | Notification Decision | Time Limit Suspension | Suspension | 0 | 1 | FALSE | 44
45 | 44 | 2 | Resumption Announcement & Tweet | Notification Decision | Communications | Calendar | 0 | 1 | FALSE | 45
46 | 44 | 2 | Notification Process Resumed Milestone Bullet | Notification Decision | Executive | Calendar | 0 | 1 | FALSE | 46
47 |  | 2 | Assessment Terminated s.39(d) | Notification Decision | CEAO | Decision | 0 | 1 | FALSE | 47
48 | 47 | 2 | Termination Announcement & Tweet | Notification Decision | Communications | Calendar | 0 | 1 | FALSE | 48
49 | 47 | 2 | Assessment Terminated Milestone Bullet | Notification Decision | Executive | Calendar | 0 | 1 | FALSE | 49
50 |  | 2 | Project Withdrawn | Notification Decision | EPD | Decision | 0 | 1 | FALSE | 50
51 | 50 | 2 | Withdrawal Announcement & Tweet | Notification Decision | Communications | Calendar | 0 | 1 | FALSE | 51
52 | 50 | 2 | Project Withdrawn Milestone Bullet | Notification Decision | Executive | Calendar | 0 | 1 | FALSE | 52
53 |  | 2 | Other | Notification Decision | Other | Milestone | 0 | 1 | FALSE | 53
54 |  | 2 | Decision: Project Notification | Notification Decision | CEAO | Decision | 10 | 1 | TRUE | 54
55 | 54 | 2 | Notification Decision Announcement & Tweet | Notification Decision | Communications | Calendar | 0 | 1 | TRUE | 55
56 | 54 | 2 | Notification Decision Milestone Bullet | Notification Decision | Executive | Calendar | 0 | 1 | TRUE | 56