## Instructions
Cell Colors
This color means that the cell has a picklist Validation constraint.
This color means that the cell has a formula and should not be changed. Change the vLookup source.
This color means the cell is open to user input
Order of Data Entry
You need to do the Phases before Events, Events before Outcomes, and Outcomes before Actions
The No Field and Row Deletion
The No (number field) of each sheet is the Validation list of the next sheet. For example the Events sheet has the heading PhaseNo which pulls from the Phases sheet No cells.
To maintain the Data Validation for all the sheets, make sure you DELETE the Entire Row for every unused row in the sheet you are working on. IE select the entire row(s) and right-click > Delete.

## Phases
No | Name | WorkType | EAAct | NumberOfDays | Legislated | Color | Visibility | SortOrder
1 | Exemption Request Intake | Exemption Request | EA Act (2018) | 90 | FALSE | #FFFFFF | REGULAR | 1
2 | Exemption Early Engagement | Exemption Request | EA Act (2018) | 90 | TRUE | #FFFFFF | REGULAR | 2
3 | Exemption DPD Development (Proponent Time) | Exemption Request | EA Act (2018) | 365 | FALSE | #FFFFFF | REGULAR | 3
4 | Exemption Readiness Decision | Exemption Request | EA Act (2018) | 60 | FALSE | #FFFFFF | REGULAR | 4
5 | Exemption Decision | Exemption Request | EA Act (2018) | 30 | FALSE | #FFFFFF | REGULAR | 5
6 | Further Readiness Decision | Exemption Request | EA Act (2018) | 30 | FALSE | #FFFFFF | HIDDEN | 6

## Events
| No | Parent | PhaseNo | EventName | Phase | EventType | EventCategory | EventPosition | MultipleDays | StartAt | NumberOfDays | Visibility | SortOrder
| 1 |  | 1 | Initial Contact with Proponent | Exemption Request Intake | Meeting | Milestone | START | FALSE | 0 | 0 | MANDATORY | 1
| 2 |  | 1 | Project Presentation Meeting | Exemption Request Intake | Meeting | Milestone | INTERMEDIATE | FALSE | 28 | 0 | MANDATORY | 2
| 3 |  | 1 | Capacity Funding Estimate | Exemption Request Intake | Capacity Funding | Finance | INTERMEDIATE | FALSE | 60 | 0 | MANDATORY | 3
| 4 | 3 | 1 | Capacity Funding Estimate Due | Exemption Request Intake | Financial | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 4
| 5 |  | 1 | Submission of "Draft" Initial Project Description & Engagement Plan | Exemption Request Intake | Submission | Milestone | INTERMEDIATE | FALSE | 80 | 0 | MANDATORY | 5
| 6 |  | 1 | Draft IPD/EP Approval Milestone Bullet | Exemption Request Intake | Generic | Milestone | INTERMEDIATE | FALSE | 85 | 0 | MANDATORY | 6
| 7 | 6 | 1 | REMINDER: Draft IPD/EP Approval Milestone Bullet | Exemption Request Intake | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 7
x | 8 |  | 1 | "Draft" Initial Project Description & Engagement Plan Initial Review | Exemption Request Intake | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 90 | 0 | MANDATORY | 8
| 9 |  | 1 | Additional Information Submission | Exemption Request Intake | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 9
x | 10 |  | 1 | Submission Withdrawn | Exemption Request Intake | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 10
| 11 |  | 1 | Other | Exemption Request Intake | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 11
| 12 |  | 1 | Last Day of Exemption Request Intake (Date Capture Milestone) | Exemption Request Intake | Date Capture | Milestone | END | FALSE | 90 | 0 | MANDATORY | 12
x | 13 |  | 2 | Approval of IPD/EP Submission | Exemption Early Engagement | Submission | Milestone | START | FALSE | 0 | 0 | MANDATORY | 13
| 14 | 13 | 2 | Approval of IPD/EP Announcement & Tweet | Exemption Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 14
| 15 | 13 | 2 | Approval of IPD/EP Milestone Bullet | Exemption Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 15
| 16 |  | 2 | Notification sent to potential PINs | Exemption Early Engagement | Notification | Milestone | INTERMEDIATE | FALSE | 7 | 0 | MANDATORY | 16
| 17 |  | 2 | Comment Period | Exemption Early Engagement | Comment Period | PCP | INTERMEDIATE | TRUE | 14 | 30 | MANDATORY | 17
| 18 | 17 | 2 | PCP Coming Soon Announcement & Tweet | Exemption Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | MANDATORY | 18
| 19 | 17 | 2 | PCP Coming Soon Milestone Bullet | Exemption Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | MANDATORY | 19
| 20 | 17 | 2 | PCP Now Open Announcement & Tweet | Exemption Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 20
| 21 | 17 | 2 | PCP Ending Soon Announcement & Tweet | Exemption Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | MANDATORY | 21
| 22 |  | 2 | Early Engagement Capacity Funding Amounts Confirmed | Exemption Early Engagement | Capacity Funding | Finance | INTERMEDIATE | FALSE | 21 | 0 | MANDATORY | 22
| 23 | 22 | 2 | Early Engagement Capacity Funding Confirmation Due | Exemption Early Engagement | Financial | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 23
| 24 |  | 2 | Fee Order: Filing of Exemption Request | Exemption Early Engagement | Fee Order | Finance | INTERMEDIATE | FALSE | 30 | 0 | MANDATORY | 24
| 25 | 24 | 2 | Filing the Exemption Request Fee Order | Exemption Early Engagement | Financial | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 25
| 26 |  | 2 | PIN Notice of Intent Completed | Exemption Early Engagement | Generic | Milestone | INTERMEDIATE | FALSE | 80 | 0 | MANDATORY | 26
| 27 |  | 2 | Draft SoE Milestone Bullet | Exemption Early Engagement | Generic | Milestone | INTERMEDIATE | FALSE | 85 | 0 | MANDATORY | 27
| 28 | 27 | 2 | REMINDER: Draft SoE Milestone Bullet Due | Exemption Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 28
| 29 |  | 2 | Additional Information Submission | Exemption Early Engagement | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 29
| 30 |  | 2 | Federal Involvement Request | Exemption Early Engagement | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 30
| 31 | 30 | 2 | Federal Involvement Milestone Bullet | Exemption Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 31
x | 32 |  | 2 | Dispute Resolution Triggered | Exemption Early Engagement | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 32
| 33 | 32 | 2 | DR Triggered Announcement & Tweet | Exemption Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 33
| 34 | 32 | 2 | Dispute Resolution Milestone Bullet | Exemption Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 34
| 35 |  | 2 | Additional Comment Period | Exemption Early Engagement | Comment Period | PCP | INTERMEDIATE | TRUE | 0 | 30 | OPTIONAL | 35
| 36 | 35 | 2 | PCP Coming Soon Announcement & Tweet | Exemption Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | 36
| 37 | 35 | 2 | Additional PCP Milestone Bullet | Exemption Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | 37
| 38 | 35 | 2 | PCP Now Open Announcement & Tweet | Exemption Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 38
| 39 | 35 | 2 | PCP Ending Soon Announcement & Tweet | Exemption Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | OPTIONAL | 39
| 40 |  | 2 | Open House | Exemption Early Engagement | Open House | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 40
| 41 |  | 2 | Virtual Information Session | Exemption Early Engagement | Virtual Information Session | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 41
| 42 |  | 2 | Comment Period Time Limit Extension | Exemption Early Engagement | PCP Time Limit Extension | Extension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 42
| 43 | 42 | 2 | PCP Extended Announcement & Tweet | Exemption Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 43
| 44 | 42 | 2 | PCP Extended Milestone Bullet | Exemption Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 44
| 45 |  | 2 | s.38 Extension of Time Limit | Exemption Early Engagement | Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | 45
| 46 | 45 | 2 | Extension Announcement & Tweet | Exemption Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 46
| 47 | 45 | 2 | Time Limit Extended Milestone Bullet | Exemption Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 47
| 48 |  | 2 | s.45 Suspension of the Exemption Request Process | Exemption Early Engagement | Time Limit Suspension | Suspension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 48
| 49 | 48 | 2 | Exemption Request Process Suspension Announcement & Tweet | Exemption Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 49
| 50 | 48 | 2 | Exemption Request Process Suspended Milestone Bullet | Exemption Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 50
| 51 |  | 2 | s.45 Resumption of the Exemption Request Process | Exemption Early Engagement | Time Limit Resumption | Suspension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 51
| 52 | 51 | 2 | Exemption Request Process Resumption Announcement & Tweet | Exemption Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 52
| 53 | 51 | 2 | Exemption Request Process Resumed Milestone Bullet | Exemption Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 53
x | 54 |  | 2 | Exemption Request Terminated s.39(d) | Exemption Early Engagement | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 54
| 55 | 54 | 2 | Termination Announcement & Tweet | Exemption Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 55
| 56 | 54 | 2 | Exemption Request Terminated Milestone Bullet | Exemption Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 56
x | 57 |  | 2 | Submission Withdrawn | Exemption Early Engagement | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 57
| 58 | 57 | 2 | Withdrawal Announcement & Tweet | Exemption Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 58
| 59 | 57 | 2 | Project Withdrawn Milestone Bullet | Exemption Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 59
| 60 |  | 2 | Other | Exemption Early Engagement | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 60
x | 61 |  | 2 | Summary of Engagement | Exemption Early Engagement | Report | Milestone | END | FALSE | 90 | 0 | MANDATORY | 61
| 62 | 61 | 2 | Summary of Engagement Announcement & Tweet | Exemption Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 62
| 63 | 61 | 2 | Summary of Engagement Milestone Bullet | Exemption Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 63
| 64 |  | 3 | Start of DPD Development (Proponent Time) (Date Capture Milestone) | Exemption DPD Development (Proponent Time) | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 64
| 65 |  | 3 | Submission of "Draft" Detailed Project Description | Exemption DPD Development (Proponent Time) | Submission | Milestone | INTERMEDIATE | FALSE | 355 | 0 | MANDATORY | 65
| 66 |  | 3 | Draft DPD Receipt Milestone Bullet | Exemption DPD Development (Proponent Time) | Generic | Milestone | INTERMEDIATE | FALSE | 360 | 0 | MANDATORY | 66
| 67 | 66 | 3 | REMINDER: Draft DPD Receipt Milestone Bullet | Exemption DPD Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 67
x | 68 |  | 3 | "Draft" Detailed Project Description Initial Review | Exemption DPD Development (Proponent Time) | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 365 | 0 | MANDATORY | 68
| 69 |  | 3 | Additional Information Submission | Exemption DPD Development (Proponent Time) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 69
x | 70 |  | 3 | Dispute Resolution Triggered | Exemption DPD Development (Proponent Time) | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 70
| 71 | 70 | 3 | DR Triggered Announcement & Tweet | Exemption DPD Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 71
| 72 | 70 | 3 | Dispute Resolution Milestone Bullet | Exemption DPD Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 72
x | 73 |  | 3 | Exemption Request Terminated s.39(d) | Exemption DPD Development (Proponent Time) | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 73
| 74 | 73 | 3 | Termination Announcement & Tweet | Exemption DPD Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 74
| 75 | 73 | 3 | Exemption Request Terminated Milestone Bullet | Exemption DPD Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 75
x | 76 |  | 3 | Submission Withdrawn | Exemption DPD Development (Proponent Time) | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 76
| 77 | 76 | 3 | Withdrawal Announcement & Tweet | Exemption DPD Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 77
| 78 | 76 | 3 | Submission Withdrawn Milestone Bullet | Exemption DPD Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 78
| 79 |  | 3 | Other | Exemption DPD Development (Proponent Time) | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 79
| 80 |  | 3 | Last Day of DPD Development (Proponent Time) (Date Capture Milestone) | Exemption DPD Development (Proponent Time) | Date Capture | Milestone | END | FALSE | 365 | 0 | MANDATORY | 80
| 81 |  | 4 | Detailed Project Description Received | Exemption Readiness Decision | Submission | Milestone | START | FALSE | 0 | 0 | MANDATORY | 81
| 82 | 81 | 4 | DPD Received Announcement & Tweet | Exemption Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 82
| 83 | 81 | 4 | DPD Received Milestone Bullet | Exemption Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 83
| 84 |  | 4 | Report referred to CEAO | Exemption Readiness Decision | Report | Milestone | INTERMEDIATE | FALSE | 50 | 0 | MANDATORY | 84
| 85 |  | 4 | Draft Readiness Decision Milestone Bullet | Exemption Readiness Decision | Generic | Milestone | INTERMEDIATE | FALSE | 50 | 0 | MANDATORY | 85
| 86 | 85 | 4 | REMINDER: Draft Readiness Decision Milestone Bullet | Exemption Readiness Decision | Executive | Milestone | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 86
x | 87 |  | 4 | Decision: Readiness Decision | Exemption Readiness Decision | CEAO | Decision | INTERMEDIATE | FALSE | 55 | 0 | MANDATORY | 87
| 88 | 87 | 4 | Readiness Decision Announcement & Tweet | Exemption Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 88
| 89 | 87 | 4 | Readiness Decision Milestone Bullet (if Project proceeds to Exemption Decision) | Exemption Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 89
| 90 |  | 4 | Exemption Package Referred to Minister | Exemption Readiness Decision | Referral | Milestone | INTERMEDIATE | FALSE | 60 | 0 | MANDATORY | 90
| 91 |  | 4 | Additional Information Submission | Exemption Readiness Decision | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 91
x | 92 |  | 4 | Dispute Resolution Triggered | Exemption Readiness Decision | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 92
| 93 | 92 | 4 | DR Triggered Announcement & Tweet | Exemption Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 93
| 94 | 92 | 4 | Dispute Resolution Milestone Bullet | Exemption Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 94
x | 95 |  | 4 | Exemption Request Terminated s.39(d) | Exemption Readiness Decision | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 95
| 96 | 95 | 4 | Termination Announcement & Tweet | Exemption Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 96
| 97 | 95 | 4 | Exemption Request Terminated Milestone Bullet | Exemption Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 97
x | 98 |  | 4 | Submission Withdrawn | Exemption Readiness Decision | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 98
| 99 | 98 | 4 | Withdrawal Announcement & Tweet | Exemption Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 99
| 100 | 98 | 4 | Submission Withdrawn Milestone Bullet | Exemption Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 100
| 101 |  | 4 | Other | Exemption Readiness Decision | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 101
| 102 |  | 4 | Last Day of Exemption Request Readiness Decision (Date Capture Milestone) | Exemption Readiness Decision | Date Capture | Milestone | END | FALSE | 65 | 0 | MANDATORY | 102
| 103 |  | 5 | Exemption Decision Package Received by Minister | Exemption Decision | Generic | Milestone | START | FALSE | 0 | 0 | MANDATORY | 103
| 104 |  | 5 | Additional Information Submission | Exemption Decision | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 104
x | 105 |  | 5 | Exemption Request Terminated s.39(d) | Exemption Decision | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 105
| 106 | 105 | 5 | Termination Announcement & Tweet | Exemption Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 106
| 107 | 105 | 5 | Exemption Request Terminated Milestone Bullet | Exemption Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 107
x | 108 |  | 5 | Submission Withdrawn | Exemption Decision | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 108
| 109 | 108 | 5 | Withdrawal Announcement & Tweet | Exemption Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 109
| 110 | 108 | 5 | Submission Withdrawn Milestone Bullet | Exemption Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 110
| 111 |  | 5 | Other | Exemption Decision | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 111
x | 112 |  | 5 | Minister's Exemption Request Decision | Exemption Decision | Minister | Decision | END | FALSE | 30 | 0 | MANDATORY | 112
| 113 | 112 | 5 | Exemption Request Decision Announcement & Tweet (unless return to CEAO) | Exemption Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 113
| 114 |  | 6 | DPD & Exemption Request Referred to CEAO for Further Decision | Further Readiness Decision | Referral | Milestone | START | FALSE | 0 | 0 | MANDATORY | 114
| 115 |  | 6 | Additional Information Submission | Further Readiness Decision | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 115
x | 116 |  | 6 | EAC Assessment Terminated s.39(d) | Further Readiness Decision | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 116
| 117 | 116 | 6 | Termination Announcement & Tweet | Further Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 117
| 118 | 116 | 6 | EAC Assessment Terminated Milestone Bullet | Further Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 118
x | 119 |  | 6 | Project Withdrawn | Further Readiness Decision | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 119
| 120 | 119 | 6 | Withdrawal Announcement & Tweet | Further Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 120
| 121 | 119 | 6 | Project Withdrawn Milestone Bullet | Further Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 121
| 122 |  | 6 | Other | Further Readiness Decision | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 122
x | 123 |  | 6 | Decision: Further Readiness Decision | Further Readiness Decision | CEAO | Decision | END | FALSE | 30 | 0 | MANDATORY | 123
| 124 | 123 | 6 | Further Readiness Decision Announcement & Tweet | Further Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 124
| 125 | 123 | 6 | Further Readiness Decision Milestone Bullet (if Project proceeds to Process Planning) | Further Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 125

## Outcomes
No | TemplateNo | TemplateName | OutcomeName | SortOrder
1 | 8 | "Draft" Initial Project Description & Engagement Plan Initial Review | Initial Review of "Draft" Initial Project Description is POSITIVE | 1
2 | 8 | "Draft" Initial Project Description & Engagement Plan Initial Review | Initial Review of "Draft" Initial Project Description is NEGATIVE | 2
3 | 10 | Submission Withdrawn | Proponent withdraws Submission from the Exemption Request process | 3
4 | 13 | Approval of IPD/EP Submission | Starts the "clock" for EAC Assessment | 4
5 | 32 | Dispute Resolution Triggered | Dispute Resolution is started | 5
6 | 54 | Exemption Request Terminated s.39(d) | Exemption Request is Terminated under s.39(d) of Act | 6
7 | 57 | Submission Withdrawn | Proponent withdraws Submission from the Exemption Request process | 7
8 | 61 | Summary of Engagement | End of Early Engagement PHASE, start of DPD Development (Proponent Time) PHASE | 8
9 | 68 | "Draft" Detailed Project Description Initial Review | Draft Detailed Project Description Initial Review is POSITIVE | 9
10 | 68 | "Draft" Detailed Project Description Initial Review | Draft Detailed Project Description Initial Review is NEGATIVE | 10
11 | 70 | Dispute Resolution Triggered | Dispute Resolution is started | 11
12 | 73 | Exemption Request Terminated s.39(d) | Exemption Request is Terminated under s.39(d) of Act | 12
13 | 76 | Submission Withdrawn | Proponent withdraws Submission from the Exemption Request process | 13
14 | 87 | Decision: Readiness Decision | Proponent must submit a Revised DPD | 14
15 | 87 | Decision: Readiness Decision | Project is Referred to Minister for Exemption | 15
16 | 92 | Dispute Resolution Triggered | Dispute Resolution is started | 16
17 | 95 | Exemption Request Terminated s.39(d) | Exemption Request is Terminated under s.39(d) of Act | 17
18 | 98 | Submission Withdrawn | Proponent withdraws Submission from the Exemption Request process | 18
19 | 105 | Exemption Request Terminated s.39(d) | Exemption Request is Terminated under s.39(d) of Act | 19
20 | 108 | Submission Withdrawn | Proponent withdraws Submission from the Exemption Request process | 20
21 | 112 | Minister's Exemption Request Decision | Project is Exempt from Requiring an EAC | 21
22 | 112 | Minister's Exemption Request Decision | Refer the Project to the CEAO for Further Decision | 22
23 | 116 | EAC Assessment Terminated s.39(d) | Exemption Request is Terminated under s.39(d) of Act | 23
24 | 119 | Project Withdrawn | Proponent withdraws Submission from the Exemption Request process | 24
25 | 123 | Decision: Further Readiness Decision | Proponent must submit a Revised DPD | 25
26 | 123 | Decision: Further Readiness Decision | Project moves to Process Planning | 26
27 |  |  |  | 27
28 |  |  |  | 28
29 |  |  |  | 29
30 |  |  |  | 30
31 |  |  |  | 31
32 |  |  |  | 32
33 |  |  |  | 33
34 |  |  |  | 34
35 |  |  |  | 35
36 |  |  |  | 36
37 |  |  |  | 37
38 |  |  |  | 38
39 |  |  |  | 39
40 |  |  |  | 40
41 |  |  |  | 41
42 |  |  |  | 42
43 |  |  |  | 43
44 |  |  |  | 44
45 |  |  |  | 45
46 |  |  |  | 46
47 |  |  |  | 47
48 |  |  |  | 48
49 |  |  |  | 49
50 |  |  |  | 50
51 |  |  |  | 51
52 |  |  |  | 52
53 |  |  |  | 53
54 |  |  |  | 54
55 |  |  |  | 55
56 |  |  |  | 56
57 |  |  |  | 57
58 |  |  |  | 58
59 |  |  |  | 59
60 |  |  |  | 60
61 |  |  |  | 61
62 |  |  |  | 62
63 |  |  |  | 63
64 |  |  |  | 64
65 |  |  |  | 65
66 |  |  |  | 66
67 |  |  |  | 67
68 |  |  |  | 68
69 |  |  |  | 69
70 |  |  |  | 70
71 |  |  |  | 71
72 |  |  |  | 72
73 |  |  |  | 73
74 |  |  |  | 74
75 |  |  |  | 75
76 |  |  |  | 76
77 |  |  |  | 77
78 |  |  |  | 78
79 |  |  |  | 79
80 |  |  |  | 80
81 |  |  |  | 81
82 |  |  |  | 82
83 |  |  |  | 83
84 |  |  |  | 84
85 |  |  |  | 85
86 |  |  |  | 86
87 |  |  |  | 87
88 |  |  |  | 88
89 |  |  |  | 89
90 |  |  |  | 90
91 |  |  |  | 91
92 |  |  |  | 92
93 |  |  |  | 93
94 |  |  |  | 94
95 |  |  |  | 95
96 |  |  |  | 96
97 |  |  |  | 97
98 |  |  |  | 98
99 |  |  |  | 99
100 |  |  |  | 100

## Actions
No | OutcomeNo | OutcomeName | ActionName | ActionDescription | AdditionalParams | SortOrder
1 | 1 | Initial Review of "Draft" Initial Project Description is POSITIVE | SetEventDate | Set ANTICIPATED of "Early Engagement ¦ Approval of IPD/EP Submission" to thisEventACTUAL +1 | {"phase_name":"Exemption Early Engagement","work_type_id": 5, "ea_act_id": 3, "event_name": "Approval of IPD/EP Submission", "start_at": 1 } | 1
2 | 2 | Initial Review of "Draft" Initial Project Description is NEGATIVE | AddEvent | Add a copy of "Submission of "Draft" Initial Project Description & Engagement Plan" to thisPhase at thisEventACTUAL +21 | {"phase_name":"Exemption Request Intake","work_type_id": 5, "ea_act_id": 3, "event_name": "Submission of "Draft" Initial Project Description & Engagement Plan", "start_at": 21 } | 2
3 | 2 | Initial Review of "Draft" Initial Project Description is NEGATIVE | AddEvent | Add a copy of ""Draft" Initial Project Description & Engagement Plan Initial Review" to thisPhase at thisEventACTUAL +28 | {"phase_name":"Exemption Request Intake","work_type_id": 5, "ea_act_id": 3, "event_name": "\"Draft\" Initial Project Description & Engagement Plan Initial Review", "start_at": 28 } | 3
4 | 3 | Proponent withdraws Submission from the Exemption Request process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 4
6 | 3 | Proponent withdraws Submission from the Exemption Request process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 6
7 | 3 | Proponent withdraws Submission from the Exemption Request process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 7
8 | 4 | Starts the "clock" for EAC Assessment | LockWorkStartDate | Set the workStartDate to thisEventACTUAL | {"start_date_locked": true} | 8
9 | 5 | Dispute Resolution is started | CreateWork | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {"work_type":15} | 9
10 | 6 | Exemption Request is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 10
12 | 6 | Exemption Request is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 12
13 | 6 | Exemption Request is Terminated under s.39(d) of Act | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 13
14 | 7 | Proponent withdraws Submission from the Exemption Request process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 14
16 | 7 | Proponent withdraws Submission from the Exemption Request process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 16
17 | 7 | Proponent withdraws Submission from the Exemption Request process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 17
18 | 8 | End of Early Engagement PHASE, start of DPD Development (Proponent Time) PHASE | SetEventDate | set "DPD Development (Proponent Time) ¦ Start of Detailed Project Description Development (Date Capture Milestone)" ACTUAL to thisEventActual +1 | {"phase_name":"Exemption DPD Development (Proponent Time)","work_type_id": 5, "ea_act_id": 3, "event_name": "Start of DPD Development (Proponent Time) (Date Capture Milestone)", "start_at": 1} | 18
19 | 9 | Draft Detailed Project Description Initial Review is POSITIVE | SetEventDate | Set ANTICIPATED of "Readiness Decision ¦ Detailed Project Description Received" to thisEventACTUAL +1 | {"phase_name":"Exemption Readiness Decision","work_type_id": 5, "ea_act_id": 3, "event_name": "Detailed Project Description Received", "start_at": 1} | 19
20 | 10 | Draft Detailed Project Description Initial Review is NEGATIVE | AddEvent | Add a copy of "Submission of Detailed Project Description" to thisPhase at thisEventACTUAL +21 | {"phase_name":"Exemption DPD Development (Proponent Time)","work_type_id": 5, "ea_act_id": 3, "event_name": "Submission of \"Draft\" Detailed Project Description", "start_at": 21 } | 20
21 | 10 | Draft Detailed Project Description Initial Review is NEGATIVE | AddEvent | Add a copy of ""Draft" Detailed Project Description Initial Review" to thisPhase at thisEventACTUAL +28 | {"phase_name":"Exemption DPD Development (Proponent Time)","work_type_id": 5, "ea_act_id": 3, "event_name": "\"Draft\" Detailed Project Description Initial Review", "start_at": 28 } | 21
22 | 11 | Dispute Resolution is started | CreateWork | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {"work_type":15} | 22
23 | 12 | Exemption Request is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 23
25 | 12 | Exemption Request is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 25
26 | 12 | Exemption Request is Terminated under s.39(d) of Act | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 26
27 | 13 | Proponent withdraws Submission from the Exemption Request process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 27
29 | 13 | Proponent withdraws Submission from the Exemption Request process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 29
30 | 13 | Proponent withdraws Submission from the Exemption Request process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 30
31 | 14 | Proponent must submit a Revised DPD | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_phases":false} | 31
32 | 14 | Proponent must submit a Revised DPD | ChangePhaseEndEvent | Set "Readiness Decision ¦ Decision: Readiness Decision" to PHASE END EVENT | {"phase_name":"Exemption Readiness Decision","work_type_id": 5, "ea_act_id": 3, "event_name": "Decision: Readiness Decision" } | 32
33 | 14 | Proponent must submit a Revised DPD | AddPhase | addPhase "DPD Development (Proponent Time)" (copy of the origal PHASE) | {"phase_name":"Exemption DPD Development (Proponent Time)","work_type_id": 5, "ea_act_id": 3, "new_name": "Exemption DPD Development (Proponent Time)", "legislated": false } | 33
34 | 14 | Proponent must submit a Revised DPD | AddPhase | addPhase "Readiness Decision" (copy of the origal PHASE) | {"phase_name":"Exemption Readiness Decision","work_type_id": 5, "ea_act_id": 3, "new_name": "Exemption Readiness Decision", "legislated": false } | 34
35 | 14 | Proponent must submit a Revised DPD | SetEventDate | Set "DPD Development (Proponent Time) ¦ Start of Detailed Project Description Development" ACTUAL to thisEventActual +1 | {"phase_name":"Exemption DPD Development (Proponent Time)","work_type_id": 5, "ea_act_id": 3, "event_name": "Start of DPD Development (Proponent Time) (Date Capture Milestone)", "start_at": 1 } | 35
37 | 16 | Dispute Resolution is started | CreateWork | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {"work_type":15} | 37
38 | 17 | Exemption Request is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 38
40 | 17 | Exemption Request is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 40
41 | 17 | Exemption Request is Terminated under s.39(d) of Act | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 41
42 | 18 | Proponent withdraws Submission from the Exemption Request process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 42
44 | 18 | Proponent withdraws Submission from the Exemption Request process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 44
45 | 18 | Proponent withdraws Submission from the Exemption Request process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 45
46 | 19 | Exemption Request is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 46
48 | 19 | Exemption Request is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 48
49 | 19 | Exemption Request is Terminated under s.39(d) of Act | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 49
50 | 20 | Proponent withdraws Submission from the Exemption Request process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 50
52 | 20 | Proponent withdraws Submission from the Exemption Request process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 52
53 | 20 | Proponent withdraws Submission from the Exemption Request process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 53
54 | 21 | Project is Exempt from Requiring an EAC | SetWorkState | Set workState to COMPLETED | {"work_state": "COMPLETED"} | 54
55 | 21 | Project is Exempt from Requiring an EAC | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 55
56 | 22 | Refer the Project to the CEAO for Further Decision | AddPhase | Set "Further Readiness Decision" PHASE to ACTIVE (show it) | {"phase_name":"Further Readiness Decision","work_type_id": 5, "ea_act_id": 3, "new_name": "Further Readiness Decision", "legislated": false } | 56
57 | 22 | Refer the Project to the CEAO for Further Decision | SetEventDate | Set "Further Readiness Decision ¦ Readiness Decision Report referred to CEAO for Further Decision" ACTUAL to thisEventACTUAL +1 | {"phase_name":"Further Readiness Decision","work_type_id": 5, "ea_act_id": 3, "event_name": "Readiness Decision Report referred to CEAO for Further Decision", "start_at": 1} | 57
58 | 23 | Exemption Request is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 58
60 | 23 | Exemption Request is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 60
61 | 23 | Exemption Request is Terminated under s.39(d) of Act | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 61
62 | 24 | Proponent withdraws Submission from the Exemption Request process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 62
64 | 24 | Proponent withdraws Submission from the Exemption Request process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 64
65 | 24 | Proponent withdraws Submission from the Exemption Request process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 65
66 | 25 | Proponent must submit a Revised DPD | AddPhase | addPhase "DPD Development (Proponent Time)" (copy of the origal PHASE) | {"phase_name":"Exemption DPD Development (Proponent Time)","work_type_id": 5, "ea_act_id": 3, "new_name": "Exemption DPD Development (Proponent Time)", "legislated": false } | 66
67 | 25 | Proponent must submit a Revised DPD | AddPhase | addPhase "Readiness Decision" (copy of the origal PHASE) | {"phase_name":"Exemption Readiness Decision","work_type_id": 5, "ea_act_id": 3, "new_name": "Exemption Readiness Decision", "legislated": false } | 67
68 | 25 | Proponent must submit a Revised DPD | SetEventDate | Set "DPD Development (Proponent Time) ¦ Start of Detailed Project Description Development" ACTUAL to thisEventActual +1 | {"phase_name":"Exemption DPD Development (Proponent Time)","work_type_id": 5, "ea_act_id": 3, "event_name": "Start of DPD Development (Proponent Time) (Date Capture Milestone)", "start_at": 1 } | 68
69 | 26 | Project moves to Process Planning | SetWorkState | Set workState to COMPLETE | {} | 69
70 | 26 | Project moves to Process Planning | CreateWork | Create a new WORK: "EAC Assessment" and link to thisWorkLinkedProject | {} | 70

## ActionBackup
36 | 15 | Project is Referred to Minister for Exemption | NO ACTION | No Action Needed | {} | 36

## Lookups
WorkType | EA Act | Legislated |  | Event Type | Event Category | Mandatory | ActionName | Event Position | Multiple Days
Project Notification | EA Act (2018) | TRUE | Milestone | Generic | Milestone | TRUE | AllEventsDeactivated | START | TRUE
Minister's Designation | EA Act (2002) | FALSE | Milestone | Meeting | Calendar | FALSE | AllEventsDeleted | INTERMEDIATE | FALSE
CEAO's Designation | EA Act (1996) |  | Milestone | Notification | Decision |  | CloseEverything | END
EAC Assessment |  |  | Milestone | Order | Finance |  | CloseWork
Exemption Request |  |  | Milestone | Referral | PCP |  | CompleteCurrentPhase
Dispute Resolution |  |  | Milestone | Report | Extension |  | CreateNewWork
EAC/Order Amendment |  |  | Milestone | Request | Suspension |  | DisableWorkStartDate
Document Review |  |  | Milestone | Submission |  |  | DuplicatePhase
EAC Extension |  |  | Milestone | Other
Substantial Start Decision |  |  | Milestone | Date Capture
EAC/Order Transfer |  |  | Extension | Time Limit Extension
EAC/Order Suspension |  |  | Extension | PCP Time Limit Extension
EAC/Order Cancellation |  |  | Suspension | Time Limit Suspension
Other |  |  | Suspension | Time Limit Resumption
|  |  | Decision | EAC Ministers
|  |  | Decision | Minister
|  |  | Decision | CEAO
|  |  | Decision | ADM
|  |  | Decision | EPD
|  |  | Decision | PAD (Lead)
|  |  | Decision | Reviewer
|  |  | Decision | Federal
|  |  | Decision | Other
|  |  | PCP | Comment Period
|  |  | PCP | Open House
|  |  | PCP | Virtual Information Session
|  |  | PCP | Other
|  |  | Calendar | Communications
|  |  | Calendar | Executive
|  |  | Calendar | Financial
|  |  | Calendar | Work
|  |  | Calendar | Other
|  |  | Finance | Capacity Funding
|  |  | Finance | Fee Order
|  |  | Finance | Penalties
|  |  | Finance | Administrative
|  |  | Finance | Other