## Phases
No | Name | WorkType | EAAct | NumberOfDays | Legislated | Color | Visibility | SortOrder | DayZero
1 | Transfer Pre-Application | EAC/Order Transfer | EA Act (2018) | 60 | 0 | #FFFFFF | REGULAR | 1 | 1
2 | Transfer Application Review | EAC/Order Transfer | EA Act (2018) | 120 | 0 | #FFFFFF | REGULAR | 2 | 1
3 | Transfer Decision | EAC/Order Transfer | EA Act (2018) | 30 | 0 | #FFFFFF | REGULAR | 3 | 1

## Events
No | Parent | PhaseNo | EventName | Phase | EventType | EventCategory | EventPosition | MultipleDays | StartAt | NumberOfDays | Visibility | SortOrder
1 |  | 1 | Initial contact with Holder | Transfer Pre-Application | Date Capture | Milestone | START | 0 | 0 | 0 | MANDATORY | 1
2 |  | 1 | Notification of FNs | Transfer Pre-Application | Generic | Milestone | INTERMEDIATE | 0 | 14 | 0 | SUGGESTED | 2
3 |  | 1 | Additional Information Submission | Transfer Pre-Application | Submission | Milestone | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 3
4 |  | 1 | Meeting with Holder | Transfer Pre-Application | Meeting | Milestone | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 4
5 |  | 1 | Direct Submission of Transfer Application - DELETE this Pre-Application Phase! | Transfer Pre-Application | PAD (Lead) | Decision | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 5
6 |  | 1 | Document Submitted to EAO for "Initial Review" | Transfer Pre-Application | Submission | Milestone | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 6
7 | 6 | 1 | EAO's Viewpoint on Submitted Document | Transfer Pre-Application | PAD (Lead) | Decision | INTERMEDIATE | 0 | 10 | 0 | OPTIONAL | 7
8 |  | 1 | Delegation of Transfer Decision to Minister | Transfer Pre-Application | Minister | Decision | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 8
9 |  | 1 | Transfer Application Withdrawn | Transfer Pre-Application | EPD | Decision | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 9
10 |  | 1 | Other | Transfer Pre-Application | Other | Milestone | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 10
11 |  | 1 | Day before Application Submitted | Transfer Pre-Application | Date Capture | Milestone | END | 0 | 60 | 0 | MANDATORY | 11
12 |  | 2 | Transfer Application Received | Transfer Application Review | Submission | Milestone | START | 0 | 0 | 0 | MANDATORY | 12
13 | 12 | 2 | Transfer Application Received Announcment & Tweet | Transfer Application Review | Communications | Calendar | INTERMEDIATE | 0 | 0 | 0 | MANDATORY | 13
14 | 12 | 2 | Transfer Application Received Milestone Bullet | Transfer Application Review | Executive | Calendar | INTERMEDIATE | 0 | 0 | 0 | MANDATORY | 14
15 |  | 2 | Transfer Application Circulated to FNs | Transfer Application Review | Generic | Milestone | INTERMEDIATE | 0 | 14 | 0 | SUGGESTED | 15
16 |  | 2 | Draft EAC/Exemption Transfer Report | Transfer Application Review | Report | Milestone | INTERMEDIATE | 0 | 100 | 0 | SUGGESTED | 16
17 |  | 2 | Additional Information Submission | Transfer Application Review | Submission | Milestone | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 17
18 |  | 2 | Document Submitted to EAO for "Initial Review" | Transfer Application Review | Submission | Milestone | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 18
19 | 18 | 2 | EAO's Viewpoint on Submitted Document | Transfer Application Review | PAD (Lead) | Decision | INTERMEDIATE | 0 | 10 | 0 | OPTIONAL | 19
20 |  | 2 | Delegation of Transfer Decision to Minister | Transfer Application Review | PAD (Lead) | Decision | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 20
21 |  | 2 | Transfer Application Withdrawn | Transfer Application Review | EPD | Decision | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 21
22 | 21 | 2 | Transfer Application Withdrawal Announcement & Tweet | Transfer Application Review | Communications | Calendar | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 22
23 | 21 | 2 | Transfer Application Withdrawn Milestone Bullet | Transfer Application Review | Executive | Calendar | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 23
24 |  | 2 | Other | Transfer Application Review | Other | Milestone | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 24
25 |  | 2 | Transfer Decision Package referred to Decision Maker | Transfer Application Review | Referral | Milestone | END | 0 | 120 | 0 | MANDATORY | 25
26 |  | 3 | Transfer Decision Package received by Decision Maker | Transfer Decision | Date Capture | Milestone | START | 0 | 0 | 0 | MANDATORY | 26
27 |  | 3 | Additional Information Submission | Transfer Decision | Submission | Milestone | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 27
28 |  | 3 | Delegation of Transfer Decision to Minister | Transfer Decision | PAD (Lead) | Decision | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 28
29 |  | 3 | Transfer Application Withdrawn | Transfer Decision | EPD | Decision | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 29
30 | 29 | 3 | Transfer Application Withdrawal Announcement & Tweet | Transfer Decision | Communications | Calendar | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 30
31 | 29 | 3 | Transfer Application Withdrawn Milestone Bullet | Transfer Decision | Executive | Calendar | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 31
32 |  | 3 | Other | Transfer Decision | Other | Milestone | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 32
33 |  | 3 | Decision Maker's Transfer Decision | Transfer Decision | CEAO | Decision | END | 0 | 0 | 0 | MANDATORY | 33
34 | 33 | 3 | EAC/Exemption Transfer Decision Announcement & Tweet | Transfer Decision | Communications | Calendar | INTERMEDIATE | 0 | 0 | 0 | MANDATORY | 34
35 | 33 | 3 | EAC/Exemption Transfer Decision Milestone Bullet | Transfer Decision | Executive | Calendar | INTERMEDIATE | 0 | 0 | 0 | MANDATORY | 35
36 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 36
37 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 37
38 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 38
39 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 39
40 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 40
41 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 41
42 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 42
43 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 43
44 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 44
45 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 45
46 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 46
47 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 47
48 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 48
49 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 49
50 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 50
51 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 51
52 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 52
53 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 53
54 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 54
55 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 55
56 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 56
57 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 57
58 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 58
59 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 59
60 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 60
61 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 61
62 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 62
63 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 63
64 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 64
65 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 65
66 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 66
67 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 67
68 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 68
69 | [6 empty] | INTERMEDIATE | 0 | 0 | 0 |  | 69

## Outcomes
No | TemplateNo | TemplateName | OutcomeName | OutcomeDescription | SortOrder
1 | 5 | Direct Submission of Transfer Application - DELETE this Pre-Application Phase! | Delete Pre-Application Phase | Delete the "Transfer Pre-Application" PHASE and go directly to "Transfer Application Review" | 1
2 | 7 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is POSITIVE | EAO takes a POSITIVE viewpoint on the information submitted | 2
3 | 7 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is NEGATIVE | EAO takes a NEGATIVE viewpoint on the information submitted | 3
4 | 8 | Delegation of Transfer Decision to Minister | Minister to Make Transfer Decision | The Decision Maker on this EAC/Exemption Order Transfer will be the Minister | 4
5 | 9 | Transfer Application Withdrawn | Holder Withdraws Transfer Application | The Holder withdraws their EAC/Exemption Order Transfer Request Application | 5
6 | 19 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is POSITIVE | EAO takes a POSITIVE viewpoint on the information submitted | 6
7 | 19 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is NEGATIVE | EAO takes a NEGATIVE viewpoint on the information submitted | 7
8 | 20 | Delegation of Transfer Decision to Minister | Minister to Make Transfer Decision | The Decision Maker on this EAC/Exemption Order Transfer will be the Minister | 8
9 | 21 | Transfer Application Withdrawn | Holder Withdraws Transfer Application | The Holder withdraws their EAC/Exemption Order Transfer Request Application | 9
10 | 28 | Delegation of Transfer Decision to Minister | Minister to Make Transfer Decision | The Decision Maker on this EAC/Exemption Order Transfer will be the Minister | 10
11 | 29 | Transfer Application Withdrawn | Holder Withdraws Transfer Application | The Holder withdraws their EAC/Exemption Order Transfer Request Application | 11
12 | 33 | Decision Maker's Transfer Decision | EAC/Order Transfer is Granted | The Holder's Request to Transfer their EAC/Exemption Order is GRANTED | 12
13 | 33 | Decision Maker's Transfer Decision | EAC/Order Transfer is Refused | The Holder's Request to Transfer their EAC/Exemption Order is REFUSED | 13
14 |  |  |  |  | 14
15 |  |  |  |  | 15
16 |  |  |  |  | 16
17 |  |  |  |  | 17
18 |  |  |  |  | 18
19 |  |  |  |  | 19
20 |  |  |  |  | 20
21 |  |  |  |  | 21
22 |  |  |  |  | 22
23 |  |  |  |  | 23
24 |  |  |  |  | 24
25 |  |  |  |  | 25
26 |  |  |  |  | 26
27 |  |  |  |  | 27
28 |  |  |  |  | 28
29 |  |  |  |  | 29
30 |  |  |  |  | 30
31 |  |  |  |  | 31
32 |  |  |  |  | 32
33 |  |  |  |  | 33
34 |  |  |  |  | 34
35 |  |  |  |  | 35

## Actions
No | OutcomeNo | OutcomeName | ActionName | ActionDescription | AdditionalParams | SortOrder
1 | 1 | Delete Pre-Application Phase | SetEventDate | Set "Transfer Application Review ¦ Transfer Application Received" ANTICIPATED to thisWorkStartDate | {"phase_name":"Transfer Application Review","work_type_id": 11, "ea_act_id": 3, "event_name": "Transfer Application Received", "start_at": 0 } | 1
2 | 1 | Delete Pre-Application Phase | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events": false} | 2
3 | 1 | Delete Pre-Application Phase | SetPhasesStatus | Set thisPhase to INACTIVE | [{"phase_name":"Transfer Pre-Application","work_type_id": 11, "ea_act_id": 3, "is_active": false }] | 3
4 | 2 | EAO's Viewpoint is POSITIVE | NONE | No Action | {} | 4
5 | 3 | EAO's Viewpoint is NEGATIVE | NONE | No Action | {} | 5
6 | 4 | Minister to Make Transfer Decision | SetWorkDecisionMaker | Set thisWorkDecisionMaker to currentMinisterEnvironment | {"position_id": 8} | 6
7 | 5 | Holder Withdraws Transfer Application | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases": false} | 7
8 | 5 | Holder Withdraws Transfer Application | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events": false} | 8
9 | 5 | Holder Withdraws Transfer Application | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 9
10 | 6 | EAO's Viewpoint is POSITIVE | NONE | No Action | {} | 10
11 | 7 | EAO's Viewpoint is NEGATIVE | NONE | No Action | {} | 11
12 | 8 | Minister to Make Transfer Decision | SetWorkDecisionMaker | Set thisWorkDecisionMaker to currentMinisterEnvironment | {"position_id": 8} | 12
13 | 9 | Holder Withdraws Transfer Application | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases": false} | 13
14 | 9 | Holder Withdraws Transfer Application | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events": false} | 14
15 | 9 | Holder Withdraws Transfer Application | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 15
16 | 10 | Minister to Make Transfer Decision | SetWorkDecisionMaker | Set thisWorkDecisionMaker to currentMinisterEnvironment | {"position_id": 8} | 16
17 | 11 | Holder Withdraws Transfer Application | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases": false} | 17
18 | 11 | Holder Withdraws Transfer Application | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events": false} | 18
19 | 11 | Holder Withdraws Transfer Application | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 19
20 | 12 | EAC/Order Transfer is Granted | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 20
21 | 13 | EAC/Order Transfer is Refused | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39 | [5 empty] | 39

## Lookups
WorkType | EA Act | Legislated |  | Event Type | Event Category | Visibility | ActionName | Event Position | Multiple Days | Action Name
Project Notification | EA Act (2018) | 1 | Milestone | Generic | Milestone | MANDATORY | AllEventsDeactivated | START | 1 | AddEvent
Minister's Designation | EA Act (2002) | 0 | Milestone | Meeting | Calendar | SUGGESTED | AllEventsDeleted | INTERMEDIATE | 0 | AddPhase
CEAO's Designation | EA Act (1996) |  | Milestone | Notification | Decision | OPTIONAL | CloseEverything | END |  | ChangePhaseEndEvent
EAC Assessment |  |  | Milestone | Order | Finance | HIDDEN | CloseWork |  |  | CreateWork
Exemption Request |  |  | Milestone | Referral | PCP |  | CompleteCurrentPhase |  |  | LockWorkStartDate
Dispute Resolution |  |  | Milestone | Report | Extension |  | CreateNewWork |  |  | SetEventDate
EAC/Order Amendment |  |  | Milestone | Request | Suspension |  | DisableWorkStartDate |  |  | SetEventStatus
Document Review |  |  | Milestone | Submission |  |  | DuplicatePhase |  |  | SetFederalInvolvement
EAC Extension |  |  | Milestone | Other | [5 empty] | SetPhaseStatus
Substantial Start Decision |  |  | Milestone | Date Capture | [5 empty] | SetProjectState
EAC/Order Transfer |  |  | Extension | Time Limit Extension | [5 empty] | SetProjectStatus
EAC/Order Suspension |  |  | Extension | PCP Time Limit Extension | [5 empty] | SetWorkDecisionMaker
EAC/Order Cancellation |  |  | Suspension | Time Limit Suspension | [5 empty] | SetWorkState
Other |  |  | Suspension | Time Limit Resumption
|  |  | Decision | EAC Ministers
|  |  | Decision | Minister
|  |  | Decision | CEAO
|  |  | Decision | ADM
|  |  | Decision | EPD
|  |  | Decision | PAD (Lead)
|  |  | Decision | Reviewer
|  |  | Decision | Federal
|  |  | Decision | Other
|  |  | PCP | Comment Period
|  |  | PCP | Open House
|  |  | PCP | Virtual Information Session
|  |  | PCP | Other
|  |  | Calendar | Communications
|  |  | Calendar | Executive
|  |  | Calendar | Financial
|  |  | Calendar | Work
|  |  | Calendar | Other
|  |  | Finance | Capacity Funding
|  |  | Finance | Fee Order
|  |  | Finance | Penalties
|  |  | Finance | Administrative
|  |  | Finance | Other