## Instructions
Cell Colors
This color means that the cell has a picklist Validation constraint.
This color means that the cell has a formula and should not be changed. Change the vLookup source.
This color means the cell is open to user input
Order of Data Entry
You need to do the Phases before Events, Events before Outcomes, and Outcomes before Actions
The No Field and Row Deletion
The No (number field) of each sheet is the Validation list of the next sheet. For example the Events sheet has the heading PhaseNo which pulls from the Phases sheet No cells.
To maintain the Data Validation for all the sheets, make sure you DELETE the Entire Row for every unused row in the sheet you are working on. IE select the entire row(s) and right-click > Delete.

## Phases
No | Name | WorkType | EAAct | NumberOfDays | Legislated | Color | SortOrder
1 | Project Notification Intake | Project Notification | EA Act (2018) | 14 | FALSE | #FFFFFF | 1
2 | Project Notification Review | Project Notification | EA Act (2018) | 50 | TRUE | #FFFFFF | 2
3 | Project Notification Decision | Project Notification | EA Act (2018) | 10 | TRUE | #FFFFFF | 3

## Events
No | Parent | PhaseNo | EventName | Phase | EventType | EventCategory | EventPosition | MultipleDays | StartAt | NumberOfDays | Mandatory | SortOrder
1 |  | 1 | Initial Contact with Proponent | Project Notification Intake | Meeting | Milestone | START | FALSE | 0 | 0 | TRUE | 1
2 |  | 1 | Submission of "Draft" Project Notification | Project Notification Intake | Submission | Milestone | INTERMEDIATE | FALSE | 7 | 0 | TRUE | 2
3 |  | 1 | "Draft" Project Notification Initial Review | Project Notification Intake | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 14 | 0 | TRUE | 3
4 |  | 1 | Additional Information Submission | Project Notification Intake | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 4
5 |  | 1 | Project Withdrawn | Project Notification Intake | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 5
6 |  | 1 | Other | Project Notification Intake | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 6
7 |  | 1 | Last Day of Project Notification Intake (Date Capture Milestone) | Project Notification Intake | Date Capture | Milestone | END | FALSE | 14 | 0 | TRUE | 7
8 |  | 2 | Project Notification Submission | Project Notification Review | Submission | Milestone | START | FALSE | 0 | 0 | TRUE | 8
9 |  | 2 | Delegation of Decision | Project Notification Review | Minister | Decision | INTERMEDIATE | FALSE | 7 | 0 | TRUE | 9
10 |  | 2 | Comment Period | Project Notification Review | Comment Period | PCP | INTERMEDIATE | TRUE | 14 | 30 | TRUE | 10
11 | 10 | 2 | PCP Coming Soon Announcement & Tweet | Project Notification Review | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | TRUE | 11
12 | 10 | 2 | PCP Coming Soon Milestone Bullet | Project Notification Review | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | TRUE | 12
13 | 10 | 2 | PCP Now Open Announcement & Tweet | Project Notification Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | TRUE | 13
14 | 10 | 2 | PCP Ending Soon Announcement & Tweet | Project Notification Review | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | TRUE | 14
15 |  | 2 | Additional Information Submission | Project Notification Review | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 15
16 |  | 2 | GHG Threshold Information Note | Project Notification Review | Report | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 16
17 | 16 | 2 | REMINDER: GHG Minister's Information Note | Project Notification Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 17
18 |  | 2 | Additional Comment Period | Project Notification Review | Comment Period | PCP | INTERMEDIATE | TRUE | 0 | 30 | FALSE | 18
19 | 18 | 2 | PCP Coming Soon Announcement & Tweet | Project Notification Review | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | FALSE | 19
20 | 18 | 2 | Additional PCP Milestone Bullet | Project Notification Review | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | FALSE | 20
21 | 18 | 2 | PCP Now Open Announcement & Tweet | Project Notification Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 21
22 | 18 | 2 | PCP Ending Soon Announcement & Tweet | Project Notification Review | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | FALSE | 22
23 |  | 2 | Open House | Project Notification Review | Open House | PCP | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 23
24 |  | 2 | Virtual Information Session | Project Notification Review | Virtual Information Session | PCP | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 24
25 |  | 2 | Comment Period Time Limit Extension | Project Notification Review | PCP Time Limit Extension | PCP | INTERMEDIATE | TRUE | 0 | 0 | FALSE | 25
26 | 25 | 2 | PCP Extended Announcement & Tweet | Project Notification Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 26
27 | 25 | 2 | PCP Extended Milestone Bullet | Project Notification Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 27
28 |  | 2 | s.38 Extension of Time Limit | Project Notification Review | Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | FALSE | 28
29 | 28 | 2 | Extension Announcement & Tweet | Project Notification Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 29
30 | 28 | 2 | Time Limit Extended Milestone Bullet | Project Notification Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 30
32 | 31 | 2 | Project Notification Process Suspension Announcement & Tweet | Project Notification Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 32
33 | 31 | 2 | Project Notification Process Suspended Milestone Bullet | Project Notification Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 33
35 | 34 | 2 | Project Notification Process Resumption Announcement & Tweet | Project Notification Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 35
36 | 34 | 2 | Project Notification Process Resumed Milestone Bullet | Project Notification Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 36
37 |  | 2 | Project Notification Terminated s.39(d) | Project Notification Review | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 37
38 | 37 | 2 | Termination Announcement & Tweet | Project Notification Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 38
39 | 37 | 2 | Project Notification Terminated Milestone Bullet | Project Notification Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 39
40 |  | 2 | Project Withdrawn | Project Notification Review | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 40
41 | 40 | 2 | Withdrawal Announcement & Tweet | Project Notification Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 41
42 | 40 | 2 | Project Withdrawn Milestone Bullet | Project Notification Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 42
43 |  | 2 | Other | Project Notification Review | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 43
44 |  | 2 | Complete Project Notification Report | Project Notification Review | Report | Milestone | END | FALSE | 50 | 0 | TRUE | 44
45 |  | 3 | Report Referred to Decision Maker | Project Notification Decision | Referral | Milestone | START | FALSE | 0 | 0 | TRUE | 45
46 |  | 3 | Draft Notification Decision Milestone Bullets | Project Notification Decision | Generic | Milestone | INTERMEDIATE | FALSE | 5 | 0 | TRUE | 46
47 | 46 | 3 | REMINDER: Draft Notification Decision Milestone Bullets Due | Project Notification Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | TRUE | 47
48 |  | 3 | Additional Information Submission | Project Notification Decision | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 48
49 |  | 3 | s.38 Extension of Time Limit | Project Notification Decision | Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | FALSE | 49
50 | 49 | 3 | Extension Announcement & Tweet | Project Notification Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 50
51 | 49 | 3 | Time Limit Extended Milestone Bullet | Project Notification Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 51
53 | 52 | 3 | Project Notification Process Suspension Announcement & Tweet | Project Notification Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 53
54 | 52 | 3 | Project Notification Process Suspended Milestone Bullet | Project Notification Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 54
56 | 55 | 3 | Project Notification Process Resumption Announcement & Tweet | Project Notification Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 56
57 | 55 | 3 | Project Notification Process Resumed Milestone Bullet | Project Notification Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 57
58 |  | 3 | Project Notification Terminated s.39(d) | Project Notification Decision | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 58
59 | 58 | 3 | Termination Announcement & Tweet | Project Notification Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 59
60 | 58 | 3 | Project Notification Terminated Milestone Bullet | Project Notification Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 60
61 |  | 3 | Project Withdrawn | Project Notification Decision | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 61
62 | 61 | 3 | Withdrawal Announcement & Tweet | Project Notification Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 62
63 | 61 | 3 | Project Withdrawn Milestone Bullet | Project Notification Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 63
64 |  | 3 | Other | Project Notification Decision | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 64
65 |  | 3 | Decision: Project Notification | Project Notification Decision | Minister | Decision | END | FALSE | 10 | 0 | TRUE | 65
66 | 65 | 3 | Notification Decision Announcement & Tweet | Project Notification Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | TRUE | 66
67 | 65 | 3 | Notification Decision Milestone Bullet | Project Notification Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | TRUE | 67

## Outcomes
No | TemplateNo | TemplateName | OutcomeName | SortOrder
1 | 3 | "Draft" Project Notification Initial Review | Initial Review of "Draft" Project Notification is POSITIVE | 1
2 | 3 | "Draft" Project Notification Initial Review | Initial Review of "Draft" Project Notification is NEGATIVE | 2
3 | 5 | Project Withdrawn | Proponent withdraws Submission from the Project Notification process | 3
4 | 8 | Project Notification Submission | Starts the "clock" for Project Notification | 4
5 | 9 | Delegation of Decision | Minister is delegated to make the final Project Notification Decision | 5
6 | 9 | Delegation of Decision | CEAO is delegated to make the final Project Notification Decision | 6
7 | 37 | Project Notification Terminated s.39(d) | Project Notification is Terminated under s.39(d) of Act | 8
8 | 40 | Project Withdrawn | Proponent withdraws Submission from the Project Notification process | 9
9 | 65 | Decision: Project Notification | No Further Review Required | 10
10 | 65 | Decision: Project Notification | More Information Needed | 11
11 | 65 | Decision: Project Notification | Project Referred to Minister (s.11) | 12
12 | 58 | Project Notification Terminated s.39(d) | Project Notification is Terminated under s.39(d) of Act | 13
13 | 61 | Project Withdrawn | Proponent withdraws Submission from the Project Notification process | 14

## Actions
No | OutcomeNo | OutcomeName | ActionName | ActionDescription | AdditionalParams | SortOrder
1 | 1 | Initial Review of "Draft" Project Notification is POSITIVE | SetEventDate | Set ANTICIPATED of "Project Notification Review ¦ Project Notification Submission" to thisEventACTUAL +1 | {"phase_name":"Project Notification Review","work_type_id": 1, "ea_act_id": 3, "event_name": "Project Notification Submission", "start_at": 1 } | 1
2 | 2 | Initial Review of "Draft" Project Notification is NEGATIVE | AddEvent | Add a copy of "Submission of "Draft" Initial Project Description" to thisPhase at thisEventACTUAL +14 | {"phase_name":"Project Notification Intake","work_type_id": 1, "ea_act_id": 3, "event_name": "Submission of \"Draft\" Project Notification", "start_at": 14 } | 2
3 | 2 | Initial Review of "Draft" Project Notification is NEGATIVE | AddEvent | Add a copy of "Initial Review of "Draft" Initial Project Description" to thisPhase at thisEventACTUAL +21 | {"phase_name":"Project Notification Intake","work_type_id": 1, "ea_act_id": 3, "event_name": "\"Draft\" Project Notification Initial Review", "start_at": 21 } | 3
4 | 3 | Proponent withdraws Submission from the Project Notification process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"is_active": false} | 4
5 | 3 | Proponent withdraws Submission from the Project Notification process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 5
6 | 3 | Proponent withdraws Submission from the Project Notification process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 6
7 | 3 | Proponent withdraws Submission from the Project Notification process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 7
8 | 4 | Starts the "clock" for Project Notification | LockWorkStartDate | Set the workStartDate to thisEventACTUAL | {"start_date_locked": true} | 8
9 | 5 | Minister is delegated to make the final Project Notification Decision | SetWorkDecisionMaker | Set the workDecisionMaker to currentMinisterEnvironment | {"position_id": 8} | 9
10 | 6 | CEAO is delegated to make the final Project Notification Decision | SetWorkDecisionMaker | Set the workDecisionMaker to currentCEAO | {"position_id": 1} | 10
15 | 7 | Project Notification is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"is_active": false} | 15
16 | 7 | Project Notification is Terminated under s.39(d) of Act | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 16
17 | 7 | Project Notification is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 17
18 | 7 | Project Notification is Terminated under s.39(d) of Act | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 18
19 | 8 | Proponent withdraws Submission from the Project Notification process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"is_active": false} | 19
20 | 8 | Proponent withdraws Submission from the Project Notification process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 20
21 | 8 | Proponent withdraws Submission from the Project Notification process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 21
22 | 8 | Proponent withdraws Submission from the Project Notification process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 22
23 | 9 | No Further Review Required | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 23
24 | 9 | No Further Review Required | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 24
25 | 10 | More Information Needed | AddPhase | addPhase "Revised Project Notification Intake"(copies of the origal PHASEs) | {"phase_name":"Project Notification Intake","work_type_id": 1, "ea_act_id": 3, "new_name": "Revised Project Notification Intake", "legislated": false } | 25
26 | 10 | More Information Needed | AddPhase | addPhase "Revised Project Notification Review" (copies of the origal PHASEs) | {"phase_name":"Project Notification Review","work_type_id": 1, "ea_act_id": 3, "new_name": "Revised Project Notification Review", "legislated": false } | 26
27 | 10 | More Information Needed | AddPhase | addPhase "Revised Project Notification Decision" (copies of the origal PHASEs) | {"phase_name":"Project Notification Decision","work_type_id": 1, "ea_act_id": 3, "new_name": "Revised Project Notification Decision", "legislated": false } | 27
28 | 11 | Project Referred to Minister (s.11) | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 28
29 | 11 | Project Referred to Minister (s.11) | CreateWork | Create a new WORK: "Minister's Designation" and link to thisWorkLinkedProject | {} | 29
30 | 12 | Project Notification is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"is_active": false} | 30
31 | 12 | Project Notification is Terminated under s.39(d) of Act | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 31
32 | 12 | Project Notification is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 32
33 | 12 | Project Notification is Terminated under s.39(d) of Act | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 33
34 | 13 | Proponent withdraws Submission from the Project Notification process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"is_active": false} | 34
35 | 13 | Proponent withdraws Submission from the Project Notification process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 35
36 | 13 | Proponent withdraws Submission from the Project Notification process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 36
37 | 13 | Proponent withdraws Submission from the Project Notification process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 37

## Lookups
WorkType | EA Act | Legislated |  | Event Type | Event Category | Mandatory | ActionName | Event Position | Multiple Days
Project Notification | EA Act (2018) | TRUE | Milestone | Generic | Milestone | TRUE | AllEventsDeactivated | START | TRUE
Minister's Designation | EA Act (2002) | FALSE | Milestone | Meeting | Calendar | FALSE | AllEventsDeleted | INTERMEDIATE | FALSE
CEAO's Designation | EA Act (1996) |  | Milestone | Notification | Decision |  | CloseEverything | END
EAC Assessment |  |  | Milestone | Order | Finance |  | CloseWork
Exemption Request |  |  | Milestone | Referral | PCP |  | CompleteCurrentPhase
Dispute Resolution |  |  | Milestone | Report | Extension |  | CreateNewWork
EAC/Order Amendment |  |  | Milestone | Request | Suspension |  | DisableWorkStartDate
Document Review |  |  | Milestone | Submission |  |  | DuplicatePhase
EAC Extension |  |  | Milestone | Other
Substantial Start Decision |  |  | Milestone | Date Capture
EAC/Order Transfer |  |  | Extension | Time Limit Extension
EAC/Order Suspension |  |  | Extension | PCP Time Limit Extension
EAC/Order Cancellation |  |  | Suspension | Time Limit Suspension
Other |  |  | Suspension | Time Limit Resumption
|  |  | Decision | EAC Ministers
|  |  | Decision | Minister
|  |  | Decision | CEAO
|  |  | Decision | ADM
|  |  | Decision | EPD
|  |  | Decision | PAD (Lead)
|  |  | Decision | Reviewer
|  |  | Decision | Federal
|  |  | Decision | Other
|  |  | PCP | Comment Period
|  |  | PCP | Open House
|  |  | PCP | Virtual Information Session
|  |  | PCP | Other
|  |  | Calendar | Communications
|  |  | Calendar | Executive
|  |  | Calendar | Financial
|  |  | Calendar | Work
|  |  | Calendar | Other
|  |  | Finance | Capacity Funding
|  |  | Finance | Fee Order
|  |  | Finance | Penalties
|  |  | Finance | Administrative
|  |  | Finance | Other