## Phases
No | Name | WorkType | EAAct | NumberOfDays | Legislated | Color | Visibility | SortOrder
1 | Pre-EA (EAC Assessment) | Assessment | EA Act (2018) | 90 | FALSE | #3eb1d7 | REGULAR | 1
2 | Early Engagement | Assessment | EA Act (2018) | 90 | TRUE | #54858d | REGULAR | 2
3 | DPD Development (Proponent Time) | Assessment | EA Act (2018) | 365 | FALSE | #6d7274 | REGULAR | 3
4 | Readiness Decision | Assessment | EA Act (2018) | 60 | FALSE | #da6d65 | REGULAR | 4
5 | Termination Decision | Assessment | EA Act (2018) | 30 | FALSE | #FFFFFF | HIDDEN | 5
6 | Further Readiness Decision | Assessment | EA Act (2018) | 30 | FALSE | #da6d65 | HIDDEN | 6
7 | Process Planning | Assessment | EA Act (2018) | 120 | TRUE | #043673 | REGULAR | 7
8 | EAC Application Development (Proponent Time) | Assessment | EA Act (2018) | 1096 | FALSE | #6d7274 | REGULAR | 8
9 | EAC Application Review | Assessment | EA Act (2018) | 180 | TRUE | #4d95d0 | REGULAR | 9
10 | Revised EAC Application Development (Proponent Time) | Assessment | EA Act (2018) | 365 | FALSE | #6d7274 | REGULAR | 10
11 | Effects Assessment & Recommendation | Assessment | EA Act (2018) | 150 | TRUE | #e7a913 | REGULAR | 11
12 | EAC Decision | Assessment | EA Act (2018) | 30 | TRUE | #6a54a3 | REGULAR | 12

## Events
No | Parent | PhaseNo | EventName | Phase | EventType | EventCategory | EventPosition | MultipleDays | StartAt | NumberOfDays | Visibility | SortOrder
1 |  | 1 | Start of Pre-EA Phase (e.g. Initial Meeting, Date Confirmation, or IPD) | Pre-EA (EAC Assessment) | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 1
2 |  | 1 | Project Presentation Meeting | Pre-EA (EAC Assessment) | Meeting | Milestone | INTERMEDIATE | FALSE | 28 | 0 | SUGGESTED | 2
3 |  | 1 | Submit Estimate for Capacity Funding | Pre-EA (EAC Assessment) | Capacity Funding | Finance | INTERMEDIATE | FALSE | 60 | 0 | SUGGESTED | 3
4 | 3 | 1 | Capacity Funding Estimate Due | Pre-EA (EAC Assessment) | Financial | Calendar | INTERMEDIATE | FALSE | 0 | 0 | SUGGESTED | 4
5 |  | 1 | Submission of IPD/EP for CEAO Approval | Pre-EA (EAC Assessment) | Submission | Milestone | INTERMEDIATE | FALSE | 80 | 0 | MANDATORY | 5
6 |  | 1 | Create IPD Approval Milestone Bullet | Pre-EA (EAC Assessment) | Generic | Milestone | INTERMEDIATE | FALSE | 85 | 0 | SUGGESTED | 6
7 | 6 | 1 | REMINDER: Create IPD Approval Milestone Bullet | Pre-EA (EAC Assessment) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | SUGGESTED | 7
8 |  | 1 | Additional Information Submission | Pre-EA (EAC Assessment) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 8
9 |  | 1 | Project Transitioning FROM the EA Act (2002) | Pre-EA (EAC Assessment) | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 9
10 | 9 | 1 | Project Transitions to 2018 Act Announcement & Tweet | Pre-EA (EAC Assessment) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 10
11 | 9 | 1 | Project Transitions to 2018 Act Milestone Bullet | Pre-EA (EAC Assessment) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 11
12 |  | 1 | Document Submitted to EAO for "Initial Review" | Pre-EA (EAC Assessment) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 12
13 | 12 | 1 | EAO's Viewpoint on Submitted Document | Pre-EA (EAC Assessment) | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 10 | 0 | OPTIONAL | 13
14 |  | 1 | Project Withdrawn | Pre-EA (EAC Assessment) | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 14
15 |  | 1 | Other | Pre-EA (EAC Assessment) | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 15
9999 |  | 1 | Last Day of Pre-EA (EAC Assessment) | Pre-EA (EAC Assessment) | Date Capture | Milestone | INTERMEDIATE | FALSE | 0 | 0 | HIDDEN | 15
16 |  | 1 | IPD/EP Approval Decision (Day Zero) | Pre-EA (EAC Assessment) | CEAO | Decision | END | FALSE | 90 | 0 | MANDATORY | 16
17 | 16 | 1 | Approval of IPD/EP Announcement & Tweet | Pre-EA (EAC Assessment) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 17
18 | 16 | 1 | Approval of IPD/EP Milestone Bullet | Pre-EA (EAC Assessment) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 18
19 |  | 2 | IPD/EP Approved (Day One) | Early Engagement | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 19
20 |  | 2 | Notification sent to potential PINs | Early Engagement | Notification | Milestone | INTERMEDIATE | FALSE | 7 | 0 | SUGGESTED | 20
21 |  | 2 | Comment Period | Early Engagement | Comment Period | PCP | INTERMEDIATE | TRUE | 14 | 30 | MANDATORY | 21
22 | 21 | 2 | PCP Coming Soon Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | MANDATORY | 22
23 | 21 | 2 | PCP Coming Soon Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | MANDATORY | 23
24 | 21 | 2 | PCP Now Open Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 24
25 | 21 | 2 | PCP Ending Soon Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | MANDATORY | 25
26 |  | 2 | Confirm Capacity Funding Amounts | Early Engagement | Capacity Funding | Finance | INTERMEDIATE | FALSE | 21 | 0 | SUGGESTED | 26
27 | 26 | 2 | Early Engagement Capacity Funding Confirmation Due | Early Engagement | Financial | Calendar | INTERMEDIATE | FALSE | 0 | 0 | SUGGESTED | 27
28 |  | 2 | Fee Order: Submission of IPD | Early Engagement | Fee Order | Finance | INTERMEDIATE | FALSE | 30 | 0 | MANDATORY | 28
29 | 28 | 2 | Fee Order for Filing of IPD | Early Engagement | Financial | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 29
30 |  | 2 | PIN Notice of Intent Completed | Early Engagement | Generic | Milestone | INTERMEDIATE | FALSE | 80 | 0 | SUGGESTED | 30
31 |  | 2 | Create SoE Milestone Bullet | Early Engagement | Generic | Milestone | INTERMEDIATE | FALSE | 85 | 0 | SUGGESTED | 31
32 | 31 | 2 | REMINDER: Create SoE Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | SUGGESTED | 32
33 |  | 2 | Additional Information Submission | Early Engagement | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 33
34 |  | 2 | Submit Estimate for Capacity Funding | Early Engagement | Capacity Funding | Finance | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 34
35 | 34 | 2 | Capacity Funding Estimate Due | Early Engagement | Financial | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 35
36 |  | 2 | Federal Substitution Request | Early Engagement | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 36
37 | 36 | 2 | Federal Substitution Request Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 37
38 |  | 2 | Dispute Resolution Triggered | Early Engagement | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 38
39 | 38 | 2 | DR Triggered Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 39
40 | 38 | 2 | Dispute Resolution Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 40
41 |  | 2 | Additional Comment Period | Early Engagement | Comment Period | PCP | INTERMEDIATE | TRUE | 0 | 30 | OPTIONAL | 41
42 | 41 | 2 | PCP Coming Soon Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | 42
43 | 41 | 2 | Additional PCP Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | 43
44 | 41 | 2 | PCP Now Open Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 44
45 | 41 | 2 | PCP Ending Soon Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | OPTIONAL | 45
46 |  | 2 | Open House | Early Engagement | Open House | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 46
47 |  | 2 | Virtual Information Session | Early Engagement | Virtual Information Session | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 47
48 |  | 2 | Comment Period Time Limit Extension | Early Engagement | PCP Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | 48
49 | 48 | 2 | PCP Extended Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 49
50 | 48 | 2 | PCP Extended Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 50
51 |  | 2 | s.38 Extension of Time Limit | Early Engagement | Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | 51
52 | 51 | 2 | Extension Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 52
53 | 51 | 2 | Time Limit Extended Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 53
54 |  | 2 | s.45 Suspension of the EAC Assessment Process | Early Engagement | Time Limit Suspension | Suspension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 54
55 | 54 | 2 | EAC Assessment Process Suspension Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 55
56 | 54 | 2 | EAC Assessment Process Suspended Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 56
57 |  | 2 | s.45 Resumption of the EAC Assessment Process | Early Engagement | Time Limit Resumption | Suspension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 57
58 | 57 | 2 | EAC Assessment Process Resumption Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 58
59 | 57 | 2 | EAC Assessment Process Resumed Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 59
60 |  | 2 | EAC Assessment Terminated s.39(d) | Early Engagement | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 60
61 | 60 | 2 | Termination Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 61
62 | 60 | 2 | EAC Assessment Terminated Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 62
63 |  | 2 | Project Withdrawn | Early Engagement | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 63
64 | 63 | 2 | Withdrawal Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 64
65 | 63 | 2 | Project Withdrawn Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 65
66 |  | 2 | Other | Early Engagement | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 66
67 |  | 2 | Summary of Engagement Published | Early Engagement | Report | Milestone | END | FALSE | 90 | 0 | MANDATORY | 67
68 | 67 | 2 | Summary of Engagement Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 68
69 | 67 | 2 | Summary of Engagement Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 69
70 |  | 3 | Start of DPD Development | DPD Development (Proponent Time) | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 70
71 |  | 3 | Create DPD Receipt Milestone Bullet | DPD Development (Proponent Time) | Generic | Milestone | INTERMEDIATE | FALSE | 360 | 0 | SUGGESTED | 71
72 | 71 | 3 | REMINDER: Create DPD Receipt Milestone Bullet | DPD Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | SUGGESTED | 72
73 |  | 3 | Additional Information Submission | DPD Development (Proponent Time) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 73
74 |  | 3 | Document Submitted to EAO for "Initial Review" | DPD Development (Proponent Time) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 74
75 | 74 | 3 | EAO's Viewpoint on Submitted Document | DPD Development (Proponent Time) | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 10 | 0 | OPTIONAL | 75
76 |  | 3 | Dispute Resolution Triggered | DPD Development (Proponent Time) | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 76
77 | 76 | 3 | DR Triggered Announcement & Tweet | DPD Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 77
78 | 76 | 3 | Dispute Resolution Milestone Bullet | DPD Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 78
79 |  | 3 | EAC Assessment Terminated s.39(d) | DPD Development (Proponent Time) | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 79
80 | 79 | 3 | Termination Announcement & Tweet | DPD Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 80
81 | 79 | 3 | EAC Assessment Terminated Milestone Bullet | DPD Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 81
82 |  | 3 | Project Withdrawn | DPD Development (Proponent Time) | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 82
83 | 82 | 3 | Withdrawal Announcement & Tweet | DPD Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 83
84 | 82 | 3 | Project Withdrawn Milestone Bullet | DPD Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 84
85 |  | 3 | Other | DPD Development (Proponent Time) | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 85
86 |  | 3 | Last Day of DPD Development (day before DPD received) | DPD Development (Proponent Time) | Date Capture | Milestone | END | FALSE | 365 | 0 | MANDATORY | 86
87 |  | 4 | Detailed Project Description Received | Readiness Decision | Submission | Milestone | START | FALSE | 0 | 0 | MANDATORY | 87
88 | 87 | 4 | DPD Received Announcement & Tweet | Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 88
89 | 87 | 4 | DPD Received Milestone Bullet | Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 89
90 |  | 4 | Fee Order: Submission of DPD | Readiness Decision | Fee Order | Finance | INTERMEDIATE | FALSE | 30 | 0 | MANDATORY | 90
91 | 90 | 4 | Fee Order for Filing of DPD | Readiness Decision | Financial | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 91
92 |  | 4 | Report referred to CEAO | Readiness Decision | Referral | Milestone | INTERMEDIATE | FALSE | 50 | 0 | MANDATORY | 92
93 |  | 4 | Create Readiness Decision Milestone Bullet | Readiness Decision | Generic | Milestone | INTERMEDIATE | FALSE | 55 | 0 | SUGGESTED | 93
94 | 93 | 4 | REMINDER: Create Readiness Decision Milestone Bullet | Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | SUGGESTED | 94
95 |  | 4 | Additional Information Submission | Readiness Decision | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 95
96 |  | 4 | Dispute Resolution Triggered | Readiness Decision | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 96
97 | 96 | 4 | DR Triggered Announcement & Tweet | Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 97
98 | 96 | 4 | Dispute Resolution Milestone Bullet | Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 98
99 |  | 4 | EAC Assessment Terminated s.39(d) | Readiness Decision | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 99
100 | 99 | 4 | Termination Announcement & Tweet | Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 100
101 | 99 | 4 | EAC Assessment Terminated Milestone Bullet | Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 101
102 |  | 4 | Project Withdrawn | Readiness Decision | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 102
103 | 102 | 4 | Withdrawal Announcement & Tweet | Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 103
104 | 102 | 4 | Project Withdrawn Milestone Bullet | Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 104
105 |  | 4 | Other | Readiness Decision | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 105
106 |  | 4 | Termination Package Referred to Minister | Readiness Decision | Referral | Milestone | INTERMEDIATE | FALSE | 0 | 0 | HIDDEN | 106
107 |  | 4 | Last Day of Readiness Decision (Termination) | Readiness Decision | Date Capture | Milestone | INTERMEDIATE | FALSE | 0 | 0 | HIDDEN | 107
108 |  | 4 | CEAO's Readiness Decision (EAC Assessment) | Readiness Decision | CEAO | Decision | END | FALSE | 60 | 0 | MANDATORY | 108
109 | 108 | 4 | Readiness Decision Announcement & Tweet | Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 109
110 | 108 | 4 | Readiness Decision Milestone Bullet | Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 110
111 |  | 5 | Termination Decision Package Received by Minister | Termination Decision | Generic | Milestone | START | FALSE | 0 | 0 | MANDATORY | 111
112 |  | 5 | Additional Information Submission | Termination Decision | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 112
113 |  | 5 | EAC Assessment Terminated s.39(d) | Termination Decision | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 113
114 | 113 | 5 | Termination Announcement & Tweet | Termination Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 114
115 | 113 | 5 | EAC Assessment Terminated Milestone Bullet | Termination Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 115
116 |  | 5 | Project Withdrawn | Termination Decision | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 116
117 | 116 | 5 | Withdrawal Announcement & Tweet | Termination Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 117
118 | 116 | 5 | Project Withdrawn Milestone Bullet | Termination Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 118
119 |  | 5 | Other | Termination Decision | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 119
120 |  | 5 | Minister's Termination Decision | Termination Decision | Minister | Decision | END | FALSE | 30 | 0 | MANDATORY | 120
121 | 120 | 5 | Termination Decision Announcement & Tweet (unless return to CEAO) | Termination Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 121
122 |  | 6 | Readiness Decision Report referred to CEAO for Further Decision | Further Readiness Decision | Referral | Milestone | START | FALSE | 0 | 0 | MANDATORY | 122
123 |  | 6 | Additional Information Submission | Further Readiness Decision | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 123
124 |  | 6 | EAC Assessment Terminated s.39(d) | Further Readiness Decision | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 124
125 |  | 6 | Termination Announcement & Tweet | Further Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 125
126 |  | 6 | EAC Assessment Terminated Milestone Bullet | Further Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 126
127 |  | 6 | Project Withdrawn | Further Readiness Decision | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 127
128 |  | 6 | Withdrawal Announcement & Tweet | Further Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 128
129 |  | 6 | Project Withdrawn Milestone Bullet | Further Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 129
130 |  | 6 | Other | Further Readiness Decision | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 130
131 |  | 6 | Last Day of Further Readiness Decision (EAC Assessment) | Further Readiness Decision | Date Capture | Milestone | INTERMEDIATE | FALSE |  | 0 | HIDDEN | 131
132 |  | 6 | CEAO's Further Readiness Decision (EAC Assessment) | Further Readiness Decision | CEAO | Decision | END | FALSE | 30 | 0 | MANDATORY | 132
133 | 132 | 6 | Further Readiness Decision Announcement & Tweet | Further Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 133
134 | 132 | 6 | Further Readiness Decision Milestone Bullet | Further Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 134
135 |  | 7 | Start of Process Planning (Day One) | Process Planning | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 135
136 |  | 7 | Federal Involvement Determination | Process Planning | Federal | Decision | INTERMEDIATE | FALSE | 30 | 0 | MANDATORY | 136
137 | 136 | 7 | Federal Involvement Announcement & Tweet (if necessary) | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 137
138 | 136 | 7 | Federal Involvement Milestone Bullet (if necessary) | Process Planning | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 138
139 |  | 7 | Draft Process Order Shared with TAC | Process Planning | Generic | Milestone | INTERMEDIATE | FALSE | 45 | 0 | SUGGESTED | 139
140 |  | 7 | Comment Period | Process Planning | Comment Period | PCP | INTERMEDIATE | TRUE | 60 | 30 | MANDATORY | 140
141 | 140 | 7 | PCP Coming Soon Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | MANDATORY | 141
142 | 140 | 7 | PCP Coming Soon Milestone Bullet | Process Planning | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | MANDATORY | 142
143 | 140 | 7 | PCP Now Open Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 143
144 | 140 | 7 | PCP Ending Soon Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | MANDATORY | 144
145 |  | 7 | Formally Establish TAC | Process Planning | Generic | Milestone | INTERMEDIATE | FALSE | 100 | 0 | SUGGESTED | 145
146 |  | 7 | Create Process Order Issued Milestone Bullet | Process Planning | Generic | Milestone | INTERMEDIATE | FALSE | 115 | 0 | SUGGESTED | 146
147 | 146 | 7 | REMINDER: Create Process Order Issue Milestone Bullet | Process Planning | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | SUGGESTED | 147
148 |  | 7 | Additional Information Submission | Process Planning | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 148
149 |  | 7 | Section 19.4 Assessment - PIN Assessment Request | Process Planning | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 149
150 |  | 7 | Summary of Engagement Report Issued | Process Planning | Report | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 150
151 |  | 7 | Establish Community Advisory Committee | Process Planning | Generic | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 151
152 |  | 7 | Dispute Resolution Triggered | Process Planning | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 152
153 | 152 | 7 | DR Triggered Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 153
154 | 152 | 7 | Dispute Resolution Milestone Bullet | Process Planning | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 154
155 |  | 7 | Additional Comment Period | Process Planning | Comment Period | PCP | INTERMEDIATE | TRUE | 0 | 30 | OPTIONAL | 155
156 | 155 | 7 | PCP Coming Soon Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | 156
157 | 155 | 7 | Additional PCP Milestone Bullet | Process Planning | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | 157
158 | 155 | 7 | PCP Now Open Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 158
159 | 155 | 7 | PCP Ending Soon Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | OPTIONAL | 159
160 |  | 7 | Open House | Process Planning | Open House | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 160
161 |  | 7 | Virtual Information Session | Process Planning | Virtual Information Session | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 161
162 |  | 7 | Comment Period Time Limit Extension | Process Planning | PCP Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | 162
163 | 162 | 7 | PCP Extended Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 163
164 | 162 | 7 | PCP Extended Milestone Bullet | Process Planning | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 164
165 |  | 7 | s.38 Extension of Time Limit | Process Planning | Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | 165
166 | 165 | 7 | Extension Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 166
167 | 165 | 7 | Time Limit Extended Milestone Bullet | Process Planning | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 167
168 |  | 7 | s.45 Suspension of the EAC Assessment Process | Process Planning | Time Limit Suspension | Suspension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 168
169 | 168 | 7 | EAC Assessment Process Suspension Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 169
170 | 168 | 7 | EAC Assessment Process Suspended Milestone Bullet | Process Planning | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 170
171 |  | 7 | s.45 Resumption of the EAC Assessment Process | Process Planning | Time Limit Resumption | Suspension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 171
172 | 171 | 7 | EAC Assessment Process Resumption Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 172
173 | 171 | 7 | EAC Assessment Process Resumed Milestone Bullet | Process Planning | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 173
174 |  | 7 | EAC Assessment Terminated s.39(d) | Process Planning | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 174
175 | 174 | 7 | Termination Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 175
176 | 174 | 7 | EAC Assessment Terminated Milestone Bullet | Process Planning | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 176
177 |  | 7 | Project Withdrawn | Process Planning | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 177
178 | 177 | 7 | Withdrawal Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 178
179 | 177 | 7 | Project Withdrawn Milestone Bullet | Process Planning | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 179
180 |  | 7 | Other | Process Planning | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 180
181 |  | 7 | Process Order Issued & Regulatory Coordination Plan Posted | Process Planning | Report | Milestone | END | FALSE | 120 | 0 | MANDATORY | 181
182 | 181 | 7 | Process Order Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 182
183 | 181 | 7 | Process Order Milestone Bullet | Process Planning | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 183
184 |  | 8 | Start of EAC Application Development | EAC Application Development (Proponent Time) | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 184
185 |  | 8 | Create EAC Application Receipt Milestone Bullet | EAC Application Development (Proponent Time) | Generic | Milestone | INTERMEDIATE | FALSE | 1090 | 0 | SUGGESTED | 185
186 | 185 | 8 | REMINDER: Create EAC Application Receipt Milestone Bullet | EAC Application Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | SUGGESTED | 186
187 |  | 8 | Additional Information Submission | EAC Application Development (Proponent Time) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 187
188 |  | 8 | Modification of Process Order | EAC Application Development (Proponent Time) | Order | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 188
189 | 188 | 8 | Modification of Process Order Announcement & Tweet | EAC Application Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 189
190 |  | 8 | Document Submitted to EAO for "Initial Review" | EAC Application Development (Proponent Time) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 190
191 | 190 | 8 | EAO's Viewpoint on Submitted Document | EAC Application Development (Proponent Time) | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 191
192 |  | 8 | Dispute Resolution Triggered | EAC Application Development (Proponent Time) | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 192
193 | 192 | 8 | DR Triggered Announcement & Tweet | EAC Application Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 193
194 | 192 | 8 | Dispute Resolution Milestone Bullet | EAC Application Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 194
195 |  | 8 | EAC Assessment Terminated s.39(d) | EAC Application Development (Proponent Time) | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 195
196 | 195 | 8 | Termination Announcement & Tweet | EAC Application Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 196
197 | 195 | 8 | EAC Assessment Terminated Milestone Bullet | EAC Application Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 197
198 |  | 8 | Project Withdrawn | EAC Application Development (Proponent Time) | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 198
199 | 198 | 8 | Withdrawal Announcement & Tweet | EAC Application Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 199
200 | 198 | 8 | Project Withdrawn Milestone Bullet | EAC Application Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 200
201 |  | 8 | Other | EAC Application Development (Proponent Time) | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 201
202 |  | 8 | Last Day of EAC Application Development (day before EAC Application received) | EAC Application Development (Proponent Time) | Date Capture | Milestone | END | FALSE | 1096 | 0 | MANDATORY | 202
203 |  | 9 | EAC Application Received | EAC Application Review | Submission | Milestone | START | FALSE | 0 | 0 | MANDATORY | 203
204 | 203 | 9 | EAC Application Received Announcement & Tweet | EAC Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 204
205 | 203 | 9 | EAC Application Received Milestone Bullet | EAC Application Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 205
206 |  | 9 | Comment Period | EAC Application Review | Comment Period | PCP | INTERMEDIATE | TRUE | 14 | 30 | MANDATORY | 206
207 | 206 | 9 | PCP Coming Soon Announcement & Tweet | EAC Application Review | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | MANDATORY | 207
208 | 206 | 9 | PCP Coming Soon Milestone Bullet | EAC Application Review | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | MANDATORY | 208
209 | 206 | 9 | PCP Now Open Announcement & Tweet | EAC Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 209
210 | 206 | 9 | PCP Ending Soon Announcement & Tweet | EAC Application Review | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | MANDATORY | 210
211 |  | 9 | Fee Order: Submission of EAC Application | EAC Application Review | Fee Order | Finance | INTERMEDIATE | FALSE | 30 | 0 | MANDATORY | 211
212 | 211 | 9 | Fee Order for Filing of EAC Application | EAC Application Review | Financial | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 212
213 |  | 9 | Create Revised Application Milestone Bullet | EAC Application Review | Generic | Milestone | INTERMEDIATE | FALSE | 175 | 0 | SUGGESTED | 213
214 | 213 | 9 | REMINDER: Create Revised Application Milestone Bullet | EAC Application Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | SUGGESTED | 214
215 |  | 9 | Additional Information Submission | EAC Application Review | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 215
216 |  | 9 | Modification of Process Order | EAC Application Review | Order | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 216
217 | 216 | 9 | Modification of Process Order Announcement & Tweet | EAC Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 217
218 |  | 9 | Dispute Resolution Triggered | EAC Application Review | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 218
219 | 218 | 9 | DR Triggered Announcement & Tweet | EAC Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 219
220 | 218 | 9 | Dispute Resolution Milestone Bullet | EAC Application Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 220
221 |  | 9 | Additional Comment Period | EAC Application Review | Comment Period | PCP | INTERMEDIATE | TRUE | 0 | 30 | OPTIONAL | 221
222 | 221 | 9 | PCP Coming Soon Announcement & Tweet | EAC Application Review | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | 222
223 | 221 | 9 | Additional PCP Milestone Bullet | EAC Application Review | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | 223
224 | 221 | 9 | PCP Now Open Announcement & Tweet | EAC Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 224
225 | 221 | 9 | PCP Ending Soon Announcement & Tweet | EAC Application Review | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | OPTIONAL | 225
226 |  | 9 | Open House | EAC Application Review | Open House | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 226
227 |  | 9 | Virtual Information Session | EAC Application Review | Virtual Information Session | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 227
228 |  | 9 | Comment Period Time Limit Extension | EAC Application Review | PCP Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | 228
229 | 228 | 9 | PCP Extended Announcement & Tweet | EAC Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 229
230 | 228 | 9 | PCP Extended Milestone Bullet | EAC Application Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 230
231 |  | 9 | s.38 Extension of Time Limit | EAC Application Review | Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | 231
232 | 231 | 9 | Extension Announcement & Tweet | EAC Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 232
233 | 231 | 9 | Time Limit Extended Milestone Bullet | EAC Application Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 233
234 |  | 9 | s.45 Suspension of the EAC Assessment Process | EAC Application Review | Time Limit Suspension | Suspension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 234
235 | 234 | 9 | EAC Assessment Process Suspension Announcement & Tweet | EAC Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 235
236 | 234 | 9 | EAC Assessment Process Suspended Milestone Bullet | EAC Application Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 236
237 |  | 9 | s.45 Resumption of the EAC Assessment Process | EAC Application Review | Time Limit Resumption | Suspension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 237
238 | 237 | 9 | EAC Assessment Process Resumption Announcement & Tweet | EAC Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 238
239 | 237 | 9 | EAC Assessment Process Resumed Milestone Bullet | EAC Application Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 239
240 |  | 9 | EAC Assessment Terminated s.39(d) | EAC Application Review | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 240
241 | 240 | 9 | Termination Announcement & Tweet | EAC Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 241
242 | 240 | 9 | EAC Assessment Terminated Milestone Bullet | EAC Application Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 242
243 |  | 9 | Project Withdrawn | EAC Application Review | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 243
244 | 243 | 9 | Withdrawal Announcement & Tweet | EAC Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 244
245 | 243 | 9 | Project Withdrawn Milestone Bullet | EAC Application Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 245
246 |  | 9 | Other | EAC Application Review | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 246
247 |  | 9 | Notice to Proponent to Prepare Revised EAC Application | EAC Application Review | Notification | Milestone | END | FALSE | 180 | 0 | MANDATORY | 247
248 | 247 | 9 | Notice of Revised EAC Application Announcement & Tweet | EAC Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 248
249 | 247 | 9 | Notice of Revised EAC Application Milestone Bullet | EAC Application Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 249
250 |  | 10 | Start of Revised EAC Application Development | Revised EAC Application Development (Proponent Time) | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 250
251 |  | 10 | Submission of Revised EAC Application for CEAO Acceptance | Revised EAC Application Development (Proponent Time) | Submission | Milestone | INTERMEDIATE | FALSE | 365 | 0 | MANDATORY | 251
252 |  | 10 | Create Revised EAC Application Acceptance Milestone Bullet | Revised EAC Application Development (Proponent Time) | Generic | Milestone | INTERMEDIATE | FALSE | 370 | 0 | SUGGESTED | 252
253 | 252 | 10 | REMINDER: Create Revised EAC Application Acceptance Milestone Bullet | Revised EAC Application Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | SUGGESTED | 253
254 |  | 10 | Additional Information Submission | Revised EAC Application Development (Proponent Time) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 254
255 |  | 10 | Modification of Process Order | Revised EAC Application Development (Proponent Time) | Order | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 255
256 | 255 | 10 | Modification of Process Order Announcement & Tweet | Revised EAC Application Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 256
257 |  | 10 | Document Submitted to EAO for "Initial Review" | Revised EAC Application Development (Proponent Time) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 257
258 | 257 | 10 | EAO's Viewpoint on Submitted Document | Revised EAC Application Development (Proponent Time) | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 258
259 |  | 10 | Dispute Resolution Triggered | Revised EAC Application Development (Proponent Time) | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 259
260 | 259 | 10 | DR Triggered Announcement & Tweet | Revised EAC Application Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 260
261 | 259 | 10 | Dispute Resolution Milestone Bullet | Revised EAC Application Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 261
262 |  | 10 | EAC Assessment Terminated s.39(d) | Revised EAC Application Development (Proponent Time) | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 262
263 | 262 | 10 | Termination Announcement & Tweet | Revised EAC Application Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 263
264 | 262 | 10 | EAC Assessment Terminated Milestone Bullet | Revised EAC Application Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 264
265 |  | 10 | Project Withdrawn | Revised EAC Application Development (Proponent Time) | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 265
266 | 265 | 10 | Withdrawal Announcement & Tweet | Revised EAC Application Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 266
267 | 265 | 10 | Project Withdrawn Milestone Bullet | Revised EAC Application Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 267
268 |  | 10 | Other | Revised EAC Application Development (Proponent Time) | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 268
269 |  | 10 | Revised EAC Application Acceptance Decision (Day Zero) | Revised EAC Application Development (Proponent Time) | CEAO | Decision | END | FALSE | 430 | 0 | MANDATORY | 269
270 |  | 10 | Acceptance of Revised EAC Application Announcement & Tweet | Revised EAC Application Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 270
271 |  | 10 | Acceptance of Revised EAC Application Milestone Bullet | Revised EAC Application Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 271
272 |  | 11 | Start of Effects Assessment (Day One) | Effects Assessment & Recommendation | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 272
273 | 272 | 11 | Revised EAC Application Accepted Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 273
274 | 272 | 11 | Revised EAC Application Accepted Milestone Bullet | Effects Assessment & Recommendation | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 274
275 |  | 11 | Draft Assessment Report & Draft Certificate Posted | Effects Assessment & Recommendation | Report | Milestone | INTERMEDIATE | FALSE | 90 | 0 | SUGGESTED | 275
276 |  | 11 | Comment Period | Effects Assessment & Recommendation | Comment Period | PCP | INTERMEDIATE | TRUE | 104 | 30 | MANDATORY | 276
277 | 276 | 11 | PCP Coming Soon Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | MANDATORY | 277
278 | 276 | 11 | PCP Coming Soon Milestone Bullet | Effects Assessment & Recommendation | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | MANDATORY | 278
279 | 276 | 11 | PCP Now Open Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 279
280 | 276 | 11 | PCP Ending Soon Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | MANDATORY | 280
281 |  | 11 | Create Memo to Ministers | Effects Assessment & Recommendation | Generic | Milestone | INTERMEDIATE | FALSE | 130 | 0 | SUGGESTED | 281
282 | 281 | 11 | REMINDER: Create Memo to Ministers | Effects Assessment & Recommendation | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | SUGGESTED | 282
283 |  | 11 | Additional Information Submission | Effects Assessment & Recommendation | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 283
284 |  | 11 | Modification of Process Order | Effects Assessment & Recommendation | Order | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 284
285 | 284 | 11 | Modification of Process Order Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 285
286 |  | 11 | Dispute Resolution Triggered | Effects Assessment & Recommendation | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 286
287 | 286 | 11 | DR Triggered Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 287
288 | 286 | 11 | Dispute Resolution Milestone Bullet | Effects Assessment & Recommendation | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 288
289 |  | 11 | Additional Comment Period | Effects Assessment & Recommendation | Comment Period | PCP | INTERMEDIATE | TRUE | 0 | 30 | OPTIONAL | 289
290 | 289 | 11 | PCP Coming Soon Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | 290
291 | 289 | 11 | Additional PCP Milestone Bullet | Effects Assessment & Recommendation | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | 291
292 | 289 | 11 | PCP Now Open Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 292
293 | 289 | 11 | PCP Ending Soon Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | OPTIONAL | 293
294 |  | 11 | Open House | Effects Assessment & Recommendation | Open House | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 294
295 |  | 11 | Virtual Information Session | Effects Assessment & Recommendation | Virtual Information Session | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 295
296 |  | 11 | Comment Period Time Limit Extension | Effects Assessment & Recommendation | PCP Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | 296
297 | 296 | 11 | PCP Extended Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 297
298 | 296 | 11 | PCP Extended Milestone Bullet | Effects Assessment & Recommendation | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 298
299 |  | 11 | s.38 Extension of Time Limit | Effects Assessment & Recommendation | Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | 299
300 | 299 | 11 | Extension Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 300
301 | 299 | 11 | Time Limit Extended Milestone Bullet | Effects Assessment & Recommendation | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 301
302 |  | 11 | s.45 Suspension of the EAC Assessment Process | Effects Assessment & Recommendation | Time Limit Suspension | Suspension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 302
303 | 302 | 11 | EAC Assessment Process Suspension Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 303
304 | 302 | 11 | EAC Assessment Process Suspended Milestone Bullet | Effects Assessment & Recommendation | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 304
305 |  | 11 | s.45 Resumption of the EAC Assessment Process | Effects Assessment & Recommendation | Time Limit Resumption | Suspension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 305
306 | 305 | 11 | EAC Assessment Process Resumption Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 306
307 | 205 | 11 | EAC Assessment Process Resumed Milestone Bullet | Effects Assessment & Recommendation | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 307
308 |  | 11 | EAC Assessment Terminated s.39(d) | Effects Assessment & Recommendation | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 308
309 | 308 | 11 | Termination Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 309
310 | 308 | 11 | EAC Assessment Terminated Milestone Bullet | Effects Assessment & Recommendation | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 310
311 |  | 11 | Project Withdrawn | Effects Assessment & Recommendation | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 311
312 | 311 | 11 | Withdrawal Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 312
313 | 311 | 11 | Project Withdrawn Milestone Bullet | Effects Assessment & Recommendation | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 313
314 |  | 11 | Other | Effects Assessment & Recommendation | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 314
315 |  | 11 | Interregnum | Effects Assessment & Recommendation | Interregnum | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | 315
316 |  | 11 | EAC Referral Package sent to Ministers | Effects Assessment & Recommendation | Referral | Milestone | END | FALSE | 150 | 0 | MANDATORY | 316
317 | 316 | 11 | Completion of Assessment and Referral to Minister Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 317
318 |  | 12 | EAC Referral Package Received by Ministers | EAC Decision | Generic | Milestone | START | FALSE | 0 | 0 | MANDATORY | 318
319 |  | 12 | Additional Information Submission | EAC Decision | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 319
320 |  | 12 | Ministers Meeting | EAC Decision | Meeting | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 320
321 |  | 12 | s.38 Extension of Time Limit | EAC Decision | Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | 321
322 | 321 | 12 | Extension Announcement & Tweet | EAC Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 322
323 | 321 | 12 | Time Limit Extended Milestone Bullet | EAC Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 323
324 |  | 12 | s.45 Suspension of the EAC Assessment Process | EAC Decision | Time Limit Suspension | Suspension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 324
325 | 324 | 12 | EAC Assessment Process Suspension Announcement & Tweet | EAC Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 325
326 | 324 | 12 | EAC Assessment Process Suspended Milestone Bullet | EAC Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 326
327 |  | 12 | s.45 Resumption of the EAC Assessment Process | EAC Decision | Time Limit Resumption | Suspension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 327
328 | 327 | 12 | EAC Assessment Process Resumption Announcement & Tweet | EAC Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 328
329 | 327 | 12 | EAC Assessment Process Resumed Milestone Bullet | EAC Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 329
330 |  | 12 | Project Withdrawn | EAC Decision | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 330
331 | 330 | 12 | Withdrawal Announcement & Tweet | EAC Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 331
332 | 330 | 12 | Project Withdrawn Milestone Bullet | EAC Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 332
333 |  | 12 | Other | EAC Decision | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 333
334 |  | 12 | EAC Ministers Decision | EAC Decision | EAC Ministers | Decision | END | FALSE | 30 | 0 | MANDATORY | 334
335 | 334 | 12 | EAC Decision Announcement & Tweet | EAC Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 335

## Outcomes
No | TemplateNo | TemplateName | OutcomeName | SortOrder
1 | 9 | Project Transitioning FROM the EA Act (2002) | Assessment Transitions to the EA Act (2018) Early Engagement PHASE | 1
2 | 9 | Project Transitioning FROM the EA Act (2002) | Assessment Transitions to the EA Act (2018) Readiness Decision PHASE | 2
3 | 9 | Project Transitioning FROM the EA Act (2002) | Assessment Transitions to the EA Act (2018) Process Planning PHASE | 3
4 | 9 | Project Transitioning FROM the EA Act (2002) | Assessment Transitions to the EA Act (2018) EAC Application Review PHASE | 4
5 | 9 | Project Transitioning FROM the EA Act (2002) | Assessment Transitions to the EA Act (2018) Effects Assessment PHASE | 5
6 | 13 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is POSITIVE | 6
7 | 13 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is NEGATIVE | 7
8 | 14 | Project Withdrawn | Proponent withdraws Project from the EAC Assessment Process | 8
9 | 16 | IPD/EP Approval Decision (Day Zero) | CEAO Approves Submitted IPD/EP | 9
10 | 16 | IPD/EP Approval Decision (Day Zero) | CEAO Requires the Proponent to Submit a Revised IPD/EP | 10
11 | 38 | Dispute Resolution Triggered | A Matter has been Referred for Dispute Resolution | 11
12 | 60 | EAC Assessment Terminated s.39(d) | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | 12
13 | 63 | Project Withdrawn | Proponent Withdraws Project from the EAC Assessment Process | 13
14 | 67 | Summary of Engagement Published | Last Day of EAC Assessment: Early Engagement PHASE | 14
15 | 75 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is POSITIVE | 15
16 | 75 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is NEGATIVE | 16
17 | 76 | Dispute Resolution Triggered | A Matter has been Referred for Dispute Resolution | 17
18 | 79 | EAC Assessment Terminated s.39(d) | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | 18
19 | 82 | Project Withdrawn | Proponent Withdraws Project from the EAC Assessment Process | 19
20 | 96 | Dispute Resolution Triggered | A Matter has been Referred for Dispute Resolution | 20
21 | 99 | EAC Assessment Terminated s.39(d) | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | 21
22 | 102 | Project Withdrawn | Proponent Withdraws Project from the EAC Assessment Process | 22
23 | 108 | CEAO's Readiness Decision (EAC Assessment) | CEAO Requires the Proponent to Submit a Revised DPD - s.16(2)(a) | 23
24 | 108 | CEAO's Readiness Decision (EAC Assessment) | Project is Referred to Minister for Termination - s.16(2)(c) | 24
25 | 108 | CEAO's Readiness Decision (EAC Assessment) | Project Moves to Process Planning PHASE - s.18(1)(a) | 25
26 | 108 | CEAO's Readiness Decision (EAC Assessment) | Project is Referred to Minister for Process Planning - s.18(1)(b) | 26
27 | 113 | EAC Assessment Terminated s.39(d) | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | 27
28 | 116 | Project Withdrawn | Proponent Withdraws Project from the EAC Assessment Process | 28
29 | 120 | Minister's Termination Decision | Project May Not Proceed as Proposed | 29
30 | 120 | Minister's Termination Decision | Project Referred to the CEAO for Further Readiness Decision | 30
31 | 124 | EAC Assessment Terminated s.39(d) | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | 31
32 | 127 | Project Withdrawn | Proponent Withdraws Project from the EAC Assessment Process | 32
33 | 132 | CEAO's Further Readiness Decision (EAC Assessment) | CEAO Requires the Proponent to Submit a Revised DPD - s.16(2)(a) | 33
34 | 132 | CEAO's Further Readiness Decision (EAC Assessment) | Project Moves to Process Planning PHASE - s.18(1)(a) | 34
35 | 132 | CEAO's Further Readiness Decision (EAC Assessment) | Project is Referred to Minister for Process Planning - s.18(1)(b) | 35
36 | 136 | Federal Involvement Determination | No Federal Involvement triggered for this WORK | 36
37 | 136 | Federal Involvement Determination | Federal Substitution Request Approved | 37
38 | 136 | Federal Involvement Determination | Other form of Federal Involvement (Coordination, etc.) | 38
39 | 152 | Dispute Resolution Triggered | A Matter has been Referred for Dispute Resolution | 39
40 | 174 | EAC Assessment Terminated s.39(d) | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | 40
41 | 177 | Project Withdrawn | Proponent Withdraws Project from the EAC Assessment Process | 41
42 | 181 | Process Order Issued & Regulatory Coordination Plan Posted | Last Day of EAC Assessment: Process Planning PHASE | 42
43 | 191 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is POSITIVE | 43
44 | 191 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is NEGATIVE | 44
45 | 192 | Dispute Resolution Triggered | A Matter has been Referred for Dispute Resolution | 45
46 | 195 | EAC Assessment Terminated s.39(d) | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | 46
47 | 198 | Project Withdrawn | Proponent Withdraws Project from the EAC Assessment Process | 47
48 | 218 | Dispute Resolution Triggered | A Matter has been Referred for Dispute Resolution | 48
49 | 240 | EAC Assessment Terminated s.39(d) | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | 49
50 | 243 | Project Withdrawn | Proponent Withdraws Project from the EAC Assessment Process | 50
51 | 247 | Notice to Proponent to Prepare Revised EAC Application | Last Day of EAC Assessment: EAC Application Review PHASE | 51
52 | 258 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is POSITIVE | 52
53 | 258 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is NEGATIVE | 53
54 | 259 | Dispute Resolution Triggered | A Matter has been Referred for Dispute Resolution | 54
55 | 262 | EAC Assessment Terminated s.39(d) | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | 55
56 | 265 | Project Withdrawn | Proponent Withdraws Project from the EAC Assessment Process | 56
57 | 269 | Revised EAC Application Acceptance Decision (Day Zero) | Revised EAC Application Sufficient to Proceed | 57
58 | 269 | Revised EAC Application Acceptance Decision (Day Zero) | Proponent must provide an updated Revised EAC Application | 58
59 | 286 | Dispute Resolution Triggered | A Matter has been Referred for Dispute Resolution | 59
60 | 308 | EAC Assessment Terminated s.39(d) | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | 60
61 | 311 | Project Withdrawn | Proponent Withdraws Project from the EAC Assessment Process | 61
62 | 316 | EAC Referral Package sent to Ministers | Last Day of EAC Assessment: Effects Assessment PHASE | 62
63 | 330 | Project Withdrawn | Proponent Withdraws Project from the EAC Assessment Process | 63
64 | 334 | EAC Ministers Decision | Environmental Assessment Certificate GRANTED | 64
65 | 334 | EAC Ministers Decision | Environmental Assessment Certificate REFUSED | 65

## Actions
No | OutcomeNo | OutcomeName | ActionName | ActionDescription | AdditionalParams | SortOrder
1 | 1 | Assessment Transitions to the EA Act (2018) Early Engagement PHASE | NONE | No Actions Needed | {} | 1
2 | 2 | Assessment Transitions to the EA Act (2018) Readiness Decision PHASE | SetEventsStatus | Set all "future" events in thisPhase to INACTIVE | {"all_future_events":false} | 2
3 | 2 | Assessment Transitions to the EA Act (2018) Readiness Decision PHASE | ChangePhaseEndEvent | Set thisEvent to PHASE END EVENT | {"phase_name":"Pre-EA (EAC Assessment)","work_type_id": 6, "ea_act_id": 3, "event_name": "Project Transitioning FROM the EA Act (2002)"} | 3
4 | 2 | Assessment Transitions to the EA Act (2018) Readiness Decision PHASE | SetPhasesStatus | Set "Early Engagement" PHASE to INACTIVE | [{"phase_name":"Early Engagement","work_type_id": 6, "ea_act_id": 3, "is_active": false }] | 4
5 | 2 | Assessment Transitions to the EA Act (2018) Readiness Decision PHASE | SetEventDate | Set "DPD Development (Proponent Time) ¦ Start of DPD Development (Day after SoE)" ANTICIPATED to thisEvent ACTUAL +1 | {"phase_name":"DPD Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "event_name": "Start of DPD Development (Day after SoE)", "start_at": 1 } | 5
6 | 3 | Assessment Transitions to the EA Act (2018) Process Planning PHASE | SetEventsStatus | Set all "future" events in thisPhase to INACTIVE | {"all_future_events":false} | 6
7 | 3 | Assessment Transitions to the EA Act (2018) Process Planning PHASE | AddEvent | Add EVENT "Pre-EA (EAC Assessment) ¦ Last Day of Pre-EA (EAC Assessment)" as a "Milestone: Date Capture" EVENT (a new EVENT) | [{"phase_name":"Pre-EA (EAC Assessment)","work_type_id": 6, "ea_act_id": 3, "event_name": "Last Day of Pre-EA (EAC Assessment)", "start_at": 1 }] | 7
8 | 3 | Assessment Transitions to the EA Act (2018) Process Planning PHASE | SetEventDate | Set "Pre-EA (EAC Assessment) ¦ Last Day of Pre-EA (EAC Assessment)" ANTICIPATED to thisEvent ACTUAL +28 | {"phase_name":"Pre-EA (EAC Assessment)","work_type_id": 6, "ea_act_id": 3, "event_name": "Last Day of Pre-EA (EAC Assessment)", "start_at": 28 } | 8
9 | 3 | Assessment Transitions to the EA Act (2018) Process Planning PHASE | ChangePhaseEndEvent | Set "Pre-EA (EAC Assessment) ¦ Last Day of Pre-EA (EAC Assessment)" to PHASE END EVENT | {"phase_name":"Pre-EA (EAC Assessment)","work_type_id": 6, "ea_act_id": 3, "event_name": "Last Day of Pre-EA (EAC Assessment)"} | 9
10 | 3 | Assessment Transitions to the EA Act (2018) Process Planning PHASE | SetPhasesStatus | Set "Early Engagement", "DPD Development (Proponent Time)", and "Readiness Decision" PHASEs to INACTIVE | [{"phase_name":"Early Engagement","work_type_id": 6, "ea_act_id": 3, "is_active": false }, {"phase_name":"DPD Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "is_active": false },{"phase_name":"Readiness Decision","work_type_id": 6, "ea_act_id": 3, "is_active": false }] | 10
11 | 3 | Assessment Transitions to the EA Act (2018) Process Planning PHASE | SetEventDate | Set "Process Planning ¦ Start of Process Planning (Day One)" ANTICIPATED to thisEvent ACTUAL +29 | {"phase_name":"Process Planning","work_type_id": 6, "ea_act_id": 3, "event_name": "Start of Process Planning (Day One)", "start_at": 29 } | 11
12 | 4 | Assessment Transitions to the EA Act (2018) EAC Application Review PHASE | SetEventsStatus | Set all "future" events in thisPhase to INACTIVE | {"all_future_events":false} | 12
13 | 4 | Assessment Transitions to the EA Act (2018) EAC Application Review PHASE | ChangePhaseEndEvent | Set thisEvent to PHASE END EVENT | {"phase_name":"Pre-EA (EAC Assessment)","work_type_id": 6, "ea_act_id": 3, "event_name": "Project Transitioning FROM the EA Act (2002)"} | 13
14 | 4 | Assessment Transitions to the EA Act (2018) EAC Application Review PHASE | SetPhasesStatus | Set "Early Engagement", "DPD Development (Proponent Time)", "Readiness Decision", and "Process Planning" PHASEs to INACTIVE | [{"phase_name":"Early Engagement","work_type_id": 6, "ea_act_id": 3, "is_active": false }, {"phase_name":"DPD Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "is_active": false },{"phase_name":"Readiness Decision","work_type_id": 6, "ea_act_id": 3, "is_active": false },{"phase_name":"Process Planning","work_type_id": 6, "ea_act_id": 3, "is_active": false }] | 14
15 | 4 | Assessment Transitions to the EA Act (2018) EAC Application Review PHASE | SetEventDate | Set "EAC Application Development (Proponent Time) ¦ Start of EAC Application Development" ANTICIPATED to thisEvent ACTUAL +1 | {"phase_name":"EAC Application Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "event_name": "Start of EAC Application Development", "start_at": 1 } | 15
16 | 5 | Assessment Transitions to the EA Act (2018) Effects Assessment PHASE | SetEventsStatus | Set all "future" events in thisPhase to INACTIVE | {"all_future_events":false} | 16
17 | 5 | Assessment Transitions to the EA Act (2018) Effects Assessment PHASE | ChangePhaseEndEvent | Set thisEvent to PHASE END EVENT | {"phase_name":"Pre-EA (EAC Assessment)","work_type_id": 6, "ea_act_id": 3, "event_name": "Project Transitioning FROM the EA Act (2002)"} | 17
18 | 5 | Assessment Transitions to the EA Act (2018) Effects Assessment PHASE | SetPhasesStatus | Set "Early Engagement", "DPD Development (Proponent Time)", "Readiness Decision", "Process Planning", "EAC Application Development (Proponent Time)", and "EAC Application Review" PHASEs to INACTIVE | [{"phase_name":"Early Engagement","work_type_id": 6, "ea_act_id": 3, "is_active": false }, {"phase_name":"DPD Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "is_active": false },{"phase_name":"Readiness Decision","work_type_id": 6, "ea_act_id": 3, "is_active": false },{"phase_name":"Process Planning","work_type_id": 6, "ea_act_id": 3, "is_active": false },{"phase_name":"EAC Application Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "is_active": false },{"phase_name":"EAC Application Review","work_type_id": 6, "ea_act_id": 3, "is_active": false }] | 18
19 | 5 | Assessment Transitions to the EA Act (2018) Effects Assessment PHASE | SetEventDate | Set "Revised EAC Application Development (Proponent Time) ¦ Start of Revised EAC Application Development" ANTICIPATED to thisEvent ACTUAL +1 | {"phase_name":"Revised EAC Application Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "event_name": "Start of Revised EAC Application Development", "start_at": 1 } | 19
20 | 6 | EAO's Viewpoint is POSITIVE | NONE | No Actions Needed | {} | 20
21 | 7 | EAO's Viewpoint is NEGATIVE | NONE | No Actions Needed | {} | 21
22 | 8 | Proponent withdraws Project from the EAC Assessment Process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 22
23 | 8 | Proponent withdraws Project from the EAC Assessment Process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 23
24 | 8 | Proponent withdraws Project from the EAC Assessment Process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 24
25 | 8 | Proponent withdraws Project from the EAC Assessment Process | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 25
26 | 9 | CEAO Approves Submitted IPD/EP | LockWorkStartDate | Set the workStartDate to thisEvent ACTUAL | {"start_date_locked": true} | 26
27 | 9 | CEAO Approves Submitted IPD/EP | SetEventDate | Set "Early Engagement ¦ IPD/EP Approved (Day One)" ANTICIPATED to thisEvent ACTUAL +1 | {"phase_name":"Early Engagement","work_type_id": 6, "ea_act_id": 3, "event_name": "IPD/EP Approved (Day One)", "start_at": 28 } | 27
28 | 10 | CEAO Requires the Proponent to Submit a Revised IPD/EP | AddEvent | Add EVENT "Pre-EA (EAC Assessment) ¦ Submission of Revised IPD/EP for CEAO Approval" at thisEvent ACTUAL +28 (a renamed copy of original EVENT),Add EVENT "Pre-EA (EAC Assessment) ¦ Revised IPD/EP Approval Decision (Day Zero)" at thisEvent ACTUAL +38 (a renamed copy of original EVENT) | [{"phase_name":"Pre-EA (EAC Assessment)","work_type_id": 6, "ea_act_id": 3, "event_name": "Submission of IPD/EP for CEAO Approval", "start_at": 28 },{"phase_name":"Pre-EA (EAC Assessment)","work_type_id": 6, "ea_act_id": 3, "event_name": "IPD/EP Approval Decision (Day Zero)", "start_at": 10 }] | 28
30 | 10 | CEAO Requires the Proponent to Submit a Revised IPD/EP | ChangePhaseEndEvent | Set "Pre-EA (EAC Assessment) ¦ Revised IPD/EP Approval Decision (Day Zero)" to PHASE END EVENT | {"phase_name":"Pre-EA (EAC Assessment)","work_type_id": 6, "ea_act_id": 3, "event_name": "IPD/EP Approval Decision (Day Zero)"} | 29
31 | 11 | A Matter has been Referred for Dispute Resolution | CreateWork | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {"work_type": 15} | 30
32 | 12 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 31
33 | 12 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 32
34 | 12 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 33
35 | 12 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 34
36 | 13 | Proponent Withdraws Project from the EAC Assessment Process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 35
37 | 13 | Proponent Withdraws Project from the EAC Assessment Process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 36
38 | 13 | Proponent Withdraws Project from the EAC Assessment Process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 37
39 | 13 | Proponent Withdraws Project from the EAC Assessment Process | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 38
40 | 14 | Last Day of EAC Assessment: Early Engagement PHASE | SetEventDate | Set "Start of DPD Development (Day after SoE) ¦ DPD Development (Proponent Time)" ANTICIPATED to thisEvent ACTUAL +1 | {"phase_name":"DPD Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "event_name": "Start of DPD Development", "start_at": 1 } | 39
41 | 15 | EAO's Viewpoint is POSITIVE | NONE | No Actions Needed | {} | 40
42 | 16 | EAO's Viewpoint is NEGATIVE | NONE | No Actions Needed | {} | 41
43 | 17 | A Matter has been Referred for Dispute Resolution | CreateWork | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {"work_type": 15} | 42
44 | 18 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 43
45 | 18 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 44
46 | 18 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 45
47 | 18 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 46
48 | 19 | Proponent Withdraws Project from the EAC Assessment Process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 47
49 | 19 | Proponent Withdraws Project from the EAC Assessment Process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 48
50 | 19 | Proponent Withdraws Project from the EAC Assessment Process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 49
51 | 19 | Proponent Withdraws Project from the EAC Assessment Process | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 50
52 | 20 | A Matter has been Referred for Dispute Resolution | CreateWork | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {"work_type": 15} | 51
53 | 21 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 52
54 | 21 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 53
55 | 21 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 54
56 | 21 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 55
57 | 22 | Proponent Withdraws Project from the EAC Assessment Process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 56
58 | 22 | Proponent Withdraws Project from the EAC Assessment Process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 57
59 | 22 | Proponent Withdraws Project from the EAC Assessment Process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 58
60 | 22 | Proponent Withdraws Project from the EAC Assessment Process | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 59
61 | 23 | CEAO Requires the Proponent to Submit a Revised DPD - s.16(2)(a) | AddPhase | Add PHASE "Revised DPD Development (Proponent Time)" (a renamed copy of original PHASE),Add PHASE "Readiness Decision" (a copy of original PHASE) | [{"phase_name":"DPD Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "new_name": "Revised DPD Development (Proponent Time)", "legislated": false },{"phase_name":"Readiness Decision","work_type_id": 6, "ea_act_id": 3, "new_name": "Revised Readiness Decision", "legislated": false }] | 60
63 | 23 | CEAO Requires the Proponent to Submit a Revised DPD - s.16(2)(a) | SetEventsStatus | Set "Readiness Decision ¦ Fee Order: Submission of DPD" EVENT to INACTIVE | [{"phase_name":"Readiness Decision","work_type_id": 6, "ea_act_id": 3, "event_name": "Fee Order: Submission of DPD", "is_active": false }] | 61
64 | 23 | CEAO Requires the Proponent to Submit a Revised DPD - s.16(2)(a) | SetEventDate | Set "Revised DPD Development (Proponent Time) ¦ Start of DPD Development" ANTICIPATED to thisEvent ACTUAL +1 | {"phase_name":"Revised DPD Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "event_name": "Start of DPD Development", "start_at": 1 } | 62
65 | 24 | Project is Referred to Minister for Termination - s.16(2)(c) | AddPhase | Set "Termination Decision" PHASE to ACTIVE | [{"phase_name":"Termination Decision","work_type_id": 6, "ea_act_id": 3, "new_name": "Termination Decision", "legislated": false }] | 63
66 | 24 | Project is Referred to Minister for Termination - s.16(2)(c) | AddEvent | Set "Readiness Decision ¦ Termination Package Referred to Minister", "Readiness Decision ¦ Last Day of Readiness Decision (Termination)" EVENTs to ACTIVE | [{"phase_name":"Readiness Decision","work_type_id": 6, "ea_act_id": 3, "event_name": "Termination Package Referred to Minister", "start_at": 1 },{"phase_name":"Readiness Decision","work_type_id": 6, "ea_act_id": 3, "event_name": "Last Day of Readiness Decision (Termination)", "start_at": 0 }] | 64
67 | 24 | Project is Referred to Minister for Termination - s.16(2)(c) | SetEventDate | Set "Readiness Decision ¦ Termination Package Referred to Minister" ANTICIPATED to thisEvent ACTUAL +5 | {"phase_name":"Readiness Decision","work_type_id": 6, "ea_act_id": 3, "event_name": "Termination Package Referred to Minister", "start_at": 5 } | 65
68 | 24 | Project is Referred to Minister for Termination - s.16(2)(c) | SetEventDate | Set "Readiness Decision ¦ Last Day of Readiness Decision (Termination)" ANTICIPATED to thisEvent ACTUAL +10 | {"phase_name":"Readiness Decision","work_type_id": 6, "ea_act_id": 3, "event_name": "Last Day of Readiness Decision (Termination)", "start_at": 10 } | 66
69 | 24 | Project is Referred to Minister for Termination - s.16(2)(c) | ChangePhaseEndEvent | Set "Readiness Decision ¦ Last Day of Readiness Decision (Termination)" to PHASE END EVENT | {"phase_name":"Readiness Decision","work_type_id": 6, "ea_act_id": 3, "event_name": "Last Day of Readiness Decision (Termination)" } | 67
70 | 25 | Project Moves to Process Planning PHASE - s.18(1)(a) | SetEventDate | Set "Process Planning ¦ Start of Process Planning (Day One)" ANTICIPATED to thisEvent ACTUAL +1 | {"phase_name":"Process Planning","work_type_id": 6, "ea_act_id": 3, "event_name": "Start of Process Planning (Day One)", "start_at": 1 } | 68
71 | 26 | Project is Referred to Minister for Process Planning - s.18(1)(b) | NONE | Process is UNKNOWN at this time | {} | 69
72 | 27 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 70
73 | 27 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 71
74 | 27 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 72
75 | 27 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 73
76 | 28 | Proponent Withdraws Project from the EAC Assessment Process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 74
77 | 28 | Proponent Withdraws Project from the EAC Assessment Process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 75
78 | 28 | Proponent Withdraws Project from the EAC Assessment Process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 76
79 | 28 | Proponent Withdraws Project from the EAC Assessment Process | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 77
80 | 29 | Project May Not Proceed as Proposed | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 78
81 | 29 | Project May Not Proceed as Proposed | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 79
82 | 29 | Project May Not Proceed as Proposed | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 80
83 | 30 | Project Referred to the CEAO for Further Readiness Decision | AddPhase | Set "Further Readiness Decision" PHASE to ACTIVE | [{"phase_name":"Further Readiness Decision","work_type_id": 6, "ea_act_id": 3, "new_name": "Further Readiness Decision", "legislated": false }] | 81
84 | 30 | Project Referred to the CEAO for Further Readiness Decision | SetEventDate | Set "Further Readiness Decision ¦ Readiness Decision Report referred to CEAO for Further Decision" ANTICIPATED to thisEvent ACTUAL +1 | {"phase_name":"Further Readiness Decision","work_type_id": 6, "ea_act_id": 3, "event_name": "Readiness Decision Report referred to CEAO for Further Decision", "start_at": 1 } | 82
85 | 31 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 83
86 | 31 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 84
87 | 31 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 85
88 | 31 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 86
89 | 32 | Proponent Withdraws Project from the EAC Assessment Process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 87
90 | 32 | Proponent Withdraws Project from the EAC Assessment Process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 88
91 | 32 | Proponent Withdraws Project from the EAC Assessment Process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 89
92 | 32 | Proponent Withdraws Project from the EAC Assessment Process | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 90
93 | 33 | CEAO Requires the Proponent to Submit a Revised DPD - s.16(2)(a) | AddPhase | Add PHASE "Revised DPD Development (Proponent Time)" (a renamed copy of original PHASE),Add PHASE "Readiness Decision" (a copy of original PHASE) | [{"phase_name":"DPD Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "new_name": "Revised DPD Development (Proponent Time)", "legislated": false },{"phase_name":"Readiness Decision","work_type_id": 6, "ea_act_id": 3, "new_name": "Readiness Decision", "legislated": false }] | 91
95 | 33 | CEAO Requires the Proponent to Submit a Revised DPD - s.16(2)(a) | SetEventsStatus | Set "Readiness Decision ¦ Fee Order: Submission of DPD" EVENT to INACTIVE | [{"phase_name":"Readiness Decision","work_type_id": 6, "ea_act_id": 3, "event_name": "Fee Order: Submission of DPD", "is_active": false }] | 92
96 | 33 | CEAO Requires the Proponent to Submit a Revised DPD - s.16(2)(a) | SetEventDate | Set "Revised DPD Development (Proponent Time) ¦ Start of DPD Development" ANTICIPATED to thisEvent ACTUAL +1 | {"phase_name":"Revised DPD Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "event_name": "Start of DPD Development", "start_at": 1 } | 93
97 | 34 | Project Moves to Process Planning PHASE - s.18(1)(a) | SetEventDate | Set "Process Planning ¦ Start of Process Planning (Day One)" ANTICIPATED to thisEvent ACTUAL +1 | {"phase_name":"Process Planning","work_type_id": 6, "ea_act_id": 3, "event_name": "Start of Process Planning (Day One)", "start_at": 1 } | 94
98 | 35 | Project is Referred to Minister for Process Planning - s.18(1)(b) | NONE | Process is UNKNOWN at this time | {} | 95
99 | 36 | No Federal Involvement triggered for this WORK | SetFederalInvolvement | Set workFederalInvolvement to "None" | {"federal_involvement_id": 2} | 96
100 | 37 | Federal Substitution Request Approved | SetFederalInvolvement | Set workFederalInvolvement to "Substituted" | {"federal_involvement_id": 8} | 97
101 | 38 | Other form of Federal Involvement (Coordination, etc.) | NONE | Process is UNKNOWN at this time | {} | 98
102 | 39 | A Matter has been Referred for Dispute Resolution | CreateWork | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {"work_type": 15} | 99
103 | 40 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 100
104 | 40 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 101
105 | 40 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 102
106 | 40 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 103
107 | 41 | Proponent Withdraws Project from the EAC Assessment Process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 104
108 | 41 | Proponent Withdraws Project from the EAC Assessment Process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 105
109 | 41 | Proponent Withdraws Project from the EAC Assessment Process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 106
110 | 41 | Proponent Withdraws Project from the EAC Assessment Process | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 107
111 | 42 | Last Day of EAC Assessment: Process Planning PHASE | SetEventDate | Set "EAC Application Development (Proponent Time)¦ Start of EAC Application Development" ANTICIPATED to thisEvent ACTUAL +1 | {"phase_name":"EAC Application Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "event_name": "Start of EAC Application Development", "start_at": 1 } | 108
112 | 43 | EAO's Viewpoint is POSITIVE | NONE | No Actions Needed | {} | 109
113 | 44 | EAO's Viewpoint is NEGATIVE | NONE | No Actions Needed | {} | 110
114 | 45 | A Matter has been Referred for Dispute Resolution | CreateWork | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {"work_type": 15} | 111
115 | 46 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 112
116 | 46 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 113
117 | 46 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 114
118 | 46 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 115
119 | 47 | Proponent Withdraws Project from the EAC Assessment Process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 116
120 | 47 | Proponent Withdraws Project from the EAC Assessment Process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 117
121 | 47 | Proponent Withdraws Project from the EAC Assessment Process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 118
122 | 47 | Proponent Withdraws Project from the EAC Assessment Process | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 119
123 | 48 | A Matter has been Referred for Dispute Resolution | CreateWork | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {"work_type": 15} | 120
124 | 49 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 121
125 | 49 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 122
126 | 49 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 123
127 | 49 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 124
128 | 50 | Proponent Withdraws Project from the EAC Assessment Process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 125
129 | 50 | Proponent Withdraws Project from the EAC Assessment Process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 126
130 | 50 | Proponent Withdraws Project from the EAC Assessment Process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 127
131 | 50 | Proponent Withdraws Project from the EAC Assessment Process | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 128
132 | 51 | Last Day of EAC Assessment: EAC Application Review PHASE | SetEventDate | Set "Revised EAC Application Development (Proponent Time) ¦ Start of Revised EAC Application Development" ANTICIPATED to thisEvent ACTUAL +1 | {"phase_name":"Revised EAC Application Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "event_name": "Start of Revised EAC Application Development", "start_at": 1 } | 129
133 | 52 | EAO's Viewpoint is POSITIVE | NONE | No Actions Needed | {} | 130
134 | 53 | EAO's Viewpoint is NEGATIVE | NONE | No Actions Needed | {} | 131
135 | 54 | A Matter has been Referred for Dispute Resolution | CreateWork | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {"work_type": 15} | 132
136 | 55 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 133
137 | 55 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 134
138 | 55 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 135
139 | 55 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 136
140 | 56 | Proponent Withdraws Project from the EAC Assessment Process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 137
141 | 56 | Proponent Withdraws Project from the EAC Assessment Process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 138
142 | 56 | Proponent Withdraws Project from the EAC Assessment Process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 139
143 | 56 | Proponent Withdraws Project from the EAC Assessment Process | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 140
144 | 57 | Revised EAC Application Sufficient to Proceed | SetEventDate | Set "Effects Assessment & Recommendation ¦ Start of Effects Assessment (Day One)" ANTICIPATED to thisEvent ACTUAL +1 | {"phase_name":"Effects Assessment & Recommendation","work_type_id": 6, "ea_act_id": 3, "event_name": "Start of Effects Assessment (Day One)", "start_at": 1 } | 141
145 | 58 | Proponent must provide an updated Revised EAC Application | AddEvent | Add EVENT "Revised EAC Application Development (Proponent Time) ¦ Submission of Updated Revised EAC Application for Acceptance" at thisEvent ACTUAL +28 (a renamed copy of original EVENT),Add EVENT "Revised EAC Application Development (Proponent Time) ¦ Updated Revised EAC Application Acceptance Decision (Day Zero)" at thisEvent ACTUAL +88 (a renamed copy of original EVENT) | [{"phase_name":"Revised EAC Application Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "event_name": "Submission of Revised EAC Application for CEAO Acceptance", "start_at": 28 },{"phase_name":"Revised EAC Application Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "event_name": "Revised EAC Application Acceptance Decision (Day Zero)", "start_at": 60 }] | 142
147 | 58 | Proponent must provide an updated Revised EAC Application | ChangePhaseEndEvent | Set "Revised EAC Application Development (Proponent Time) ¦ Updated Revised EAC Application Acceptance Decision (Day Zero)" to PHASE END EVENT | {"phase_name":"Revised EAC Application Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "event_name": "Revised EAC Application Acceptance Decision (Day Zero)"} | 143
148 | 59 | A Matter has been Referred for Dispute Resolution | CreateWork | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {"work_type": 15} | 144
149 | 60 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 145
150 | 60 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 146
151 | 60 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 147
152 | 60 | EAC Assessment is Terminated under s.39(d) of EA Act (2018) | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 148
153 | 61 | Proponent Withdraws Project from the EAC Assessment Process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 149
154 | 61 | Proponent Withdraws Project from the EAC Assessment Process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 150
155 | 61 | Proponent Withdraws Project from the EAC Assessment Process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 151
156 | 61 | Proponent Withdraws Project from the EAC Assessment Process | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 152
157 | 62 | Last Day of EAC Assessment: Effects Assessment PHASE | SetEventDate | Set "EAC Decision ¦ EAC Referral Package Received by Ministers" ANTICIPATED to thisEvent ACTUAL +1 | {"phase_name":"EAC Decision","work_type_id": 6, "ea_act_id": 3, "event_name": "EAC Referral Package Received by Ministers", "start_at": 1 } | 153
158 | 63 | Proponent Withdraws Project from the EAC Assessment Process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 154
159 | 63 | Proponent Withdraws Project from the EAC Assessment Process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 155
160 | 63 | Proponent Withdraws Project from the EAC Assessment Process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 156
161 | 63 | Proponent Withdraws Project from the EAC Assessment Process | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 157
162 | 64 | Environmental Assessment Certificate GRANTED | SetWorkState | Set workState to COMPLETED | {"work_state": "COMPLETED"} | 158
163 | 64 | Environmental Assessment Certificate GRANTED | SetProjectState | Set linked PROJECT projectState to "Active: Pre-Construction" | {"project_state": "PRE_CONSTRUCTION"} | 159
164 | 65 | Environmental Assessment Certificate REFUSED | SetWorkState | Set workState to COMPLETED | {"work_state": "COMPLETED"} | 160
165 | 65 | Environmental Assessment Certificate REFUSED | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 161
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
====================================================================== | ====================================================================== | ====================================================================== | ====================================================================== | ====================================================================== | ====================================================================== | ======================================================================

## Lookups
WorkType | EA Act | Legislated |  | Event Type | Event Category | Visibility | ActionName | Event Position | Multiple Days | Action Name
Project Notification | EA Act (2018) | TRUE | Milestone | Generic | Milestone | MANDATORY | AllEventsDeactivated | START | TRUE | AddEvent
Minister's Designation | EA Act (2002) | FALSE | Milestone | Meeting | Calendar | SUGGESTED | AllEventsDeleted | INTERMEDIATE | FALSE | AddPhase
CEAO's Designation | EA Act (1996) |  | Milestone | Notification | Decision | OPTIONAL | CloseEverything | END |  | ChangePhaseEndEvent
Assessment |  |  | Milestone | Order | Finance | HIDDEN | CloseWork |  |  | CreateWork
Exemption Request |  |  | Milestone | Referral | PCP |  | CompleteCurrentPhase |  |  | LockWorkStartDate
Dispute Resolution |  |  | Milestone | Report | Extension |  | CreateNewWork |  |  | SetEventDate
EAC/Order Amendment |  |  | Milestone | Request | Suspension |  | DisableWorkStartDate |  |  | SetEventStatus
Document Review |  |  | Milestone | Submission |  |  | DuplicatePhase |  |  | SetFederalInvolvement
EAC Extension |  |  | Milestone | Other | [5 empty] | SetPhaseStatus
Substantial Start Decision |  |  | Milestone | Date Capture | [5 empty] | SetProjectState
EAC/Order Transfer |  |  | Extension | Time Limit Extension | [5 empty] | SetProjectStatus
EAC/Order Suspension |  |  | Extension | PCP Time Limit Extension | [5 empty] | SetWorkDecisionMaker
EAC/Order Cancellation |  |  | Extension | Interregnum | [5 empty] | SetWorkState
Other |  |  | Suspension | Time Limit Suspension | [5 empty] | NONE
|  |  | Suspension | Time Limit Resumption
|  |  | Decision | EAC Ministers
|  |  | Decision | Minister
|  |  | Decision | CEAO
|  |  | Decision | ADM
|  |  | Decision | EPD
|  |  | Decision | PAD (Lead)
|  |  | Decision | Reviewer
|  |  | Decision | Federal
|  |  | Decision | Other
|  |  | PCP | Comment Period
|  |  | PCP | Open House
|  |  | PCP | Virtual Information Session
|  |  | PCP | Other
|  |  | Calendar | Communications
|  |  | Calendar | Executive
|  |  | Calendar | Financial
|  |  | Calendar | Work
|  |  | Calendar | Other
|  |  | Finance | Capacity Funding
|  |  | Finance | Fee Order
|  |  | Finance | Penalties
|  |  | Finance | Administrative
|  |  | Finance | Other