## Phases
No | Name | WorkType | EAAct | NumberOfDays | Legislated | Color | Visibility | SortOrder
1 | Minister's Designation Intake | Minister's Designation | EA Act (2018) | 14 | FALSE | #3eb1d7 | REGULAR | 1
2 | Minister's Designation Application Review | Minister's Designation | EA Act (2018) | 25 | TRUE | #3eb1d7 | REGULAR | 2
3 | Minister's Designation Application Development | Minister's Designation | EA Act (2018) | 30 | FALSE | #3eb1d7 | HIDDEN | 3
4 | Minister's Designation Decision | Minister's Designation | EA Act (2018) | 5 | TRUE | #3eb1d7 | REGULAR | 4

## Events
No | Parent | PhaseNo | EventName | Phase | EventType | EventCategory | EventPosition | MultipleDays | StartAt | NumberOfDays | Visibility | SortOrder
1 |  | 1 | Start of Intake (e.g. Initial Meeting, Date Confirmation, or Draft Sharing) | Minister's Designation Intake | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 1
2 |  | 1 | Additional Information Submission | Minister's Designation Intake | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 2
3 |  | 1 | Document Submitted to EAO for "Initial Review" | Minister's Designation Intake | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 3
4 | 3 | 1 | EAO's Viewpoint on Submitted Document | Minister's Designation Intake | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 4
5 |  | 1 | Minister's Designation Application Withdrawn | Minister's Designation Intake | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 5
6 |  | 1 | Direct Submission of Minister's Designation Application - DELETE this Intake Phase! | Minister's Designation Intake | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 6
7 |  | 1 | Other | Minister's Designation Intake | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 7
8 |  | 1 | Last Day of Minister's Designation Intake (day before Application submission) | Minister's Designation Intake | Date Capture | Milestone | END | FALSE | 14 | 0 | MANDATORY | 8
9 |  | 2 | Submission of Minister's Designation Application to the EAO (day zero) | Minister's Designation Application Review | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 9
10 |  | 2 | Screening Decision for Minister's Designation Application | Minister's Designation Application Review | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 3 | 0 | MANDATORY | 10
11 |  | 2 | Delegation of Decision | Minister's Designation Application Review | Minister | Decision | INTERMEDIATE | FALSE | 21 | 0 | MANDATORY | 11
12 |  | 2 | Complete Minister's Designation Report | Minister's Designation Application Review | Report | Milestone | INTERMEDIATE | FALSE | 21 | 0 | SUGGESTED | 12
13 |  | 2 | Additional Information Submission | Minister's Designation Application Review | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 13
14 |  | 2 | Circulate Draft Designation Report | Minister's Designation Application Review | Generic | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 14
15 |  | 2 | Additional Comment Period | Minister's Designation Application Review | Comment Period | PCP | INTERMEDIATE | TRUE | 0 | 30 | OPTIONAL | 15
16 | 15 | 2 | PCP Coming Soon Announcement & Tweet | Minister's Designation Application Review | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | 16
17 | 15 | 2 | Additional PCP Milestone Bullet | Minister's Designation Application Review | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | 17
18 | 15 | 2 | PCP Now Open Announcement & Tweet | Minister's Designation Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 18
19 | 15 | 2 | PCP Ending Soon Announcement & Tweet | Minister's Designation Application Review | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | OPTIONAL | 19
20 |  | 2 | Open House | Minister's Designation Application Review | Open House | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 20
21 |  | 2 | Virtual Information Session | Minister's Designation Application Review | Virtual Information Session | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 21
22 |  | 2 | Comment Period Time Limit Extension | Minister's Designation Application Review | PCP Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | 22
23 | 22 | 2 | PCP Extended Announcement & Tweet | Minister's Designation Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 23
24 | 22 | 2 | PCP Extended Milestone Bullet | Minister's Designation Application Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 24
25 |  | 2 | s.38 Extension of Time Limit | Minister's Designation Application Review | Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | 25
26 | 25 | 2 | Extension Announcement & Tweet | Minister's Designation Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 26
27 | 25 | 2 | Time Limit Extended Milestone Bullet | Minister's Designation Application Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 27
28 |  | 2 | Minister's Designation Process Terminated s.39(d) | Minister's Designation Application Review | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 28
29 | 28 | 2 | Termination Announcement & Tweet | Minister's Designation Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 29
30 | 28 | 2 | Minister's Designation Terminated Milestone Bullet | Minister's Designation Application Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 30
31 |  | 2 | Minister's Designation Application Withdrawn | Minister's Designation Application Review | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 31
32 | 31 | 2 | Withdrawal Announcement & Tweet | Minister's Designation Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 32
33 | 31 | 2 | Minister's Designation Application Withdrawn Milestone Bullet | Minister's Designation Application Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 33
34 |  | 2 | Other | Minister's Designation Application Review | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 34
35 |  | 2 | Minister's Designation Report referred to Decision Maker | Minister's Designation Application Review | Referral | Milestone | END | FALSE | 25 | 0 | MANDATORY | 35
36 |  | 3 | Start of Minister's Designation Application Development (Submitter Time) | Minister's Designation Application Development | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 36
37 |  | 3 | Additional Information Submission | Minister's Designation Application Development | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 37
38 |  | 3 | Document Submitted to EAO for "Initial Review" | Minister's Designation Application Development | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 38
39 | 38 | 3 | EAO's Viewpoint on Submitted Document | Minister's Designation Application Development | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 39
40 |  | 3 | Minister's Designation Application Withdrawn | Minister's Designation Application Development | EPD | Decision | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | 40
41 |  | 3 | Other | Minister's Designation Application Development | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 41
42 |  | 3 | Last Day of Minister's Designation Application Development (day before Application submission) | Minister's Designation Application Development | Date Capture | Milestone | END | FALSE | 30 | 0 | MANDATORY | 42
43 |  | 4 | Minister's Designation Report Received by Decision Maker | Minister's Designation Decision | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 43
44 |  | 4 | Create Minister's Designation Decision Milestone Bullet (only if CEAO) | Minister's Designation Decision | Generic | Milestone | INTERMEDIATE | FALSE | 3 | 0 | SUGGESTED | 44
45 | 44 | 4 | REMINDER: Create Minister's Designation Decision Milestone Bullet Due (only if CEAO) | Minister's Designation Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | SUGGESTED | 45
46 |  | 4 | Additional Information Submission | Minister's Designation Decision | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 46
47 |  | 4 | s.38 Extension of Time Limit | Minister's Designation Decision | Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | 47
48 | 47 | 4 | Extension Announcement & Tweet | Minister's Designation Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 48
49 | 47 | 4 | Time Limit Extended Milestone Bullet | Minister's Designation Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 49
50 |  | 4 | Minister's Designation Application Withdrawn | Minister's Designation Decision | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 50
51 | 50 | 4 | Withdrawal Announcement & Tweet | Minister's Designation Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 51
52 | 50 | 4 | Minister's Designation Application Withdrawn Milestone Bullet | Minister's Designation Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 52
53 |  | 4 | Other | Minister's Designation Decision | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 53
54 |  | 4 | Minister's Designation Decision | Minister's Designation Decision | Minister | Decision | END | FALSE | 5 | 0 | MANDATORY | 54
55 | 54 | 4 | Minister's Designation Decision Announcement & Tweet | Minister's Designation Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 55
56 | 54 | 4 | Minister's Designation Decision Milestone Bullet (only if CEAO) | Minister's Designation Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 56

## Outcomes
No | TemplateNo | TemplateName | OutcomeName | SortOrder
1 | 4 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is POSITIVE | 1
2 | 4 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is NEGATIVE | 2
3 | 5 | Minister's Designation Application Withdrawn | Proponent Withdraws Project from the Minister's Designation Process | 3
4 | 6 | Direct Submission of Minister's Designation Application - DELETE this Intake Phase! | Delete this "Intake Phase" and go directly to "Minister's Designation Review" | 4
5 | 10 | Screening Decision for Minister's Designation Application | Draft Minister's Designation Application is "incomplete" | 5
6 | 10 | Screening Decision for Minister's Designation Application | Draft Minister's Designation Application is for an "eligible" project | 6
7 | 10 | Screening Decision for Minister's Designation Application | Project submitted exceeds RPR threshold(s) | 7
8 | 10 | Screening Decision for Minister's Designation Application | Project submitted exceeds RPR threshold(s) and is Substantially Started | 8
9 | 11 | Delegation of Decision | Minister to make the Minister's Designation Decision | 9
10 | 11 | Delegation of Decision | CEAO is delegated to make the Minister's Designation Decision | 10
11 | 28 | Minister's Designation Process Terminated s.39(d) | Minister's Designation request is Terminated under s.39(d) of Act | 11
12 | 31 | Minister's Designation Application Withdrawn | Proponent Withdraws Project from the Minister's Designation Process | 12
13 | 39 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is POSITIVE | 13
14 | 39 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is NEGATIVE | 14
15 | 40 | Minister's Designation Application Withdrawn | Proponent Withdraws Project from the Minister's Designation Process | 15
16 | 50 | Minister's Designation Application Withdrawn | Proponent Withdraws Project from the Minister's Designation Process | 16
17 | 54 | Minister's Designation Decision | Decision Maker Designates Project as Reviewable | 17
18 | 54 | Minister's Designation Decision | Decision Maker Declines to Designate Project as Reviewable | 18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51

## Actions
No | OutcomeNo | OutcomeName | ActionName | ActionDescription | AdditionalParams | SortOrder
1 | 1 | EAO's Viewpoint is POSITIVE | NONE | No Actions Needed | {} | 1
2 | 2 | EAO's Viewpoint is NEGATIVE | NONE | No Actions Needed | {} | 2
3 | 3 | Proponent Withdraws Project from the Minister's Designation Process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 3
4 | 3 | Proponent Withdraws Project from the Minister's Designation Process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 4
5 | 3 | Proponent Withdraws Project from the Minister's Designation Process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 5
6 | 3 | Proponent Withdraws Project from the Minister's Designation Process | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 6
7 | 4 | Delete this "Intake Phase" and go directly to "Minister's Designation Review" | SetEventDate | Set "Minister's Designation Application Review ¦ Submission of Minister's Designation Application to the EAO (day zero)" ANTICIPATED to thisEvent ACTUAL | {"phase_name":"Minister's Designation Application Review","work_type_id": 2, "ea_act_id": 3, "event_name": "Submission of Minister's Designation Application to the EAO (day zero)", "start_at": 0 } | 7
8 | 4 | Delete this "Intake Phase" and go directly to "Minister's Designation Review" | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 8
9 | 4 | Delete this "Intake Phase" and go directly to "Minister's Designation Review" | SetPhasesStatus | Set thisPhase to INACTIVE | [{"phase_name":"Minister's Designation Intake","work_type_id": 2, "ea_act_id": 3, "is_active": false }] | 9
10 | 5 | Draft Minister's Designation Application is "incomplete" | SetEventsStatus | Set all "future" EVENTS in thisPhase to INACTIVE | {"all_future_events":false} | 10
11 | 5 | Draft Minister's Designation Application is "incomplete" | ChangePhaseEndEvent | Set thisEvent to PHASE END EVENT | {"phase_name":"Minister's Designation Application Review","work_type_id": 2, "ea_act_id": 3, "event_name": "Screening Decision for Minister's Designation Application"} | 11
12 | 5 | Draft Minister's Designation Application is "incomplete" | AddPhase | Set "Minister's Designation Application Development" to ACTIVE | [{"phase_name":"Minister's Designation Application Development","work_type_id": 2, "ea_act_id": 3, "new_name": "Minister's Designation Application Development", "legislated": false },{"phase_name":"Minister's Designation Application Review","work_type_id": 2, "ea_act_id": 3, "new_name": "Minister's Designation Application Review", "legislated": true }] | 12
14 | 5 | Draft Minister's Designation Application is "incomplete" | SetEventDate | Set "Minister's Designation Application Development ¦ Start of Minister's Designation Application Development (Submitter Time)" ANTICIPATED to thisEvent ACTUAL +1 | {"phase_name":"Minister's Designation Application Development","work_type_id": 2, "ea_act_id": 3, "event_name": "Start of Minister's Designation Application Development (Submitter Time)", "start_at": 0 } | 14
15 | 6 | Draft Minister's Designation Application is for an "eligible" project | NONE | No Actions Needed | {} | 15
16 | 7 | Project submitted exceeds RPR threshold(s) | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 16
17 | 7 | Project submitted exceeds RPR threshold(s) | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 17
18 | 7 | Project submitted exceeds RPR threshold(s) | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 18
19 | 7 | Project submitted exceeds RPR threshold(s) | CreateWork | createWork: "EAC Assessment" and link to thisWorkLinkedProject | {"work_type": 6} | 19
20 | 7 | Project submitted exceeds RPR threshold(s) | ChangePhaseEndEvent | Set thisEvent to PHASE END EVENT | {"phase_name":"Minister's Designation Application Review","work_type_id": 2, "ea_act_id": 3, "event_name": "Screening Decision for Minister's Designation Application"} | 20
21 | 8 | Project submitted exceeds RPR threshold(s) and is Substantially Started | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 21
22 | 8 | Project submitted exceeds RPR threshold(s) and is Substantially Started | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 22
23 | 8 | Project submitted exceeds RPR threshold(s) and is Substantially Started | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 23
24 | 8 | Project submitted exceeds RPR threshold(s) and is Substantially Started | ChangePhaseEndEvent | Set thisEvent to PHASE END EVENT | {"phase_name":"Minister's Designation Application Review","work_type_id": 2, "ea_act_id": 3, "event_name": "Screening Decision for Minister's Designation Application"} | 24
25 | 9 | Minister to make the Minister's Designation Decision | NONE | No Actions Needed | {} | 25
26 | 10 | CEAO is delegated to make the Minister's Designation Decision | SetWorkDecisionMaker | Set the workDecisionMaker to currentCEAO | {"position_id": 1} | 26
27 | 11 | Minister's Designation request is Terminated under s.39(d) of Act | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 27
28 | 11 | Minister's Designation request is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 28
29 | 11 | Minister's Designation request is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 29
30 | 11 | Minister's Designation request is Terminated under s.39(d) of Act | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 30
31 | 12 | Proponent Withdraws Project from the Minister's Designation Process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 31
32 | 12 | Proponent Withdraws Project from the Minister's Designation Process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 32
33 | 12 | Proponent Withdraws Project from the Minister's Designation Process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 33
34 | 12 | Proponent Withdraws Project from the Minister's Designation Process | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 34
35 | 13 | EAO's Viewpoint is POSITIVE | NONE | No Actions Needed | {} | 35
36 | 14 | EAO's Viewpoint is NEGATIVE | NONE | No Actions Needed | {} | 36
37 | 15 | Proponent Withdraws Project from the Minister's Designation Process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 37
38 | 15 | Proponent Withdraws Project from the Minister's Designation Process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 38
39 | 15 | Proponent Withdraws Project from the Minister's Designation Process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 39
40 | 15 | Proponent Withdraws Project from the Minister's Designation Process | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 40
41 | 16 | Proponent Withdraws Project from the Minister's Designation Process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 41
42 | 16 | Proponent Withdraws Project from the Minister's Designation Process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 42
43 | 16 | Proponent Withdraws Project from the Minister's Designation Process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 43
44 | 16 | Proponent Withdraws Project from the Minister's Designation Process | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 44
45 | 17 | Decision Maker Designates Project as Reviewable | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 45
46 | 17 | Decision Maker Designates Project as Reviewable | CreateWork | createWork: "EAC Assessment" and link to thisWorkLinkedProject | {"work_type": 6} | 46
47 | 18 | Decision Maker Declines to Designate Project as Reviewable | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 47
48 | 18 | Decision Maker Declines to Designate Project as Reviewable | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 48

## Lookups
WorkType | EA Act | Legislated |  | Event Type | Event Category | Visibility | ActionName | Event Position | Multiple Days | Action Name
Project Notification | EA Act (2018) | TRUE | Milestone | Generic | Milestone | MANDATORY | AllEventsDeactivated | START | TRUE | AddEvent
Minister's Designation | EA Act (2002) | FALSE | Milestone | Meeting | Calendar | SUGGESTED | AllEventsDeleted | INTERMEDIATE | FALSE | AddPhase
CEAO's Designation | EA Act (1996) |  | Milestone | Notification | Decision | OPTIONAL | CloseEverything | END |  | ChangePhaseEndEvent
EAC Assessment |  |  | Milestone | Order | Finance | HIDDEN | CloseWork |  |  | CreateWork
Exemption Request |  |  | Milestone | Referral | PCP |  | CompleteCurrentPhase |  |  | LockWorkStartDate
Dispute Resolution |  |  | Milestone | Report | Extension |  | CreateNewWork |  |  | SetEventDate
EAC/Order Amendment |  |  | Milestone | Request | Suspension |  | DisableWorkStartDate |  |  | SetEventsStatus
Document Review |  |  | Milestone | Submission |  |  | DuplicatePhase |  |  | SetFederalInvolvement
EAC Extension |  |  | Milestone | Other | [5 empty] | SetPhasesStatus
Substantial Start Decision |  |  | Milestone | Date Capture | [5 empty] | SetProjectState
EAC/Order Transfer |  |  | Extension | Time Limit Extension | [5 empty] | SetProjectStatus
EAC/Order Suspension |  |  | Extension | PCP Time Limit Extension | [5 empty] | SetWorkDecisionMaker
EAC/Order Cancellation |  |  | Extension | Interregnum | [5 empty] | SetWorkState
Other |  |  | Suspension | Time Limit Suspension | [5 empty] | NONE
|  |  | Suspension | Time Limit Resumption
|  |  | Decision | EAC Ministers
|  |  | Decision | Minister
|  |  | Decision | CEAO
|  |  | Decision | ADM
|  |  | Decision | EPD
|  |  | Decision | PAD (Lead)
|  |  | Decision | Reviewer
|  |  | Decision | Federal
|  |  | Decision | Other
|  |  | PCP | Comment Period
|  |  | PCP | Open House
|  |  | PCP | Virtual Information Session
|  |  | PCP | Other
|  |  | Calendar | Communications
|  |  | Calendar | Executive
|  |  | Calendar | Financial
|  |  | Calendar | Work
|  |  | Calendar | Other
|  |  | Finance | Capacity Funding
|  |  | Finance | Fee Order
|  |  | Finance | Penalties
|  |  | Finance | Administrative
|  |  | Finance | Other