## Instructions
Cell Colors
This color means that the cell has a picklist Validation constraint.
This color means that the cell has a formula and should not be changed. Change the vLookup source.
This color means the cell is open to user input
Order of Data Entry
You need to do the Phases before Events, Events before Outcomes, and Outcomes before Actions
The No Field and Row Deletion
The No (number field) of each sheet is the Validation list of the next sheet. For example the Events sheet has the heading PhaseNo which pulls from the Phases sheet No cells.
To maintain the Data Validation for all the sheets, make sure you DELETE the Entire Row for every unused row in the sheet you are working on. IE select the entire row(s) and right-click > Delete.

## Phases
No | Name | WorkType | EAAct | NumberOfDays | Legislated | Color | SortOrder
1 | Initial Contact | EAC/Order Amendment | EA Act (2018) | 60 | FALSE | #FFFFFF | 1
2 | Amendment Procedures | EAC/Order Amendment | EA Act (2018) | 60 | FALSE | #FFFFFF | 2
3 | Amendment Application Development (Proponent Time) | EAC/Order Amendment | EA Act (2018) | 365 | FALSE | #FFFFFF | 3
4 | Amendment Application Submission | EAC/Order Amendment | EA Act (2018) | 30 | FALSE | #FFFFFF | 4
5 | Amendment Application Review (Simple) | EAC/Order Amendment | EA Act (2018) | 60 | FALSE | #FFFFFF | 5
6 | Amendment Application Review (Typical) | EAC/Order Amendment | EA Act (2018) | 180 | FALSE | #FFFFFF | 6
7 | Amendment Application Review (Complex) | EAC/Order Amendment | EA Act (2018) | 240 | FALSE | #FFFFFF | 7
8 | Amendment Application Decision | EAC/Order Amendment | EA Act (2018) | 30 | FALSE | #FFFFFF | 8

## Events
No | Parent | PhaseNo | EventName | Phase | EventType | EventCategory | EventPosition | MultipleDays | StartAt | NumberOfDays | Mandatory | SortOrder
1 |  | 1 | Initial Contact with Holder | Initial Contact | Meeting | Milestone | START | FALSE | 0 | 0 | TRUE | 1
2 |  | 1 | Submission of Amendment Project Description | Initial Contact | Submission | Milestone | INTERMEDIATE | FALSE | 60 | 0 | TRUE | 2
3 |  | 1 | Additional Information Submission | Initial Contact | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 3
4 |  | 1 | Submission Withdrawn | Initial Contact | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 4
5 |  | 1 | Other | Initial Contact | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 5
6 |  | 1 | Last Day of Initial Contact (Date Capture) | Initial Contact | Date Capture | Milestone | END | FALSE | 60 | 0 | TRUE | 6
7 |  | 2 | Start of Assessment Procedures Development (Date Capture) | Amendment Procedures | Date Capture | Milestone | START | FALSE | 0 | 0 | TRUE | 7
8 |  | 2 | Additional Information Submission | Amendment Procedures | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 8
9 |  | 2 | Amendment Application Information Requirements | Amendment Procedures | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 9
10 |  | 2 | Notification of Potential PINs | Amendment Procedures | Notification | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 10
11 |  | 2 | PIN Notice Complete | Amendment Procedures | Generic | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 11
12 |  | 2 | TAC Established | Amendment Procedures | Generic | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 12
13 |  | 2 | CAC Established | Amendment Procedures | Generic | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 13
14 |  | 2 | Dispute Resolution Triggered | Amendment Procedures | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 14
15 | 14 | 2 | DR Triggered Announcement & Tweet | Amendment Procedures | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 15
16 | 14 | 2 | Dispute Resolution Milestone Bullet | Amendment Procedures | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 16
17 |  | 2 | Additional Comment Period | Amendment Procedures | Comment Period | PCP | INTERMEDIATE | TRUE | 0 | 30 | FALSE | 17
18 | 17 | 2 | PCP Coming Soon Announcement & Tweet | Amendment Procedures | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | FALSE | 18
19 | 17 | 2 | Additional PCP Milestone Bullet | Amendment Procedures | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | FALSE | 19
20 | 17 | 2 | PCP Now Open Announcement & Tweet | Amendment Procedures | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 20
21 | 17 | 2 | PCP Ending Soon Announcement & Tweet | Amendment Procedures | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | FALSE | 21
22 |  | 2 | Open House | Amendment Procedures | Open House | PCP | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 22
23 |  | 2 | Virtual Information Session | Amendment Procedures | Virtual Information Session | PCP | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 23
24 |  | 2 | Comment Period Time Limit Extension | Amendment Procedures | PCP Time Limit Extension | Extension | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 24
25 | 24 | 2 | PCP Extended Announcement & Tweet | Amendment Procedures | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 25
26 | 24 | 2 | PCP Extended Milestone Bullet | Amendment Procedures | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 26
27 |  | 2 | Amendment Request Terminated s.39(d) | Amendment Procedures | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 27
28 | 27 | 2 | Termination Announcement & Tweet | Amendment Procedures | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 28
29 | 27 | 2 | Amendment Request Terminated Milestone Bullet | Amendment Procedures | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 29
30 |  | 2 | Amendment Request Withdrawn | Amendment Procedures | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 30
31 | 30 | 2 | Withdrawal Announcement & Tweet | Amendment Procedures | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 31
32 | 30 | 2 | Amendment Request Withdrawn Milestone Bullet | Amendment Procedures | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 32
33 |  | 2 | Other | Amendment Procedures | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 33
34 |  | 2 | Assessment Procedures Posted | Amendment Procedures | Report | Milestone | END | FALSE | 60 | 0 | TRUE | 34
35 | 34 | 2 | Assessment Procedures Posted Announcement & Tweet | Amendment Procedures | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | TRUE | 35
36 | 34 | 2 | Assessment Procedures Posted Milestone Bullet | Amendment Procedures | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | TRUE | 36
37 |  | 3 | Start of Amendment Application Development (Proponent Time) (Date Capture Milestone) | Amendment Application Development (Proponent Time) | Date Capture | Milestone | START | FALSE | 0 | 0 | TRUE | 37
38 |  | 3 | Submission of "Draft" Amendment Application | Amendment Application Development (Proponent Time) | Submission | Milestone | INTERMEDIATE | FALSE | 355 | 0 | TRUE | 38
39 |  | 3 | Draft Amendment Application Receipt Milestone Bullet | Amendment Application Development (Proponent Time) | Generic | Milestone | INTERMEDIATE | FALSE | 360 | 0 | TRUE | 39
40 |  | 3 | REMINDER: Draft Amendment Application Receipt Milestone Bullet | Amendment Application Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | TRUE | 40
41 |  | 3 | "Draft" Amendment Application Initial Review | Amendment Application Development (Proponent Time) | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 365 | 0 | TRUE | 41
42 |  | 3 | Additional Information Submission | Amendment Application Development (Proponent Time) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 42
43 |  | 3 | Dispute Resolution Triggered | Amendment Application Development (Proponent Time) | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 43
44 | 43 | 3 | DR Triggered Announcement & Tweet | Amendment Application Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 44
45 | 43 | 3 | Dispute Resolution Milestone Bullet | Amendment Application Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 45
46 |  | 3 | Amendment Terminated s.39(d) | Amendment Application Development (Proponent Time) | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 46
47 | 46 | 3 | Termination Announcement & Tweet | Amendment Application Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 47
48 | 46 | 3 | Amendment Terminated Milestone Bullet | Amendment Application Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 48
49 |  | 3 | Amendment Withdrawn | Amendment Application Development (Proponent Time) | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 49
50 | 49 | 3 | Withdrawal Announcement & Tweet | Amendment Application Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 50
51 | 49 | 3 | Amendment Withdrawn Milestone Bullet | Amendment Application Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 51
52 |  | 3 | Other | Amendment Application Development (Proponent Time) | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 52
53 |  | 3 | Last Day of Amendment Application Development (Proponent Time) (Date Capture Milestone) | Amendment Application Development (Proponent Time) | Date Capture | Milestone | END | FALSE | 365 | 0 | TRUE | 53
54 |  | 4 | Amendment Application Received | Amendment Application Submission | Submission | Milestone | START | FALSE | 0 | 0 | TRUE | 54
55 | 54 | 4 | Amendment Application Announcement & Tweet | Amendment Application Submission | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | TRUE | 55
56 | 54 | 4 | Amendment Application Milestone Bullet | Amendment Application Submission | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | TRUE | 56
57 |  | 4 | Delegation of Decision | Amendment Application Submission | CEAO | Decision | INTERMEDIATE | FALSE | 25 | 0 | TRUE | 57
58 |  | 4 | Fee Order: Filing of Amendment Application | Amendment Application Submission | Fee Order | Finance | INTERMEDIATE | FALSE | 30 | 0 | TRUE | 58
59 | 58 | 4 | Filing the Amendment Application Fee Order | Amendment Application Submission | Financial | Calendar | INTERMEDIATE | FALSE | 0 | 0 | TRUE | 59
60 |  | 4 | Additional Information Submission | Amendment Application Submission | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 60
61 |  | 4 | Review of Supplementary Information | Amendment Application Submission | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 61
62 |  | 4 | Dispute Resolution Triggered | Amendment Application Submission | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 62
63 | 62 | 4 | DR Triggered Announcement & Tweet | Amendment Application Submission | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 63
64 | 62 | 4 | Dispute Resolution Milestone Bullet | Amendment Application Submission | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 64
65 |  | 4 | Amendment Terminated s.39(d) | Amendment Application Submission | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 65
66 | 65 | 4 | Termination Announcement & Tweet | Amendment Application Submission | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 66
67 | 65 | 4 | Amendment Terminated Milestone Bullet | Amendment Application Submission | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 67
68 |  | 4 | Amendment Withdrawn | Amendment Application Submission | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 68
69 | 68 | 4 | Withdrawal Announcement & Tweet | Amendment Application Submission | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 69
70 | 68 | 4 | Amendment Withdrawn Milestone Bullet | Amendment Application Submission | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 70
71 |  | 4 | Other | Amendment Application Submission | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 71
72 |  | 4 | Amendment Complexity/Fee Decision | Amendment Application Submission | EPD | Decision | END | FALSE | 30 | 0 | TRUE | 72
73 |  | 5 | Start of Amendment Application Review (Simple) (Date Capture) | Amendment Application Review (Simple) | Date Capture | Milestone | START | FALSE | 0 | 0 | TRUE | 73
74 |  | 5 | Final Amendment Report & Recommendation | Amendment Application Review (Simple) | Report | Milestone | INTERMEDIATE | FALSE | 50 | 0 | TRUE | 74
75 |  | 5 | Additional Information Submission | Amendment Application Review (Simple) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 75
76 |  | 5 | Review of Supplementary Information | Amendment Application Review (Simple) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 76
77 |  | 5 | Dispute Resolution Triggered | Amendment Application Review (Simple) | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 77
78 | 77 | 5 | DR Triggered Announcement & Tweet | Amendment Application Review (Simple) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 78
79 | 77 | 5 | Dispute Resolution Milestone Bullet | Amendment Application Review (Simple) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 79
80 |  | 5 | Additional Comment Period | Amendment Application Review (Simple) | Comment Period | PCP | INTERMEDIATE | TRUE | 0 | 30 | FALSE | 80
81 | 80 | 5 | PCP Coming Soon Announcement & Tweet | Amendment Application Review (Simple) | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | FALSE | 81
82 | 80 | 5 | Additional PCP Milestone Bullet | Amendment Application Review (Simple) | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | FALSE | 82
83 | 80 | 5 | PCP Now Open Announcement & Tweet | Amendment Application Review (Simple) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 83
84 | 80 | 5 | PCP Ending Soon Announcement & Tweet | Amendment Application Review (Simple) | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | FALSE | 84
85 |  | 5 | Open House | Amendment Application Review (Simple) | Open House | PCP | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 85
86 |  | 5 | Virtual Information Session | Amendment Application Review (Simple) | Virtual Information Session | PCP | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 86
87 |  | 5 | Comment Period Time Limit Extension | Amendment Application Review (Simple) | PCP Time Limit Extension | Extension | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 87
88 | 87 | 5 | PCP Extended Announcement & Tweet | Amendment Application Review (Simple) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 88
89 | 87 | 5 | PCP Extended Milestone Bullet | Amendment Application Review (Simple) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 89
90 |  | 5 | Amendment Terminated s.39(d) | Amendment Application Review (Simple) | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 90
91 | 90 | 5 | Termination Announcement & Tweet | Amendment Application Review (Simple) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 91
92 | 90 | 5 | Amendment Terminated Milestone Bullet | Amendment Application Review (Simple) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 92
93 |  | 5 | Amendment Withdrawn | Amendment Application Review (Simple) | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 93
94 | 93 | 5 | Withdrawal Announcement & Tweet | Amendment Application Review (Simple) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 94
95 | 93 | 5 | Amendment Withdrawn Milestone Bullet | Amendment Application Review (Simple) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 95
96 |  | 5 | Other | Amendment Application Review (Simple) | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 96
97 |  | 5 | Amendment Report Referred to Decision Maker | Amendment Application Review (Simple) | Referral | Milestone | END | FALSE | 60 | 0 | TRUE | 97
98 |  | 6 | Start of Amendment Application Review (Typical) (Date Capture) | Amendment Application Review (Typical) | Date Capture | Milestone | START | FALSE | 0 | 0 | TRUE | 98
99 |  | 6 | Draft Amendment Assessment Report & Recommendation | Amendment Application Review (Typical) | Report | Milestone | INTERMEDIATE | FALSE | 90 | 0 | TRUE | 99
100 |  | 6 | Final Amendment Report & Recommendation | Amendment Application Review (Typical) | Report | Milestone | INTERMEDIATE | FALSE | 150 | 0 | TRUE | 100
101 |  | 6 | Additional Information Submission | Amendment Application Review (Typical) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 101
102 |  | 6 | Review of Supplementary Information | Amendment Application Review (Typical) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 102
103 |  | 6 | Dispute Resolution Triggered | Amendment Application Review (Typical) | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 103
104 | 103 | 6 | DR Triggered Announcement & Tweet | Amendment Application Review (Typical) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 104
105 | 103 | 6 | Dispute Resolution Milestone Bullet | Amendment Application Review (Typical) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 105
106 |  | 6 | Additional Comment Period | Amendment Application Review (Typical) | Comment Period | PCP | INTERMEDIATE | TRUE | 0 | 30 | FALSE | 106
107 | 106 | 6 | PCP Coming Soon Announcement & Tweet | Amendment Application Review (Typical) | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | FALSE | 107
108 | 106 | 6 | Additional PCP Milestone Bullet | Amendment Application Review (Typical) | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | FALSE | 108
109 | 106 | 6 | PCP Now Open Announcement & Tweet | Amendment Application Review (Typical) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 109
110 | 106 | 6 | PCP Ending Soon Announcement & Tweet | Amendment Application Review (Typical) | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | FALSE | 110
111 |  | 6 | Open House | Amendment Application Review (Typical) | Open House | PCP | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 111
112 |  | 6 | Virtual Information Session | Amendment Application Review (Typical) | Virtual Information Session | PCP | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 112
113 |  | 6 | Comment Period Time Limit Extension | Amendment Application Review (Typical) | PCP Time Limit Extension | Extension | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 113
114 | 113 | 6 | PCP Extended Announcement & Tweet | Amendment Application Review (Typical) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 114
115 | 113 | 6 | PCP Extended Milestone Bullet | Amendment Application Review (Typical) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 115
116 |  | 6 | Amendment Terminated s.39(d) | Amendment Application Review (Typical) | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 116
117 | 116 | 6 | Termination Announcement & Tweet | Amendment Application Review (Typical) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 117
118 | 116 | 6 | Amendment Terminated Milestone Bullet | Amendment Application Review (Typical) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 118
119 |  | 6 | Amendment Withdrawn | Amendment Application Review (Typical) | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 119
120 | 119 | 6 | Withdrawal Announcement & Tweet | Amendment Application Review (Typical) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 120
121 | 119 | 6 | Amendment Withdrawn Milestone Bullet | Amendment Application Review (Typical) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 121
122 |  | 6 | Other | Amendment Application Review (Typical) | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 122
123 |  | 6 | Amendment Report Referred to Decision Maker | Amendment Application Review (Typical) | Referral | Milestone | END | FALSE | 180 | 0 | TRUE | 123
124 |  | 7 | Start of Amendment Application Review (Complex) (Date Capture) | Amendment Application Review (Complex) | Date Capture | Milestone | START | FALSE | 0 | 0 | TRUE | 124
125 |  | 7 | Draft Amendment Assessment Report & Recommendation | Amendment Application Review (Complex) | Report | Milestone | INTERMEDIATE | FALSE | 150 | 0 | TRUE | 125
126 |  | 7 | Final Amendment Report & Recommendation | Amendment Application Review (Complex) | Report | Milestone | INTERMEDIATE | FALSE | 210 | 0 | TRUE | 126
127 |  | 7 | Additional Information Submission | Amendment Application Review (Complex) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 127
128 |  | 7 | Review of Supplementary Information | Amendment Application Review (Complex) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 128
129 |  | 7 | Dispute Resolution Triggered | Amendment Application Review (Complex) | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 129
130 | 129 | 7 | DR Triggered Announcement & Tweet | Amendment Application Review (Complex) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 130
131 | 129 | 7 | Dispute Resolution Milestone Bullet | Amendment Application Review (Complex) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 131
132 |  | 7 | Additional Comment Period | Amendment Application Review (Complex) | Comment Period | PCP | INTERMEDIATE | TRUE | 0 | 30 | FALSE | 132
133 | 132 | 7 | PCP Coming Soon Announcement & Tweet | Amendment Application Review (Complex) | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | FALSE | 133
134 | 132 | 7 | Additional PCP Milestone Bullet | Amendment Application Review (Complex) | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | FALSE | 134
135 | 132 | 7 | PCP Now Open Announcement & Tweet | Amendment Application Review (Complex) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 135
136 | 132 | 7 | PCP Ending Soon Announcement & Tweet | Amendment Application Review (Complex) | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | FALSE | 136
137 |  | 7 | Open House | Amendment Application Review (Complex) | Open House | PCP | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 137
138 |  | 7 | Virtual Information Session | Amendment Application Review (Complex) | Virtual Information Session | PCP | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 138
139 |  | 7 | Comment Period Time Limit Extension | Amendment Application Review (Complex) | PCP Time Limit Extension | Extension | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 139
140 | 139 | 7 | PCP Extended Announcement & Tweet | Amendment Application Review (Complex) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 140
141 | 139 | 7 | PCP Extended Milestone Bullet | Amendment Application Review (Complex) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 141
142 |  | 7 | Amendment Terminated s.39(d) | Amendment Application Review (Complex) | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 142
143 | 142 | 7 | Termination Announcement & Tweet | Amendment Application Review (Complex) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 143
144 | 142 | 7 | Amendment Terminated Milestone Bullet | Amendment Application Review (Complex) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 144
145 |  | 7 | Amendment Withdrawn | Amendment Application Review (Complex) | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 145
146 | 145 | 7 | Withdrawal Announcement & Tweet | Amendment Application Review (Complex) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 146
147 | 145 | 7 | Amendment Withdrawn Milestone Bullet | Amendment Application Review (Complex) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 147
148 |  | 7 | Other | Amendment Application Review (Complex) | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 148
149 |  | 7 | Amendment Report Referred to Decision Maker | Amendment Application Review (Complex) | Referral | Milestone | END | FALSE | 240 | 0 | TRUE | 149
150 |  | 8 | Referral Package Received by Decision Maker | Amendment Application Decision | Generic | Milestone | START | FALSE | 0 | 0 | TRUE | 150
151 |  | 8 | Draft Amendment Decision Milestone Bullets | Amendment Application Decision | Generic | Milestone | INTERMEDIATE | FALSE | 25 | 0 | TRUE | 151
152 | 151 | 8 | REMINDER: Draft Amendment Decision Milestone Bullets Due | Amendment Application Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | TRUE | 152
153 |  | 8 | Additional Information Submission | Amendment Application Decision | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 153
154 |  | 8 | Amendment Withdrawn | Amendment Application Decision | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 154
155 | 154 | 8 | Withdrawal Announcement & Tweet | Amendment Application Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 155
156 | 154 | 8 | Amendment Withdrawn Milestone Bullet | Amendment Application Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 156
157 |  | 8 | Other | Amendment Application Decision | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | FALSE | 157
158 |  | 8 | Amendment Decision | Amendment Application Decision | CEAO | Decision | END | FALSE | 30 | 0 | TRUE | 158
159 | 158 | 8 | Amendment Decision Announcement & Tweet | Amendment Application Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | TRUE | 159
160 | 158 | 8 | Amendment Decision Milestone Bullet (only if Decision is not: Minister) | Amendment Application Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | TRUE | 160

## Outcomes
No | TemplateNo | TemplateName | OutcomeName | SortOrder
1 | 4 | Submission Withdrawn | Holder withdraws Submission from the Amendment process | 1
2 | 14 | Dispute Resolution Triggered | Dispute Resolution is started | 2
3 | 27 | Amendment Request Terminated s.39(d) | Amendment Request is Terminated under s.39(d) of Act | 3
4 | 30 | Amendment Request Withdrawn | Holder withdraws Amendment Request from EA process | 4
5 | 34 | Assessment Procedures Posted | End of Amendment Procedures PHASE, start of Amendment Application Development (Proponent Time) PHASE | 5
6 | 41 | "Draft" Amendment Application Initial Review | Initial Review of "Draft" Amendment Application is POSITIVE | 6
7 | 41 | "Draft" Amendment Application Initial Review | Initial Review of "Draft" Amendment Application is NEGATIVE | 7
8 | 43 | Dispute Resolution Triggered | Dispute Resolution is started | 8
9 | 46 | Amendment Terminated s.39(d) | Amendment is Terminated under s.39(d) of Act | 9
10 | 49 | Amendment Withdrawn | Holder withdraws Application from Amendment process | 10
11 | 54 | Amendment Application Received | Starts the "clock" for Amendment | 11
12 | 57 | Delegation of Decision | ADM, EA Operations is delegated to make the final Amendment Decision | 12
13 | 57 | Delegation of Decision | CEAO is delegated to make the final Amendment Decision | 13
14 | 57 | Delegation of Decision | Minister is delegated to make the final Amendment Decision | 14
15 | 62 | Dispute Resolution Triggered | Dispute Resolution is started | 15
16 | 65 | Amendment Terminated s.39(d) | Amendment is Terminated under s.39(d) of Act | 16
17 | 68 | Amendment Withdrawn | Holder withdraws Application from Amendment process | 17
18 | 72 | Amendment Complexity/Fee Decision | Amendment is determined to be "Simple" | 18
19 | 72 | Amendment Complexity/Fee Decision | Amendment is determined to be "Typical" | 19
20 | 72 | Amendment Complexity/Fee Decision | Amendment is determined to be "Complex" | 20
21 | 77 | Dispute Resolution Triggered | Dispute Resolution is started | 21
22 | 90 | Amendment Terminated s.39(d) | Amendment is Terminated under s.39(d) of Act | 22
23 | 93 | Amendment Withdrawn | Holder withdraws Application from Amendment process | 23
24 | 103 | Dispute Resolution Triggered | Dispute Resolution is started | 24
25 | 116 | Amendment Terminated s.39(d) | Amendment is Terminated under s.39(d) of Act | 25
26 | 119 | Amendment Withdrawn | Holder withdraws Application from Amendment process | 26
27 | 129 | Dispute Resolution Triggered | Dispute Resolution is started | 27
28 | 142 | Amendment Terminated s.39(d) | Amendment is Terminated under s.39(d) of Act | 28
29 | 145 | Amendment Withdrawn | Holder withdraws Application from Amendment process | 29
30 | 154 | Amendment Withdrawn | Holder withdraws Application from Amendment process | 30
31 | 158 | Amendment Decision | Decision Maker Amends the EAC/Exemption Order | 31
32 | 158 | Amendment Decision | Decision Maker Refuses to Amend the EAC/Exemption Order | 32

## Actions
No | OutcomeNo | OutcomeName | ActionName | ActionDescription | AdditionalParams | SortOrder
1 | 1 | Holder withdraws Submission from the Amendment process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {} | 1
2 | 1 | Holder withdraws Submission from the Amendment process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {} | 2
3 | 1 | Holder withdraws Submission from the Amendment process | SetWorkState | Set workState to WITHDRAWN | {} | 3
4 | 2 | Dispute Resolution is started | CreateWork | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {} | 4
5 | 3 | Amendment Request is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {} | 5
6 | 3 | Amendment Request is Terminated under s.39(d) of Act | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {} | 6
7 | 3 | Amendment Request is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {} | 7
8 | 4 | Holder withdraws Amendment Request from EA process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {} | 8
9 | 4 | Holder withdraws Amendment Request from EA process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {} | 9
10 | 4 | Holder withdraws Amendment Request from EA process | SetWorkState | Set workState to WITHDRAWN | {} | 10
11 | 5 | End of Amendment Procedures PHASE, start of Amendment Application Development (Proponent Time) PHASE | SetEventDate | Sets ACTUAL of "Amendment Application Development (Proponent Time) ¦ Start of Amendment Application Development (Proponent Time) (Date Capture Milestone)" to thisEventACTUAL +1 | {} | 11
12 | 6 | Initial Review of "Draft" Amendment Application is POSITIVE | SetEventDate | Set ANTICIPATED of "Amendment Application Submission ¦ Amendment Application Received" to thisEventACTUAL +1 | {} | 12
13 | 7 | Initial Review of "Draft" Amendment Application is NEGATIVE | AddEvent | Add a copy of "Amendment Application Development (Proponent Time) ¦ Submission of "Draft" Amendment Application" to thisPhase at thisEventACTUAL +28 | {} | 13
14 | 7 | Initial Review of "Draft" Amendment Application is NEGATIVE | AddEvent | Add a copy of "Amendment Application Development (Proponent Time) ¦ "Draft" Amendment Application Initial Review" to thisPhase at thisEventACTUAL +38 | {} | 14
15 | 8 | Dispute Resolution is started | CreateWork | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {} | 15
16 | 9 | Amendment is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {} | 16
17 | 9 | Amendment is Terminated under s.39(d) of Act | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {} | 17
18 | 9 | Amendment is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {} | 18
19 | 10 | Holder withdraws Application from Amendment process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {} | 19
20 | 10 | Holder withdraws Application from Amendment process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {} | 20
21 | 10 | Holder withdraws Application from Amendment process | SetWorkState | Set workState to WITHDRAWN | {} | 21
22 | 11 | Starts the "clock" for Amendment | LockWorkStartDate | Set the workStartDate to thisEventACTUAL | {} | 22
23 | 12 | ADM, EA Operations is delegated to make the final Amendment Decision | SetWorkDecisionMaker | Set the workDecisionMaker to currentADMoperations | {} | 23
24 | 13 | CEAO is delegated to make the final Amendment Decision | SetWorkDecisionMaker | Set the workDecisionMaker to currentCEAO | {} | 24
25 | 14 | Minister is delegated to make the final Amendment Decision | SetWorkDecisionMaker | Set the workDecisionMaker to currentMinisterEnvironment | {} | 25
26 | 15 | Dispute Resolution is started | CreateWork | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {} | 26
27 | 16 | Amendment is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {} | 27
28 | 16 | Amendment is Terminated under s.39(d) of Act | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {} | 28
29 | 16 | Amendment is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {} | 29
30 | 17 | Holder withdraws Application from Amendment process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {} | 30
31 | 17 | Holder withdraws Application from Amendment process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {} | 31
32 | 17 | Holder withdraws Application from Amendment process | SetWorkState | Set workState to WITHDRAWN | {} | 32
33 | 18 | Amendment is determined to be "Simple" | SetPhasesStatus | Set "Amendment Application Review (Typical)" PHASE to INACTIVE | {} | 33
34 | 18 | Amendment is determined to be "Simple" | SetPhasesStatus | Set "Amendment Application Review (Simple)" PHASE to ACTIVE | {} | 34
35 | 18 | Amendment is determined to be "Simple" | SetEventDate | Set "Amendment Application Review (Simple) ¦ Start of Amendment Application Review (Simple) (Date Capture)" to thisEvent ACTUAL +1 | {} | 35
36 | 19 | Amendment is determined to be "Typical" | SetEventDate | Set "Amendment Application Review (Typical) ¦ Start of Amendment Application Review (Typical) (Date Capture)" to thisEvent ACTUAL +1 | {} | 36
37 | 20 | Amendment is determined to be "Complex" | SetPhasesStatus | Set "Amendment Application Review (Typical)" PHASE to INACTIVE | {} | 37
38 | 20 | Amendment is determined to be "Complex" | SetPhasesStatus | Set "Amendment Application Review (Complex)" PHASE to ACTIVE | {} | 38
39 | 20 | Amendment is determined to be "Complex" | SetEventDate | Set "Amendment Application Review (Complex) ¦ Start of Amendment Application Review (Complex) (Date Capture)" to thisEvent ACTUAL +1 | {} | 39
40 | 21 | Dispute Resolution is started | CreateWork | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {} | 40
41 | 22 | Amendment is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {} | 41
42 | 22 | Amendment is Terminated under s.39(d) of Act | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {} | 42
43 | 22 | Amendment is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {} | 43
44 | 23 | Holder withdraws Application from Amendment process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {} | 44
45 | 23 | Holder withdraws Application from Amendment process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {} | 45
46 | 23 | Holder withdraws Application from Amendment process | SetWorkState | Set workState to WITHDRAWN | {} | 46
47 | 24 | Dispute Resolution is started | CreateWork | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {} | 47
48 | 25 | Amendment is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {} | 48
49 | 25 | Amendment is Terminated under s.39(d) of Act | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {} | 49
50 | 25 | Amendment is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {} | 50
51 | 26 | Holder withdraws Application from Amendment process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {} | 51
52 | 26 | Holder withdraws Application from Amendment process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {} | 52
53 | 26 | Holder withdraws Application from Amendment process | SetWorkState | Set workState to WITHDRAWN | {} | 53
54 | 27 | Dispute Resolution is started | CreateWork | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {} | 54
55 | 28 | Amendment is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {} | 55
56 | 28 | Amendment is Terminated under s.39(d) of Act | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {} | 56
57 | 28 | Amendment is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {} | 57
58 | 29 | Holder withdraws Application from Amendment process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {} | 58
59 | 29 | Holder withdraws Application from Amendment process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {} | 59
60 | 29 | Holder withdraws Application from Amendment process | SetWorkState | Set workState to WITHDRAWN | {} | 60
61 | 30 | Holder withdraws Application from Amendment process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {} | 61
62 | 30 | Holder withdraws Application from Amendment process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {} | 62
63 | 30 | Holder withdraws Application from Amendment process | SetWorkState | Set workState to WITHDRAWN | {} | 63
64 | 31 | Decision Maker Amends the EAC/Exemption Order | SetWorkState | Set workState to COMPLETE | {} | 64
65 | 32 | Decision Maker Refuses to Amend the EAC/Exemption Order | SetWorkState | Set workState to COMPLETE | {} | 65

## Lookups
WorkType | EA Act | Legislated |  | Event Type | Event Category | Mandatory | ActionName | Event Position | Multiple Days
Project Notification | EA Act (2018) | TRUE | Milestone | Generic | Milestone | TRUE | AllEventsDeactivated | START | TRUE
Minister's Designation | EA Act (2002) | FALSE | Milestone | Meeting | Calendar | FALSE | AllEventsDeleted | INTERMEDIATE | FALSE
CEAO's Designation | EA Act (1996) |  | Milestone | Notification | Decision |  | CloseEverything | END
EAC Assessment |  |  | Milestone | Order | Finance |  | CloseWork
Exemption Request |  |  | Milestone | Referral | PCP |  | CompleteCurrentPhase
Dispute Resolution |  |  | Milestone | Report | Extension |  | CreateNewWork
EAC/Order Amendment |  |  | Milestone | Request | Suspension |  | DisableWorkStartDate
Document Review |  |  | Milestone | Submission |  |  | DuplicatePhase
EAC Extension |  |  | Milestone | Other
Substantial Start Decision |  |  | Milestone | Date Capture
EAC/Order Transfer |  |  | Extension | Time Limit Extension
EAC/Order Suspension |  |  | Extension | PCP Time Limit Extension
EAC/Order Cancellation |  |  | Suspension | Time Limit Suspension
Other |  |  | Suspension | Time Limit Resumption
|  |  | Decision | EAC Ministers
|  |  | Decision | Minister
|  |  | Decision | CEAO
|  |  | Decision | ADM
|  |  | Decision | EPD
|  |  | Decision | PAD (Lead)
|  |  | Decision | Reviewer
|  |  | Decision | Federal
|  |  | Decision | Other
|  |  | PCP | Comment Period
|  |  | PCP | Open House
|  |  | PCP | Virtual Information Session
|  |  | PCP | Other
|  |  | Calendar | Communications
|  |  | Calendar | Executive
|  |  | Calendar | Financial
|  |  | Calendar | Work
|  |  | Calendar | Other
|  |  | Finance | Capacity Funding
|  |  | Finance | Fee Order
|  |  | Finance | Penalties
|  |  | Finance | Administrative
|  |  | Finance | Other