## Phases
No | Name | WorkType | EAAct | NumberOfDays | Legislated | Color | SortOrder
1 | Notification Review | Project Notification | EA Act (2018) | 50 | TRUE | #ffffff | 1
2 | Notification Decision | Project Notification | EA Act (2018) | 10 | TRUE | #ffffff | 2

## Events
No | Parent | PhaseNo | EventName | Phase | EventType | EventCategory | StartAt | NumberOfDays | Mandatory | SortOrder
1 |  | 1 | Project Notification Submission | Notification Review | Submission | Milestone | 0 | 0 | TRUE | 1
2 | 4 | 1 | PCP Coming Soon Announcement & Tweet | Notification Review | Communications | Calendar | -7 | 0 | TRUE | 2
3 | 4 | 1 | PCP Coming Soon Milestone Bullet | Notification Review | Executive | Calendar | -7 | 0 | TRUE | 3
4 |  | 1 | Comment Period | Notification Review | Comment Period | PCP | 14 | 30 | TRUE | 4
5 | 4 | 1 | PCP Now Open Announcement & Tweet | Notification Review | Communications | Calendar | 0 | 0 | TRUE | 5
6 | 4 | 1 | PCP Ending Soon Announcement & Tweet | Notification Review | Communications | Calendar | number_of_days-2 | 0 | TRUE | 6
7 |  | 1 | Additional Information Submission | Notification Review | Submission | Milestone | 0 | 0 | FALSE | 7
8 |  | 1 | GHG Threshold Information Note | Notification Review | Report | Milestone | 0 | 0 | FALSE | 8
9 | 8 | 1 | REMINDER: GHG Minister's Information Note |  | Executive | Calendar | 0 | 0 | FALSE | 9
10 | 12 | 1 | PCP Coming Soon Announcement & Tweet | Notification Review | Communications | Calendar | -7 | 0 | FALSE | 10
11 | 12 | 1 | Additional PCP Milestone Bullet | Notification Review | Executive | Calendar | -7 | 0 | FALSE | 11
12 |  | 1 | Additional Comment Period | Notification Review | Comment Period | PCP | 0 | 0 | FALSE | 12
13 | 12 | 1 | PCP Now Open Announcement & Tweet | Notification Review | Communications | Calendar | 0 | 0 | FALSE | 13
14 | 12 | 1 | PCP Ending Soon Announcement & Tweet | Notification Review | Communications | Calendar | number_of_days-2 | 0 | FALSE | 14
15 |  | 1 | Open House | Notification Review | Open House | PCP | 0 | 0 | FALSE | 15
16 |  | 1 | Virtual Information Session | Notification Review | Virtual Information Session | PCP | 0 | 0 | FALSE | 16
17 |  | 1 | Comment Period Time Limit Extension | Notification Review | PCP Time Limit Extension | Extension | 0 | 0 | FALSE | 17
18 | 17 | 1 | PCP Extended Announcement & Tweet | Notification Review | Communications | Calendar | 0 | 0 | FALSE | 18
19 | 17 | 1 | PCP Extended Milestone Bullet | Notification Review | Executive | Calendar | 0 | 0 | FALSE | 19
20 |  | 1 | s.38 Extension of Time Limit | Notification Review | Time Limit Extension | Extension | 0 | 0 | FALSE | 20
21 | 20 | 1 | Extension Announcement & Tweet | Notification Review | Communications | Calendar | 0 | 0 | FALSE | 21
22 | 20 | 1 | Time Limit Extended Milestone Bullet | Notification Review | Executive | Calendar | 0 | 0 | FALSE | 22
23 |  | 1 | Project Notification Terminated s.39(d) | Notification Review | CEAO | Decision | 0 | 0 | FALSE | 23
24 | 23 | 1 | Termination Announcement & Tweet | Notification Review | Communications | Calendar | 0 | 0 | FALSE | 24
25 | 23 | 1 | Project Notification Terminated Milestone Bullet | Notification Review | Executive | Calendar | 0 | 0 | FALSE | 25
26 |  | 1 | Project Withdrawn | Notification Review | EPD | Decision | 0 | 0 | FALSE | 26
27 | 26 | 1 | Withdrawal Announcement & Tweet | Notification Review | Communications | Calendar | 0 | 0 | FALSE | 27
28 | 26 | 1 | Project Withdrawn Milestone Bullet | Notification Review | Executive | Calendar | 0 | 0 | FALSE | 28
29 |  | 1 | Other | Notification Review | Other | Milestone | 0 | 0 | FALSE | 29
30 |  | 1 | Report Referred to Decision Maker | Notification Review | Report | Milestone | 50 | 0 | TRUE | 30
31 |  | 2 | Draft Notification Decision Milestone Bullets | Notification Decision | Generic | Milestone | 5 | 0 | TRUE | 31
32 | 31 | 2 | REMINDER: Draft Notification Decision Milestone Bullets Due | Notification Decision | Executive | Calendar | 0 | 0 | TRUE | 32
33 |  | 2 | Additional Information Submission | Notification Decision | Submission | Milestone | 0 | 0 | FALSE | 33
34 |  | 2 | s.38 Extension of Time Limit | Notification Decision | Time Limit Extension | Extension | 0 | 0 | FALSE | 34
35 | 34 | 2 | Extension Announcement & Tweet | Notification Decision | Communications | Calendar | 0 | 0 | FALSE | 35
36 | 34 | 2 | Time Limit Extended Milestone Bullet | Notification Decision | Executive | Calendar | 0 | 0 | FALSE | 36
37 |  | 2 | Project Notification Terminated s.39(d) | Notification Decision | CEAO | Decision | 0 | 0 | FALSE | 37
38 | 37 | 2 | Termination Announcement & Tweet | Notification Decision | Communications | Calendar | 0 | 0 | FALSE | 38
39 | 37 | 2 | Project Notification Terminated Milestone Bullet | Notification Decision | Executive | Calendar | 0 | 0 | FALSE | 39
40 |  | 2 | Project Withdrawn | Notification Decision | EPD | Decision | 0 | 0 | FALSE | 40
41 | 40 | 2 | Withdrawal Announcement & Tweet | Notification Decision | Communications | Calendar | 0 | 0 | FALSE | 41
42 | 40 | 2 | Project Withdrawn Milestone Bullet | Notification Decision | Executive | Calendar | 0 | 0 | FALSE | 42
43 |  | 2 | Other | Notification Decision | Other | Milestone | 0 | 0 | FALSE | 43
44 |  | 2 | Decision: Project Notification | Notification Decision | CEAO | Decision | 10 | 0 | TRUE | 44
45 | 44 | 2 | Notification Decision Announcement & Tweet | Notification Decision | Communications | Calendar | 0 | 0 | TRUE | 45
46 | 44 | 2 | Notification Decision Milestone Bullet | Notification Decision | Executive | Calendar | 0 | 0 | TRUE | 46

## Outcomes
No | TemplateNo | TemplateName | OutcomeName | SortOrder
1 | 30 | 30 | Notification Review Phase Ends | 1
2 | 23 | 23 | Assessment is Terminated under s.39(d) of Act | 2
3 | 26 | 26 | Proponent withdraws Project from EA process | 3
4 | 44 | 44 | No Further Review Required | 4
5 | 44 | 44 | More Information Needed | 5
6 | 44 | 44 | Project Referred to Minister (s.11) | 6
7 | 37 | 37 | Assessment is Terminated under s.39(d) of Act | 7
8 | 40 | 40 | Proponent withdraws Project from EA process | 8

## Actions
No | OutcomeNo | OutcomeName | ActionName | ActionDescription | AdditionalParams | SortOrder
1 | 1 | 1 | CompleteCurrentPhase | Setting actual date closes the current phase and set the start of the next phase | {} | 1
2 | 1 | 1 | DisableWorkStartDate | Set the startdate of the work and lock further date changes | {} | 2
3 | 2 | 2 | CloseEverything | All Events are "Closed" or DELETED, Work is "Closed", Project is "Closed" | {} | 3
4 | 3 | 3 | CloseEverything | All Events are "Closed" or DELETED, Work is "Closed", Project is "Closed" | {} | 4
5 | 4 | 4 | CloseEverything | All Events are "Closed" or DELETED, Work is "Closed", Project is "Closed" | {} | 5
6 | 5 | 5 | DuplicatePhase | Duplicate the given phase | {"phase_name":"Notification Review","work_type_id": 1, "ea_act_id": 3 } | 6
7 | 5 | 5 | DuplicatePhase | Duplicate the given phase | {"phase_name":"Notification Decision","work_type_id": 1, "ea_act_id": 3 } | 7
8 | 6 | 6 | DeactivateAllEvents | Set is_active flag to false of all events from the point of action execution | {} | 8
9 | 6 | 6 | DeleteAllEvents | Set is_deleted flag to true of all events from the point of action execution | {} | 9
10 | 6 | 6 | CloseWork | Closes the work | {} | 10
11 | 6 | 6 | CreateNewWork | Create a new work of the given type from the existing work information | {"work_type_id": 2} | 11
12 | 7 | 7 | CloseEverything | All Events are "Closed" or DELETED, Work is "Closed", Project is "Closed" | {} | 12
13 | 8 | 8 | CloseEverything | All Events are "Closed" or DELETED, Work is "Closed", Project is "Closed" | {} | 13