## Phases
No | Name | WorkType | EAAct | NumberOfDays | Legislated | Color | Visibility | SortOrder
1 | Pre-EA (Exemption Request) | Exemption Order | EA Act (2018) | 90 | FALSE | #3eb1d7 | REGULAR | 1
2 | Early Engagement | Exemption Order | EA Act (2018) | 90 | TRUE | #54858d | REGULAR | 2
3 | DPD Development (Proponent Time) | Exemption Order | EA Act (2018) | 365 | FALSE | #6d7274 | REGULAR | 3
4 | Readiness Decision | Exemption Order | EA Act (2018) | 60 | FALSE | #da6d65 | REGULAR | 4
5 | Exemption Decision | Exemption Order | EA Act (2018) | 30 | FALSE | #FFFFFF | REGULAR | 5
6 | Further Readiness Decision | Exemption Order | EA Act (2018) | 60 | FALSE | #da6d65 | HIDDEN | 6

## Events
No | Parent | PhaseNo | EventName | Phase | EventType | EventCategory | EventPosition | MultipleDays | StartAt | NumberOfDays | Visibility | SortOrder
1 |  | 1 | Start of Pre-EA Phase (e.g. Initial Meeting, Date Confirmation, or IPD) | Pre-EA (Exemption Request) | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 1
2 |  | 1 | Project Presentation Meeting | Pre-EA (Exemption Request) | Meeting | Milestone | INTERMEDIATE | FALSE | 28 | 0 | SUGGESTED | 2
3 |  | 1 | Submit Estimate for Capacity Funding | Pre-EA (Exemption Request) | Capacity Funding | Finance | INTERMEDIATE | FALSE | 60 | 0 | SUGGESTED | 3
4 | 3 | 1 | Capacity Funding Estimate Due | Pre-EA (Exemption Request) | Financial | Calendar | INTERMEDIATE | FALSE | 0 | 0 | SUGGESTED | 4
5 |  | 1 | Submission of IPD/EP for CEAO Approval | Pre-EA (Exemption Request) | Submission | Milestone | INTERMEDIATE | FALSE | 80 | 0 | MANDATORY | 5
6 |  | 1 | Create IPD Approval Milestone Bullet | Pre-EA (Exemption Request) | Generic | Milestone | INTERMEDIATE | FALSE | 85 | 0 | SUGGESTED | 6
7 | 6 | 1 | REMINDER: Create IPD Approval Milestone Bullet | Pre-EA (Exemption Request) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | SUGGESTED | 7
8 |  | 1 | Additional Information Submission | Pre-EA (Exemption Request) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 8
9 |  | 1 | Document Submitted to EAO for "Initial Review" | Pre-EA (Exemption Request) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 9
10 | 9 | 1 | EAO's Viewpoint on Submitted Document | Pre-EA (Exemption Request) | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 10
11 |  | 1 | Project Withdrawn | Pre-EA (Exemption Request) | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 11
12 |  | 1 | Other | Pre-EA (Exemption Request) | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 12
13 |  | 1 | IPD/EP Approval Decision (Day Zero) | Pre-EA (Exemption Request) | CEAO | Decision | END | FALSE | 90 | 0 | MANDATORY | 13
14 | 13 | 1 | Approval of IPD/EP Announcement & Tweet | Pre-EA (Exemption Request) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 14
15 | 13 | 1 | Approval of IPD/EP Milestone Bullet | Pre-EA (Exemption Request) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 15
16 |  | 2 | IPD/EP Approved (Day One) | Early Engagement | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 16
17 |  | 2 | Notification sent to potential PINs | Early Engagement | Notification | Milestone | INTERMEDIATE | FALSE | 7 | 0 | SUGGESTED | 17
18 |  | 2 | Comment Period | Early Engagement | Comment Period | PCP | INTERMEDIATE | TRUE | 14 | 30 | MANDATORY | 18
19 | 18 | 2 | PCP Coming Soon Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | MANDATORY | 19
20 | 18 | 2 | PCP Coming Soon Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | MANDATORY | 20
21 | 18 | 2 | PCP Now Open Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 21
22 | 18 | 2 | PCP Ending Soon Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | MANDATORY | 22
23 |  | 2 | Confirm Capacity Funding Amounts | Early Engagement | Capacity Funding | Finance | INTERMEDIATE | FALSE | 21 | 0 | SUGGESTED | 23
24 | 23 | 2 | Early Engagement Capacity Funding Confirmation Due | Early Engagement | Financial | Calendar | INTERMEDIATE | FALSE | 0 | 0 | SUGGESTED | 24
25 |  | 2 | Fee Order: Submission of Exemption Request | Early Engagement | Fee Order | Finance | INTERMEDIATE | FALSE | 30 | 0 | MANDATORY | 25
26 | 25 | 2 | Fee Order for Filing of Exemption Request | Early Engagement | Financial | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 26
27 |  | 2 | PIN Notice of Intent Completed | Early Engagement | Generic | Milestone | INTERMEDIATE | FALSE | 80 | 0 | MANDATORY | 27
28 |  | 2 | Create SoE Milestone Bullet | Early Engagement | Generic | Milestone | INTERMEDIATE | FALSE | 85 | 0 | SUGGESTED | 28
29 | 28 | 2 | REMINDER: Create SoE Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | SUGGESTED | 29
30 |  | 2 | Additional Information Submission | Early Engagement | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 30
31 |  | 2 | Submit Estimate for Capacity Funding | Early Engagement | Capacity Funding | Finance | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 31
32 | 31 | 2 | Capacity Funding Estimate Due | Early Engagement | Financial | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 32
33 |  | 2 | Dispute Resolution Triggered | Early Engagement | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 33
34 | 33 | 2 | DR Triggered Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 34
35 | 33 | 2 | Dispute Resolution Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 35
36 |  | 2 | Additional Comment Period | Early Engagement | Comment Period | PCP | INTERMEDIATE | TRUE | 0 | 30 | OPTIONAL | 36
37 | 36 | 2 | PCP Coming Soon Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 37
38 | 36 | 2 | Additional PCP Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 38
39 | 36 | 2 | PCP Now Open Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 39
40 | 36 | 2 | PCP Ending Soon Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 40
41 |  | 2 | Open House | Early Engagement | Open House | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 41
42 |  | 2 | Virtual Information Session | Early Engagement | Virtual Information Session | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 42
43 |  | 2 | Comment Period Time Limit Extension | Early Engagement | PCP Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | 43
44 | 43 | 2 | PCP Extended Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 44
45 | 43 | 2 | PCP Extended Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 45
46 |  | 2 | s.38 Extension of Time Limit | Early Engagement | Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | 46
47 | 46 | 2 | Extension Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 47
48 | 46 | 2 | Time Limit Extended Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 48
49 |  | 2 | s.45 Suspension of the Exemption Request Process | Early Engagement | Time Limit Suspension | Suspension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 49
50 | 49 | 2 | Exemption Request Process Suspension Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 50
51 | 49 | 2 | Exemption Request Process Suspended Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 51
52 |  | 2 | s.45 Resumption of the Exemption Request Process | Early Engagement | Time Limit Resumption | Suspension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 52
53 | 52 | 2 | Exemption Request Process Resumption Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 53
54 | 52 | 2 | Exemption Request Process Resumed Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 54
55 |  | 2 | Exemption Request Terminated s.39(d) | Early Engagement | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 55
56 | 55 | 2 | Termination Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 56
57 | 55 | 2 | Exemption Request Terminated Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 57
58 |  | 2 | Project Withdrawn | Early Engagement | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 58
59 | 58 | 2 | Withdrawal Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 59
60 | 58 | 2 | Project Withdrawn Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 60
61 |  | 2 | Other | Early Engagement | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 61
62 |  | 2 | Summary of Engagement Published | Early Engagement | Report | Milestone | END | FALSE | 90 | 0 | MANDATORY | 62
63 | 62 | 2 | Summary of Engagement Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 63
64 | 62 | 2 | Summary of Engagement Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 64
65 |  | 3 | Start of DPD Development | DPD Development (Proponent Time) | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 65
66 |  | 3 | Create DPD Receipt Milestone Bullet | DPD Development (Proponent Time) | Generic | Milestone | INTERMEDIATE | FALSE | 360 | 0 | SUGGESTED | 66
67 | 66 | 3 | REMINDER: Create DPD Receipt Milestone Bullet | DPD Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | SUGGESTED | 67
68 |  | 3 | Additional Information Submission | DPD Development (Proponent Time) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 68
69 |  | 3 | Document Submitted to EAO for "Initial Review" | DPD Development (Proponent Time) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 69
70 | 69 | 3 | EAO's Viewpoint on Submitted Document | DPD Development (Proponent Time) | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 70
71 |  | 3 | Dispute Resolution Triggered | DPD Development (Proponent Time) | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 71
72 | 71 | 3 | DR Triggered Announcement & Tweet | DPD Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 72
73 | 71 | 3 | Dispute Resolution Milestone Bullet | DPD Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 73
74 |  | 3 | Exemption Request Terminated s.39(d) | DPD Development (Proponent Time) | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 74
75 | 74 | 3 | Termination Announcement & Tweet | DPD Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 75
76 | 74 | 3 | Exemption Request Terminated Milestone Bullet | DPD Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 76
77 |  | 3 | Project Withdrawn | DPD Development (Proponent Time) | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 77
78 | 77 | 3 | Withdrawal Announcement & Tweet | DPD Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 78
79 | 77 | 3 | Project Withdrawn Milestone Bullet | DPD Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 79
80 |  | 3 | Other | DPD Development (Proponent Time) | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 80
81 |  | 3 | Last Day of DPD Development (day before DPD received) | DPD Development (Proponent Time) | Date Capture | Milestone | END | FALSE | 365 | 0 | MANDATORY | 81
82 |  | 4 | Detailed Project Description Received | Readiness Decision | Submission | Milestone | START | FALSE | 0 | 0 | MANDATORY | 82
83 | 82 | 4 | DPD Received Announcement & Tweet | Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 83
84 | 82 | 4 | DPD Received Milestone Bullet | Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 84
85 |  | 4 | Exemption Request Report referred to CEAO | Readiness Decision | Referral | Milestone | INTERMEDIATE | FALSE | 50 | 0 | MANDATORY | 85
86 |  | 4 | CEAO's Readiness Decision (Exemption Request) | Readiness Decision | CEAO | Decision | INTERMEDIATE | FALSE | 60 | 0 | MANDATORY | 86
87 |  | 4 | Exemption Request Package Referred to Minister | Readiness Decision | Referral | Milestone | INTERMEDIATE | FALSE | 65 | 0 | MANDATORY | 87
88 |  | 4 | Additional Information Submission | Readiness Decision | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 88
89 |  | 4 | Dispute Resolution Triggered | Readiness Decision | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 89
90 | 89 | 4 | DR Triggered Announcement & Tweet | Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 90
91 | 89 | 4 | Dispute Resolution Milestone Bullet | Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 91
92 |  | 4 | Exemption Request Terminated s.39(d) | Readiness Decision | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 92
93 | 92 | 4 | Termination Announcement & Tweet | Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 93
94 | 92 | 4 | Exemption Request Terminated Milestone Bullet | Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 94
95 |  | 4 | Project Withdrawn | Readiness Decision | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 95
96 | 95 | 4 | Withdrawal Announcement & Tweet | Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 96
97 | 95 | 4 | Project Withdrawn Milestone Bullet | Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 97
98 |  | 4 | Other | Readiness Decision | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 98
99 |  | 4 | Last Day of Readiness Decision (Exemption Request) | Readiness Decision | Date Capture | Milestone | END | FALSE | 70 | 0 | MANDATORY | 99
100 |  | 5 | Exemption Request Package Received by Minister | Exemption Decision | Generic | Milestone | START | FALSE | 0 | 0 | MANDATORY | 100
101 |  | 5 | Additional Information Submission | Exemption Decision | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 101
102 |  | 5 | Minister Meeting | Exemption Decision | Meeting | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 102
103 |  | 5 | s.38 Extension of Time Limit | Exemption Decision | Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | 103
104 | 103 | 5 | Extension Announcement & Tweet | Exemption Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 104
105 | 103 | 5 | Time Limit Extended Milestone Bullet | Exemption Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 105
106 |  | 5 | s.45 Suspension of the Exemption Request Process | Exemption Decision | Time Limit Suspension | Suspension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 106
107 | 106 | 5 | Exemption Request Process Suspension Announcement & Tweet | Exemption Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 107
108 | 106 | 5 | Exemption Request Process Suspended Milestone Bullet | Exemption Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 108
109 |  | 5 | s.45 Resumption of the Exemption Request Process | Exemption Decision | Time Limit Resumption | Suspension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 109
110 | 109 | 5 | Exemption Request Process Resumption Announcement & Tweet | Exemption Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 110
111 | 109 | 5 | Exemption Request Process Resumed Milestone Bullet | Exemption Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 111
112 |  | 5 | Project Withdrawn | Exemption Decision | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 112
113 | 112 | 5 | Withdrawal Announcement & Tweet | Exemption Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 113
114 | 112 | 5 | Project Withdrawn Milestone Bullet | Exemption Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 114
115 |  | 5 | Other | Exemption Decision | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 115
116 |  | 5 | Minister's Exemption Request Decision | Exemption Decision | Minister | Decision | END | FALSE | 30 | 0 | MANDATORY | 116
117 | 116 | 5 | Exemption Request Announcement & Tweet (unless return to CEAO) | Exemption Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 117
118 |  | 6 | Exemption Request Report referred to CEAO for Further Decision | Further Readiness Decision | Referral | Milestone | START | FALSE | 0 | 0 | MANDATORY | 118
119 |  | 6 | Additional Information Submission | Further Readiness Decision | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 119
120 |  | 6 | Dispute Resolution Triggered | Further Readiness Decision | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 120
121 | 120 | 6 | DR Triggered Announcement & Tweet | Further Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 121
122 | 120 | 6 | Dispute Resolution Milestone Bullet | Further Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 122
123 |  | 6 | EAC Assessment Terminated s.39(d) | Further Readiness Decision | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 123
124 | 123 | 6 | Termination Announcement & Tweet | Further Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 124
125 | 123 | 6 | EAC Assessment Terminated Milestone Bullet | Further Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 125
126 |  | 6 | Project Withdrawn | Further Readiness Decision | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 126
127 | 126 | 6 | Withdrawal Announcement & Tweet | Further Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 127
128 | 126 | 6 | Project Withdrawn Milestone Bullet | Further Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 128
129 |  | 6 | Other | Further Readiness Decision | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 129
99999 |  | 6 | Last Day of Further Readiness Decision | Further Readiness Decision | Date Capture | Milestone | INTERMEDIATE | FALSE | 0 | 0 | HIDDEN | 129
130 |  | 6 | CEAO's Further Readiness Decision (Exemption Request) | Further Readiness Decision | CEAO | Decision | END | FALSE | 60 | 0 | MANDATORY | 130
131 | 131 | 6 | Further Readiness Decision Announcement & Tweet | Further Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 131
132 | 131 | 6 | Further Readiness Decision Milestone Bullet (if Project proceeds to Process Planning) | Further Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 132

## Outcomes
No | TemplateNo | TemplateName | OutcomeName | SortOrder | TESTED
1 | 10 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is POSITIVE | 1
2 | 10 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is NEGATIVE | 2
3 | 11 | Project Withdrawn | Proponent Withdraws Project from the Exemption Request Process | 3
4 | 13 | IPD/EP Approval Decision (Day Zero) | CEAO Approves Submitted IPD/EP - s.13(3)(a) | 4
5 | 13 | IPD/EP Approval Decision (Day Zero) | CEAO Requires the Proponent to Submit a Revised IPD/EP - s.13(3)(b) | 5
6 | 33 | Dispute Resolution Triggered | A Matter has been Referred for Dispute Resolution | 6
7 | 55 | Exemption Request Terminated s.39(d) | Exemption Request is Terminated under s.39(d) of EA Act (2018) | 7
8 | 58 | Project Withdrawn | Proponent Withdraws Project from the Exemption Request Process | 8
9 | 62 | Summary of Engagement Published | Last Day of Exemption Request: Early Engagement PHASE | 9
10 | 70 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is POSITIVE | 10
11 | 70 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is NEGATIVE | 11
12 | 74 | Exemption Request Terminated s.39(d) | Exemption Request is Terminated under s.39(d) of EA Act (2018) | 12
13 | 77 | Project Withdrawn | Proponent Withdraws Project from the Exemption Request Process | 13
14 | 86 | CEAO's Readiness Decision (Exemption Request) | CEAO Requires the Proponent to Submit a Revised DPD - s.16(2)(a) | 14
15 | 86 | CEAO's Readiness Decision (Exemption Request) | Project is Referred to Minister for Exemption - s.16(2)(b) | 15
16 | 89 | Dispute Resolution Triggered | A Matter has been Referred for Dispute Resolution | 16
17 | 92 | Exemption Request Terminated s.39(d) | Exemption Request is Terminated under s.39(d) of EA Act (2018) | 17
18 | 95 | Project Withdrawn | Proponent Withdraws Project from the Exemption Request Process | 18
19 | 99 | Last Day of Readiness Decision (Exemption Request) | Last Day of Exemption Request: Readiness Decision PHASE | 19
20 | 112 | Project Withdrawn | Proponent Withdraws Project from the Exemption Request Process | 20
21 | 116 | Minister's Exemption Request Decision | Project is Exempt from Requiring an EAC | 21
22 | 116 | Minister's Exemption Request Decision | Refer the Project to the CEAO for Further Decision | 22
23 | 120 | Dispute Resolution Triggered | A Matter has been Referred for Dispute Resolution | 23
24 | 123 | EAC Assessment Terminated s.39(d) | Exemption Request is Terminated under s.39(d) of EA Act (2018) | 24
25 | 126 | Project Withdrawn | Proponent Withdraws Project from the Exemption Request Process | 25
26 | 130 | CEAO's Further Readiness Decision (Exemption Request) | CEAO Requires the Proponent to Submit a Revised Exemption Request DPD - s.16(2)(a) | 26
27 | 130 | CEAO's Further Readiness Decision (Exemption Request) | CEAO Requires the Proponent to Submit a Revised EAC Assessment DPD - s.16(2)(a) | 27
28 | 130 | CEAO's Further Readiness Decision (Exemption Request) | Project Moves to EAC Assessment: Process Planning PHASE - s.18(1)(a) | 28
29 | 130 | CEAO's Further Readiness Decision (Exemption Request) | Project is Referred to Minister for EAC Assessment: Process Planning - s.18(1)(b) | 29

## Actions
No | OutcomeNo | OutcomeName | ActionName | ActionDescription | AdditionalParams | SortOrder
1 | 1 | EAO's Viewpoint is POSITIVE | NONE | No Actions Needed | {} | 1
2 | 2 | EAO's Viewpoint is NEGATIVE | NONE | No Actions Needed | {} | 2
3 | 3 | Proponent Withdraws Project from the Exemption Request Process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 3
4 | 3 | Proponent Withdraws Project from the Exemption Request Process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 4
5 | 3 | Proponent Withdraws Project from the Exemption Request Process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 5
6 | 3 | Proponent Withdraws Project from the Exemption Request Process | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 6
7 | 4 | CEAO Approves Submitted IPD/EP - s.13(3)(a) | LockWorkStartDate | Set the workStartDate to thisEvent ACTUAL | {"start_date_locked": true} | 7
8 | 4 | CEAO Approves Submitted IPD/EP - s.13(3)(a) | SetEventDate | Set "Early Engagement ¦ IPD/EP Approved (Day One)" ANTICIPATED to thisEvent ACTUAL +1 | {"phase_name":"Early Engagement","work_type_id": 5, "ea_act_id": 3, "event_name": "IPD/EP Approved (Day One)", "start_at": 1 } | 8
9 | 5 | CEAO Requires the Proponent to Submit a Revised IPD/EP - s.13(3)(b) | AddEvent | Add EVENT "Pre-EA (Exemption Request) ¦ Submission of IPD/EP for CEAO Approval" at thisEvent ACTUAL +28 (a renamed copy of original EVENT), Add EVENT "Pre-EA (Exemption Request) ¦ IPD/EP Approval Decision (Day Zero)" at thisEvent ACTUAL +38 (a renamed copy of original EVENT) | [{"phase_name":"Pre-EA (Exemption Request)","work_type_id": 5, "ea_act_id": 3, "event_name": "Submission of IPD/EP for CEAO Approval", "start_at": 28 },{"phase_name":"Pre-EA (Exemption Request)","work_type_id": 5, "ea_act_id": 3, "event_name": "IPD/EP Approval Decision (Day Zero)", "start_at": 10 }] | 9
10 | 5 | CEAO Requires the Proponent to Submit a Revised IPD/EP - s.13(3)(b) | ChangePhaseEndEvent | Set (new EVENT) "Pre-EA (Exemption Request) ¦ IPD/EP Approval Decision (Day Zero)" to PHASE END EVENT | {"phase_name":"Pre-EA (Exemption Request)","work_type_id": 5, "ea_act_id": 3, "event_name": "IPD/EP Approval Decision (Day Zero)"} | 10
11 | 6 | A Matter has been Referred for Dispute Resolution | NONE | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {"work_type": 15} | 11
12 | 7 | Exemption Request is Terminated under s.39(d) of EA Act (2018) | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 12
13 | 7 | Exemption Request is Terminated under s.39(d) of EA Act (2018) | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 13
14 | 7 | Exemption Request is Terminated under s.39(d) of EA Act (2018) | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 14
15 | 7 | Exemption Request is Terminated under s.39(d) of EA Act (2018) | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 15
16 | 8 | Proponent Withdraws Project from the Exemption Request Process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 16
17 | 8 | Proponent Withdraws Project from the Exemption Request Process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 17
18 | 8 | Proponent Withdraws Project from the Exemption Request Process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 18
19 | 8 | Proponent Withdraws Project from the Exemption Request Process | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 19
20 | 9 | Last Day of Exemption Request: Early Engagement PHASE | SetEventDate | Set "Start of DPD Development (Day after SoE) ¦ DPD Development (Proponent Time)" ANTICIPATED to thisEvent ACTUAL +1 | {"phase_name":"DPD Development (Proponent Time)","work_type_id": 5, "ea_act_id": 3, "event_name": "Start of DPD Development", "start_at": 1 } | 20
21 | 10 | EAO's Viewpoint is POSITIVE | NONE | No Actions Needed | {} | 21
22 | 11 | EAO's Viewpoint is NEGATIVE | NONE | No Actions Needed | {} | 22
23 | 12 | Exemption Request is Terminated under s.39(d) of EA Act (2018) | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 23
24 | 12 | Exemption Request is Terminated under s.39(d) of EA Act (2018) | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 24
25 | 12 | Exemption Request is Terminated under s.39(d) of EA Act (2018) | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 25
26 | 12 | Exemption Request is Terminated under s.39(d) of EA Act (2018) | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 26
27 | 13 | Proponent Withdraws Project from the Exemption Request Process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 27
28 | 13 | Proponent Withdraws Project from the Exemption Request Process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 28
29 | 13 | Proponent Withdraws Project from the Exemption Request Process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 29
30 | 13 | Proponent Withdraws Project from the Exemption Request Process | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 30
31 | 14 | CEAO Requires the Proponent to Submit a Revised DPD - s.16(2)(a) | ChangePhaseEndEvent | Set thisEvent to PHASE END EVENT | {"phase_name":"Readiness Decision","work_type_id": 5, "ea_act_id": 3, "event_name": "CEAO's Readiness Decision (Exemption Request)"} | 31
32 | 14 | CEAO Requires the Proponent to Submit a Revised DPD - s.16(2)(a) | NONE | Set "Readiness Decision ¦ Exemption Request Package Referred to Minister", "Readiness Decision ¦ Last Day of Readiness Decision (Exemption Request)" to INACTIVE | [{"phase_name":"Readiness Decision","work_type_id": 5, "ea_act_id": 3, "event_name": "Exemption Request Package Referred to Minister", "is_active": false },{"phase_name":"Readiness Decision","work_type_id": 5, "ea_act_id": 3, "event_name": "Last Day of Readiness Decision (Exemption Request)", "is_active": false }] | 32
33 | 14 | CEAO Requires the Proponent to Submit a Revised DPD - s.16(2)(a) | AddPhase | Add PHASE "Revised DPD Development (Proponent Time)" (a renamed copy of original PHASE),Add PHASE "Readiness Decision" (a copy of original PHASE) | [{"phase_name":"DPD Development (Proponent Time)","work_type_id": 5, "ea_act_id": 3, "new_name": "Revised DPD Development (Proponent Time)", "legislated": false },{"phase_name":"Readiness Decision","work_type_id": 5, "ea_act_id": 3, "new_name": "Readiness Decision", "legislated": false }] | 33
34 | 14 | CEAO Requires the Proponent to Submit a Revised DPD - s.16(2)(a) | SetEventDate | Set "Revised DPD Development (Proponent Time) ¦ Start of DPD Development" ANTICIPATED to thisEvent ACTUAL +1 | {"phase_name":"Revised DPD Development (Proponent Time)","work_type_id": 5, "ea_act_id": 3, "event_name": "Start of DPD Development", "start_at": 1 } | 34
35 | 15 | Project is Referred to Minister for Exemption - s.16(2)(b) | NONE | No Actions Needed | {} | 35
36 | 16 | A Matter has been Referred for Dispute Resolution | NONE | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {"work_type": 15} | 36
37 | 17 | Exemption Request is Terminated under s.39(d) of EA Act (2018) | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 37
38 | 17 | Exemption Request is Terminated under s.39(d) of EA Act (2018) | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 38
39 | 17 | Exemption Request is Terminated under s.39(d) of EA Act (2018) | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 39
40 | 17 | Exemption Request is Terminated under s.39(d) of EA Act (2018) | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 40
41 | 18 | Proponent Withdraws Project from the Exemption Request Process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 41
42 | 18 | Proponent Withdraws Project from the Exemption Request Process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 42
43 | 18 | Proponent Withdraws Project from the Exemption Request Process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 43
44 | 18 | Proponent Withdraws Project from the Exemption Request Process | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 44
45 | 19 | Last Day of Exemption Request: Readiness Decision PHASE | SetEventDate | Set "Exemption Decision ¦ Exemption Request Package Received by Minister" ANTICIPATED to thisEvent ACTUAL +1 | {"phase_name":"Exemption Decision","work_type_id": 5, "ea_act_id": 3, "event_name": "Exemption Request Package Received by Minister", "start_at": 1 } | 45
46 | 20 | Proponent Withdraws Project from the Exemption Request Process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 46
47 | 20 | Proponent Withdraws Project from the Exemption Request Process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 47
48 | 20 | Proponent Withdraws Project from the Exemption Request Process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 48
49 | 20 | Proponent Withdraws Project from the Exemption Request Process | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 49
50 | 21 | Project is Exempt from Requiring an EAC | SetWorkState | Set workState to COMPLETED | {"work_state": "COMPLETED"} | 50
51 | 21 | Project is Exempt from Requiring an EAC | SetProjectState | Set linked PROJECT projectState to "Active: Pre-Construction" | {"project_state": "PRE_CONSTRUCTION"} | 51
52 | 22 | Refer the Project to the CEAO for Further Decision | AddPhase | Set "Further Readiness Decision" PHASE to ACTIVE | [{"phase_name":"Further Readiness Decision","work_type_id": 5, "ea_act_id": 3, "new_name": "Further Readiness Decision", "legislated": false }] | 52
53 | 22 | Refer the Project to the CEAO for Further Decision | SetEventDate | Set "Further Readiness Decision ¦ Exemption Request Report referred to CEAO for Further Decision" ANTICIPATED to thisEvent ACTUAL +1 | {"phase_name":"Further Readiness Decision","work_type_id": 5, "ea_act_id": 3, "event_name": "Exemption Request Report referred to CEAO for Further Decision", "start_at": 1 } | 53
54 | 23 | A Matter has been Referred for Dispute Resolution | NONE | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {"work_type": 15} | 54
55 | 24 | Exemption Request is Terminated under s.39(d) of EA Act (2018) | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 55
56 | 24 | Exemption Request is Terminated under s.39(d) of EA Act (2018) | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 56
57 | 24 | Exemption Request is Terminated under s.39(d) of EA Act (2018) | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 57
58 | 24 | Exemption Request is Terminated under s.39(d) of EA Act (2018) | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 58
59 | 25 | Proponent Withdraws Project from the Exemption Request Process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 59
60 | 25 | Proponent Withdraws Project from the Exemption Request Process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 60
61 | 25 | Proponent Withdraws Project from the Exemption Request Process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 61
62 | 25 | Proponent Withdraws Project from the Exemption Request Process | SetProjectStatus | Set linked PROJECT projectActive to FALSE | {"is_active": false} | 62
63 | 26 | CEAO Requires the Proponent to Submit a Revised Exemption Request DPD - s.16(2)(a) | AddPhase | Add PHASE "Revised DPD Development (Proponent Time)" (a renamed copy of original PHASE),Add PHASE "Further Readiness Decision" (a copy of original PHASE) | [{"phase_name":"DPD Development (Proponent Time)","work_type_id": 5, "ea_act_id": 3, "new_name": "Revised DPD Development (Proponent Time)", "legislated": false },{"phase_name":"Further Readiness Decision","work_type_id": 5, "ea_act_id": 3, "new_name": "Further Readiness Decision", "legislated": false }] | 63
64 | 26 | CEAO Requires the Proponent to Submit a Revised Exemption Request DPD - s.16(2)(a) | SetEventDate | Set "Revised DPD Development (Proponent Time) ¦ Start of DPD Development" ANTICIPATED to thisEvent ACTUAL +1 | {"phase_name":"Revised DPD Development (Proponent Time)","work_type_id": 5, "ea_act_id": 3, "event_name": "Start of DPD Development", "start_at": 1 } | 64
65 | 27 | CEAO Requires the Proponent to Submit a Revised EAC Assessment DPD - s.16(2)(a) | CreateWork | Create a new WORK: "EAC Assessment" and link to thisWorkLinkedProject | {"work_type": 6} | 65
66 | 27 | CEAO Requires the Proponent to Submit a Revised EAC Assessment DPD - s.16(2)(a) | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 66
67 | 27 | CEAO Requires the Proponent to Submit a Revised EAC Assessment DPD - s.16(2)(a) | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 67
68 | 27 | CEAO Requires the Proponent to Submit a Revised EAC Assessment DPD - s.16(2)(a) | SetWorkState | Set workState to COMPLETED | {"work_state": "COMPLETED"} | 68
69 | 28 | Project Moves to EAC Assessment: Process Planning PHASE - s.18(1)(a) | CreateWork | Create a new WORK: "EAC Assessment" and link to thisWorkLinkedProject | {"work_type": 6} | 69
70 | 28 | Project Moves to EAC Assessment: Process Planning PHASE - s.18(1)(a) | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 70
71 | 28 | Project Moves to EAC Assessment: Process Planning PHASE - s.18(1)(a) | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 71
72 | 28 | Project Moves to EAC Assessment: Process Planning PHASE - s.18(1)(a) | SetWorkState | Set workState to COMPLETED | {"work_state": "COMPLETED"} | 72
73 | 29 | Project is Referred to Minister for EAC Assessment: Process Planning - s.18(1)(b) | NONE | Process is UNKNOWN at this time | {} | 73

## Lookups
WorkType | EA Act | Legislated |  | Event Type | Event Category | Visibility | ActionName | Event Position | Multiple Days | Action Name
Project Notification | EA Act (2018) | TRUE | Milestone | Generic | Milestone | MANDATORY | AllEventsDeactivated | START | TRUE | AddEvent
Minister's Designation | EA Act (2002) | FALSE | Milestone | Meeting | Calendar | SUGGESTED | AllEventsDeleted | INTERMEDIATE | FALSE | AddPhase
CEAO's Designation | EA Act (1996) |  | Milestone | Notification | Decision | OPTIONAL | CloseEverything | END |  | ChangePhaseEndEvent
EAC Assessment |  |  | Milestone | Order | Finance | HIDDEN | CloseWork |  |  | CreateWork
Exemption Order |  |  | Milestone | Referral | PCP |  | CompleteCurrentPhase |  |  | LockWorkStartDate
Dispute Resolution |  |  | Milestone | Report | Extension |  | CreateNewWork |  |  | SetEventDate
EAC/Order Amendment |  |  | Milestone | Request | Suspension |  | DisableWorkStartDate |  |  | SetEventsStatus
Document Review |  |  | Milestone | Submission |  |  | DuplicatePhase |  |  | SetFederalInvolvement
EAC Extension |  |  | Milestone | Other | [5 empty] | SetPhasesStatus
Substantial Start Decision |  |  | Milestone | Date Capture | [5 empty] | SetProjectState
EAC/Order Transfer |  |  | Extension | Time Limit Extension | [5 empty] | SetProjectStatus
EAC/Order Suspension |  |  | Extension | PCP Time Limit Extension | [5 empty] | SetWorkDecisionMaker
EAC/Order Cancellation |  |  | Extension | Interregnum | [5 empty] | SetWorkState
Other |  |  | Suspension | Time Limit Suspension | [5 empty] | NONE
|  |  | Suspension | Time Limit Resumption
|  |  | Decision | EAC Ministers
|  |  | Decision | Minister
|  |  | Decision | CEAO
|  |  | Decision | ADM
|  |  | Decision | EPD
|  |  | Decision | PAD (Lead)
|  |  | Decision | Reviewer
|  |  | Decision | Federal
|  |  | Decision | Other
|  |  | PCP | Comment Period
|  |  | PCP | Open House
|  |  | PCP | Virtual Information Session
|  |  | PCP | Other
|  |  | Calendar | Communications
|  |  | Calendar | Executive
|  |  | Calendar | Financial
|  |  | Calendar | Work
|  |  | Calendar | Other
|  |  | Finance | Capacity Funding
|  |  | Finance | Fee Order
|  |  | Finance | Penalties
|  |  | Finance | Administrative
|  |  | Finance | Other