## Phases
No | Name | WorkType | EAAct | NumberOfDays | Legislated | Color | Visibility | SortOrder
1 | Initial Contact | Amendment | EA Act (2018) | 28 | FALSE | #a6bb2e | REGULAR | 1
2 | Procedures Development | Amendment | EA Act (2018) | 28 | FALSE | #a6bb2e | REGULAR | 2
3 | Amendment Application Development (Proponent Time) | Amendment | EA Act (2018) | 180 | FALSE | #6d7274 | REGULAR | 3
4 | Complexity Decision | Amendment | EA Act (2018) | 30 | FALSE | #a6bb2e | REGULAR | 4
5 | Amendment Review (Typical) | Amendment | EA Act (2018) | 150 | FALSE | #a6bb2e | REGULAR | 5
6 | Amendment Review (Simple) | Amendment | EA Act (2018) | 30 | FALSE | #a6bb2e | HIDDEN | 6
7 | Amendment Review (32.5) | Amendment | EA Act (2018) | 60 | FALSE | #a6bb2e | HIDDEN | 7
8 | Amendment Review (Complex) | Amendment | EA Act (2018) | 700 | FALSE | #a6bb2e | HIDDEN | 8
9 | Decision | Amendment | EA Act (2018) | 30 | FALSE | #a6bb2e | REGULAR | 9

## Events
No | Parent | PhaseNo | EventName | Phase | EventType | EventCategory | EventPosition | MultipleDays | StartAt | NumberOfDays | Visibility | SortOrder
1 |  | 1 | Start of Initial Contact (Contact, Date Confirmation, etc.) | Initial Contact | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 1
2 |  | 1 | Initial Meeting with Proponent | Initial Contact | Meeting | Milestone | INTERMEDIATE | FALSE | 7 | 0 | SUGGESTED | 2
3 |  | 1 | Submission of Amendment Project Description | Initial Contact | Submission | Milestone | INTERMEDIATE | FALSE | 14 | 0 | SUGGESTED | 3
4 |  | 1 | Additional Information Submission | Initial Contact | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 4
5 |  | 1 | Meeting with Proponent | Initial Contact | Meeting | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 5
6 |  | 1 | Document Submitted to EAO for "Initial Review" | Initial Contact | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 6
7 | 6 | 1 | EAO's Viewpoint on Submitted Document | Initial Contact | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 7
8 |  | 1 | Holder Withdraws from the Amendment Process | Initial Contact | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 8
9 |  | 1 | Other | Initial Contact | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 9
10 |  | 1 | Choose the "Path" of this Amendment Process | Initial Contact | PAD (Lead) | Decision | END | FALSE | 28 | 0 | MANDATORY | 10
11 |  | 2 | Start of Procedures Development | Procedures Development | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 11
12 |  | 2 | Create Amendment Workplan | Procedures Development | Report | Milestone | INTERMEDIATE | FALSE | 14 | 0 | SUGGESTED | 12
13 |  | 2 | Create Draft Amendment Procedures | Procedures Development | Report | Milestone | INTERMEDIATE | FALSE | 21 | 0 | SUGGESTED | 13
14 |  | 2 | Additional Information Submission | Procedures Development | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 14
15 |  | 2 | Amendment Application Information Requirements | Procedures Development | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 15
16 |  | 2 | Notification of Potential PINs | Procedures Development | Notification | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 16
17 |  | 2 | PIN Notice Complete | Procedures Development | Generic | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 17
18 |  | 2 | TAC Established | Procedures Development | Generic | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 18
19 |  | 2 | CAC Established | Procedures Development | Generic | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 19
20 |  | 2 | Document Submitted to EAO for "Initial Review" | Procedures Development | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 20
21 | 20 | 2 | EAO's Viewpoint on Submitted Document | Procedures Development | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 21
22 |  | 2 | Dispute Resolution Triggered | Procedures Development | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 22
23 | 22 | 2 | DR Triggered Announcement & Tweet | Procedures Development | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 23
24 | 22 | 2 | Dispute Resolution Milestone Bullet | Procedures Development | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 24
25 |  | 2 | Holder Withdraws from the Amendment Process | Procedures Development | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 25
26 |  | 2 | Other | Procedures Development | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 26
27 |  | 2 | Amendment Procedures Posted | Procedures Development | Report | Milestone | END | FALSE | 28 | 0 | MANDATORY | 27
28 |  | 3 | Start of Amendment Application Development (Proponent Time) | Amendment Application Development (Proponent Time) | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 28
29 |  | 3 | Additional Information Submission | Amendment Application Development (Proponent Time) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 29
30 |  | 3 | Amendment Application Information Requirements/Procedures | Amendment Application Development (Proponent Time) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 30
31 |  | 3 | Document Submitted to EAO for "Initial Review" | Amendment Application Development (Proponent Time) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 31
32 | 31 | 3 | EAO's Viewpoint on Submitted Document | Amendment Application Development (Proponent Time) | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 32
33 |  | 3 | Dispute Resolution Triggered | Amendment Application Development (Proponent Time) | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 33
34 | 33 | 3 | DR Triggered Announcement & Tweet | Amendment Application Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 34
35 | 33 | 3 | Dispute Resolution Milestone Bullet | Amendment Application Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 35
36 |  | 3 | Holder Withdraws from the Amendment Process | Amendment Application Development (Proponent Time) | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 36
37 |  | 3 | Other | Amendment Application Development (Proponent Time) | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 37
38 |  | 3 | Last Day of Amendment Application Development (Proponent Time) | Amendment Application Development (Proponent Time) | Date Capture | Milestone | END | FALSE | 180 | 0 | MANDATORY | 38
39 |  | 4 | Amendment Application Received (Start of Review) | Complexity Decision | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 39
40 | 39 | 4 | Amendment Application Received Announcement & Tweet | Complexity Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 40
41 | 39 | 4 | Amendment Application Received Milestone Bullet | Complexity Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 41
42 |  | 4 | Amendment Complexity/Fee Decision | Complexity Decision | EPD | Decision | INTERMEDIATE | FALSE | 25 | 0 | MANDATORY | 42
43 |  | 4 | Additional Information Submission | Complexity Decision | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 43
44 |  | 4 | Review of Supplementary Information | Complexity Decision | Generic | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 44
45 |  | 4 | Amendment Application Information Requirements/Procedures | Complexity Decision | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 45
46 |  | 4 | Notification of Potential PINs | Complexity Decision | Notification | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 46
47 |  | 4 | PIN Notice Complete | Complexity Decision | Generic | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 47
48 |  | 4 | TAC Established | Complexity Decision | Generic | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 48
49 |  | 4 | CAC Established | Complexity Decision | Generic | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 49
50 |  | 4 | Dispute Resolution Triggered | Complexity Decision | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 50
51 | 50 | 4 | DR Triggered Announcement & Tweet | Complexity Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 51
52 | 50 | 4 | Dispute Resolution Milestone Bullet | Complexity Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 52
53 |  | 4 | Amendment Withdrawn | Complexity Decision | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 53
54 | 53 | 4 | Withdrawal Announcement & Tweet | Complexity Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 54
55 | 53 | 4 | Amendment Withdrawn Milestone Bullet | Complexity Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 55
56 |  | 4 | Other | Complexity Decision | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 56
57 |  | 4 | Fee Order: Submission of Amendment Application | Complexity Decision | Fee Order | Finance | END | FALSE | 30 | 0 | MANDATORY | 57
58 |  | 4 | Fee Order for Filing of Amendment Application | Complexity Decision | Financial | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 58
59 |  | 5 | Continuation of Application Review | Amendment Review (Typical) | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 59
60 |  | 5 | Draft Amendment & Recommendation Report | Amendment Review (Typical) | Report | Milestone | INTERMEDIATE | FALSE | 120 | 0 | SUGGESTED | 60
61 |  | 5 | Final Amendment Report & Recommendation | Amendment Review (Typical) | Report | Milestone | INTERMEDIATE | FALSE | 145 | 0 | MANDATORY | 61
62 |  | 5 | Delegation of Amendment Decision | Amendment Review (Typical) | CEAO | Decision | INTERMEDIATE | FALSE | 145 | 0 | MANDATORY | 62
63 |  | 5 | Additional Information Submission | Amendment Review (Typical) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 63
64 |  | 5 | Document Submitted to EAO for "Initial Review" | Amendment Review (Typical) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 64
65 | 64 | 5 | EAO's Viewpoint on Submitted Document | Amendment Review (Typical) | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 65
66 |  | 5 | Review of Supplementary Information | Amendment Review (Typical) | Generic | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 66
67 |  | 5 | Amendment Application Information Requirements/Procedures | Amendment Review (Typical) | Notification | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 67
68 |  | 5 | Notification of Potential PINs | Amendment Review (Typical) | Generic | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 68
69 |  | 5 | PIN Notice Complete | Amendment Review (Typical) | Generic | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 69
70 |  | 5 | TAC Established | Amendment Review (Typical) | Generic | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 70
71 |  | 5 | CAC Established | Amendment Review (Typical) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 71
72 |  | 5 | Dispute Resolution Triggered | Amendment Review (Typical) | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 72
73 | 72 | 5 | DR Triggered Announcement & Tweet | Amendment Review (Typical) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 73
74 | 72 | 5 | Dispute Resolution Milestone Bullet | Amendment Review (Typical) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 74
75 |  | 5 | Additional Comment Period | Amendment Review (Typical) | Comment Period | PCP | INTERMEDIATE | TRUE | 0 | 30 | OPTIONAL | 75
76 | 75 | 5 | PCP Coming Soon Announcement & Tweet | Amendment Review (Typical) | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | 76
77 | 75 | 5 | Additional PCP Milestone Bullet | Amendment Review (Typical) | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | 77
78 | 75 | 5 | PCP Now Open Announcement & Tweet | Amendment Review (Typical) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 78
79 | 75 | 5 | PCP Ending Soon Announcement & Tweet | Amendment Review (Typical) | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | OPTIONAL | 79
80 |  | 5 | Open House | Amendment Review (Typical) | Open House | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 80
81 |  | 5 | Virtual Information Session | Amendment Review (Typical) | Virtual Information Session | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 81
82 |  | 5 | Comment Period Time Limit Extension | Amendment Review (Typical) | PCP Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | 82
83 | 82 | 5 | PCP Extended Announcement & Tweet | Amendment Review (Typical) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 83
84 | 82 | 5 | PCP Extended Milestone Bullet | Amendment Review (Typical) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 84
85 |  | 5 | Amendment Withdrawn | Amendment Review (Typical) | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 85
86 | 85 | 5 | Withdrawal Announcement & Tweet | Amendment Review (Typical) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 86
87 | 85 | 5 | Project Withdrawn Milestone Bullet | Amendment Review (Typical) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 87
88 |  | 5 | Other | Amendment Review (Typical) | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 88
89 |  | 5 | Amendment Decision Package Referred to Decision Maker | Amendment Review (Typical) | Referral | Milestone | END | FALSE | 150 | 0 | MANDATORY | 89
90 |  | 6 | Continuation of Application Review | Amendment Review (Simple) | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 90
91 |  | 6 | Final Amendment Report & Recommendation | Amendment Review (Simple) | Report | Milestone | INTERMEDIATE | FALSE | 25 | 0 | MANDATORY | 91
92 |  | 6 | Delegation of Amendment Decision | Amendment Review (Simple) | CEAO | Decision | INTERMEDIATE | FALSE | 30 | 0 | MANDATORY | 92
93 |  | 6 | Additional Information Submission | Amendment Review (Simple) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 93
94 |  | 6 | Draft Amendment & Recommendation Report | Amendment Review (Simple) | Report | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 94
95 |  | 6 | Document Submitted to EAO for "Initial Review" | Amendment Review (Simple) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 95
96 | 95 | 6 | EAO's Viewpoint on Submitted Document | Amendment Review (Simple) | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 96
97 |  | 6 | Dispute Resolution Triggered | Amendment Review (Simple) | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 97
98 | 97 | 6 | DR Triggered Announcement & Tweet | Amendment Review (Simple) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 98
99 | 97 | 6 | Dispute Resolution Milestone Bullet | Amendment Review (Simple) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 99
100 |  | 6 | Additional Comment Period | Amendment Review (Simple) | Comment Period | PCP | INTERMEDIATE | TRUE | 0 | 30 | OPTIONAL | 100
101 | 100 | 6 | PCP Coming Soon Announcement & Tweet | Amendment Review (Simple) | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | 101
102 | 100 | 6 | Additional PCP Milestone Bullet | Amendment Review (Simple) | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | 102
103 | 100 | 6 | PCP Now Open Announcement & Tweet | Amendment Review (Simple) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 103
104 | 100 | 6 | PCP Ending Soon Announcement & Tweet | Amendment Review (Simple) | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | OPTIONAL | 104
105 |  | 6 | Open House | Amendment Review (Simple) | Open House | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 105
106 |  | 6 | Virtual Information Session | Amendment Review (Simple) | Virtual Information Session | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 106
107 |  | 6 | Comment Period Time Limit Extension | Amendment Review (Simple) | PCP Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | 107
108 | 107 | 6 | PCP Extended Announcement & Tweet | Amendment Review (Simple) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 108
109 | 107 | 6 | PCP Extended Milestone Bullet | Amendment Review (Simple) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 109
110 |  | 6 | Amendment Withdrawn | Amendment Review (Simple) | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 110
111 | 110 | 6 | Withdrawal Announcement & Tweet | Amendment Review (Simple) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 111
112 | 110 | 6 | Project Withdrawn Milestone Bullet | Amendment Review (Simple) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 112
113 |  | 6 | Other | Amendment Review (Simple) | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 113
114 |  | 6 | Amendment Decision Package Referred to Decision Maker | Amendment Review (Simple) | Referral | Milestone | END | FALSE | 30 | 0 | MANDATORY | 114
115 |  | 7 | Continuation of Application Review | Amendment Review (32.5) | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 115
116 |  | 7 | Final Amendment Report & Recommendation | Amendment Review (32.5) | Report | Milestone | INTERMEDIATE | FALSE | 55 | 0 | MANDATORY | 116
117 |  | 7 | Delegation of Amendment Decision | Amendment Review (32.5) | CEAO | Decision | INTERMEDIATE | FALSE | 60 | 0 | MANDATORY | 117
118 |  | 7 | Additional Information Submission | Amendment Review (32.5) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 118
119 |  | 7 | Draft Amendment & Recommendation Report | Amendment Review (32.5) | Report | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 119
120 | 119 | 7 | Document Submitted to EAO for "Initial Review" | Amendment Review (32.5) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 120
121 |  | 7 | EAO's Viewpoint on Submitted Document | Amendment Review (32.5) | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 121
122 |  | 7 | Dispute Resolution Triggered | Amendment Review (32.5) | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 122
123 | 122 | 7 | DR Triggered Announcement & Tweet | Amendment Review (32.5) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 123
124 | 122 | 7 | Dispute Resolution Milestone Bullet | Amendment Review (32.5) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 124
125 |  | 7 | Additional Comment Period | Amendment Review (32.5) | Comment Period | PCP | INTERMEDIATE | TRUE | 0 | 30 | OPTIONAL | 125
126 | 125 | 7 | PCP Coming Soon Announcement & Tweet | Amendment Review (32.5) | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | 126
127 | 125 | 7 | Additional PCP Milestone Bullet | Amendment Review (32.5) | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | 127
128 | 125 | 7 | PCP Now Open Announcement & Tweet | Amendment Review (32.5) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 128
129 | 125 | 7 | PCP Ending Soon Announcement & Tweet | Amendment Review (32.5) | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | OPTIONAL | 129
130 |  | 7 | Open House | Amendment Review (32.5) | Open House | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 130
131 |  | 7 | Virtual Information Session | Amendment Review (32.5) | Virtual Information Session | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 131
132 |  | 7 | Comment Period Time Limit Extension | Amendment Review (32.5) | PCP Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | 132
133 | 132 | 7 | PCP Extended Announcement & Tweet | Amendment Review (32.5) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 133
134 | 132 | 7 | PCP Extended Milestone Bullet | Amendment Review (32.5) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 134
135 |  | 7 | Amendment Withdrawn | Amendment Review (32.5) | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 135
136 | 135 | 7 | Withdrawal Announcement & Tweet | Amendment Review (32.5) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 136
137 | 135 | 7 | Project Withdrawn Milestone Bullet | Amendment Review (32.5) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 137
138 |  | 7 | Other | Amendment Review (32.5) | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 138
139 |  | 7 | Amendment Decision Package Referred to Decision Maker | Amendment Review (32.5) | Referral | Milestone | END | FALSE | 60 | 0 | MANDATORY | 139
140 |  | 8 | Continuation of Application Review | Amendment Review (Complex) | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 140
141 |  | 8 | Comment Period | Amendment Review (Complex) | Comment Period | PCP | INTERMEDIATE | TRUE | 90 | 30 | SUGGESTED | 141
142 | 141 | 8 | PCP Coming Soon Announcement & Tweet | Amendment Review (Complex) | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | SUGGESTED | 142
143 | 141 | 8 | PCP Coming Soon Milestone Bullet | Amendment Review (Complex) | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | SUGGESTED | 143
144 | 141 | 8 | PCP Now Open Announcement & Tweet | Amendment Review (Complex) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | SUGGESTED | 144
145 | 141 | 8 | PCP Ending Soon Announcement & Tweet | Amendment Review (Complex) | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | SUGGESTED | 145
146 |  | 8 | Draft Amendment & Recommendation Report | Amendment Review (Complex) | Report | Milestone | INTERMEDIATE | FALSE | 620 | 0 | SUGGESTED | 146
147 |  | 8 | Final Amendment Report & Recommendation | Amendment Review (Complex) | Report | Milestone | INTERMEDIATE | FALSE | 680 | 0 | MANDATORY | 147
148 |  | 8 | Delegation of Amendment Decision | Amendment Review (Complex) | CEAO | Decision | INTERMEDIATE | FALSE | 690 | 0 | MANDATORY | 148
149 |  | 8 | Additional Information Submission | Amendment Review (Complex) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 149
150 |  | 8 | Document Submitted to EAO for "Initial Review" | Amendment Review (Complex) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 150
151 | 150 | 8 | EAO's Viewpoint on Submitted Document | Amendment Review (Complex) | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 151
152 |  | 8 | Review of Supplementary Information | Amendment Review (Complex) | Generic | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 152
153 |  | 8 | Amendment Application Information Requirements/Procedures | Amendment Review (Complex) | Report | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 153
154 |  | 8 | Notification of Potential PINs | Amendment Review (Complex) | Generic | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 154
155 |  | 8 | PIN Notice Complete | Amendment Review (Complex) | Generic | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 155
156 |  | 8 | TAC Established | Amendment Review (Complex) | Generic | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 156
157 |  | 8 | CAC Established | Amendment Review (Complex) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 157
158 |  | 8 | Dispute Resolution Triggered | Amendment Review (Complex) | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 158
159 | 158 | 8 | DR Triggered Announcement & Tweet | Amendment Review (Complex) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 159
160 | 158 | 8 | Dispute Resolution Milestone Bullet | Amendment Review (Complex) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 160
161 |  | 8 | Additional Comment Period | Amendment Review (Complex) | Comment Period | PCP | INTERMEDIATE | TRUE | 0 | 30 | OPTIONAL | 161
162 | 161 | 8 | PCP Coming Soon Announcement & Tweet | Amendment Review (Complex) | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | 162
163 | 161 | 8 | Additional PCP Milestone Bullet | Amendment Review (Complex) | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | 163
164 | 161 | 8 | PCP Now Open Announcement & Tweet | Amendment Review (Complex) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 164
165 | 161 | 8 | PCP Ending Soon Announcement & Tweet | Amendment Review (Complex) | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | OPTIONAL | 165
166 |  | 8 | Open House | Amendment Review (Complex) | Open House | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 166
167 |  | 8 | Virtual Information Session | Amendment Review (Complex) | Virtual Information Session | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 167
168 |  | 8 | Comment Period Time Limit Extension | Amendment Review (Complex) | PCP Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | 168
169 | 168 | 8 | PCP Extended Announcement & Tweet | Amendment Review (Complex) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 169
170 | 168 | 8 | PCP Extended Milestone Bullet | Amendment Review (Complex) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 170
171 |  | 8 | Amendment Withdrawn | Amendment Review (Complex) | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 171
172 | 171 | 8 | Withdrawal Announcement & Tweet | Amendment Review (Complex) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 172
173 | 171 | 8 | Project Withdrawn Milestone Bullet | Amendment Review (Complex) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 173
174 |  | 8 | Other | Amendment Review (Complex) | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 174
175 |  | 8 | Amendment Decision Package Referred to Decision Maker | Amendment Review (Complex) | Referral | Milestone | END | FALSE | 700 | 0 | MANDATORY | 175
176 |  | 9 | Amendment Decision Package Received by Decision Maker | Decision | Generic | Milestone | START | FALSE | 0 | 0 | MANDATORY | 176
177 |  | 9 | Create Amendment Decision Milestone Bullet | Decision | Generic | Milestone | INTERMEDIATE | FALSE | 25 | 0 | SUGGESTED | 177
178 | 177 | 9 | REMINDER: Create Amendment Decision Milestone Bullet (if not Minister) | Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | SUGGESTED | 178
179 |  | 9 | Additional Information Submission | Decision | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 179
180 |  | 9 | Amendment Withdrawn | Decision | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 180
181 | 180 | 9 | Withdrawal Announcement & Tweet | Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 181
182 | 180 | 9 | Amendment Withdrawn Milestone Bullet | Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 182
183 |  | 9 | Other | Decision | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 183
184 |  | 9 | Amendment Decision | Decision | CEAO | Decision | END | FALSE | 30 | 0 | MANDATORY | 184
185 | 184 | 9 | Amendment Decision Announcement & Tweet | Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 185
186 | 184 | 9 | Amendment Decision Milestone Bullet (only if Decision is not: Minister) | Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 186
187 | [11 empty] | 187
188 | [11 empty] | 188
189 | [11 empty] | 189
190 | [11 empty] | 190
191 | [11 empty] | 191
192 | [11 empty] | 192
193 | [11 empty] | 193
194 | [11 empty] | 194
195 | [11 empty] | 195
196 | [11 empty] | 196
197 | [11 empty] | 197
198 | [11 empty] | 198
199 | [11 empty] | 199
200 | [11 empty] | 200
201 | [11 empty] | 201
202 | [11 empty] | 202
203 | [11 empty] | 203
204 | [11 empty] | 204
205 | [11 empty] | 205
206 | [11 empty] | 206
207 | [11 empty] | 207
208 | [11 empty] | 208
209 | [11 empty] | 209
210 | [11 empty] | 210
211 | [11 empty] | 211
212 | [11 empty] | 212
213 | [11 empty] | 213
214 | [11 empty] | 214
215 | [11 empty] | 215
216 | [11 empty] | 216
217 | [11 empty] | 217
218 | [11 empty] | 218
219 | [11 empty] | 219
220 | [11 empty] | 220
221 | [11 empty] | 221
222 | [11 empty] | 222
223 | [11 empty] | 223
224 | [11 empty] | 224
225 | [11 empty] | 225
226 | [11 empty] | 226
227 | [11 empty] | 227
228 | [11 empty] | 228
229 | [11 empty] | 229
230 | [11 empty] | 230
231 | [11 empty] | 231
232 | [11 empty] | 232
233 | [11 empty] | 233
234 | [11 empty] | 234
235 | [11 empty] | 235
236 | [11 empty] | 236
237 | [11 empty] | 237
238 | [11 empty] | 238
239 | [11 empty] | 239
240 | [11 empty] | 240
241 | [11 empty] | 241
242 | [11 empty] | 242
243 | [11 empty] | 243
244 | [11 empty] | 244
245 | [11 empty] | 245
246 | [11 empty] | 246
247 | [11 empty] | 247
248 | [11 empty] | 248
249 | [11 empty] | 249
250 | [11 empty] | 250
251 | [11 empty] | 251
252 | [11 empty] | 252
253 | [11 empty] | 253
254 | [11 empty] | 254
255 | [11 empty] | 255
256 | [11 empty] | 256
257 | [11 empty] | 257
258 | [11 empty] | 258
259 | [11 empty] | 259
260 | [11 empty] | 260
261 | [11 empty] | 261
262 | [11 empty] | 262
263 | [11 empty] | 263
264 | [11 empty] | 264
265 | [11 empty] | 265
266 | [11 empty] | 266
267 | [11 empty] | 267
268 | [11 empty] | 268
269 | [11 empty] | 269
270 | [11 empty] | 270
271 | [11 empty] | 271
272 | [11 empty] | 272
273 | [11 empty] | 273
274 | [11 empty] | 274
275 | [11 empty] | 275
276 | [11 empty] | 276
277 | [11 empty] | 277
278 | [11 empty] | 278
279 | [11 empty] | 279
280 | [11 empty] | 280
281 | [11 empty] | 281
282 | [11 empty] | 282
283 | [11 empty] | 283
284 | [11 empty] | 284
285 | [11 empty] | 285
286 | [11 empty] | 286
287 | [11 empty] | 287
288 | [11 empty] | 288
289 | [11 empty] | 289
290 | [11 empty] | 290
291 | [11 empty] | 291
292 | [11 empty] | 292
293 | [11 empty] | 293
294 | [11 empty] | 294
295 | [11 empty] | 295
296 | [11 empty] | 296
297 | [11 empty] | 297
298 | [11 empty] | 298
299 | [11 empty] | 299
300 | [11 empty] | 300
301 | [11 empty] | 301
302 | [11 empty] | 302
303 | [11 empty] | 303
304 | [11 empty] | 304
305 | [11 empty] | 305
306 | [11 empty] | 306
307 | [11 empty] | 307
308 | [11 empty] | 308
309 | [11 empty] | 309
310 | [11 empty] | 310
311 | [11 empty] | 311
312 | [11 empty] | 312
313 | [11 empty] | 313
314 | [11 empty] | 314
315 | [11 empty] | 315
316 | [11 empty] | 316
317 | [11 empty] | 317
318 | [11 empty] | 318
319 | [11 empty] | 319
320 | [11 empty] | 320
321 | [11 empty] | 321
322 | [11 empty] | 322
323 | [11 empty] | 323
324 | [11 empty] | 324
325 | [11 empty] | 325
326 | [11 empty] | 326
327 | [11 empty] | 327
328 | [11 empty] | 328
329 | [11 empty] | 329
330 | [11 empty] | 330
331 | [11 empty] | 331
332 | [11 empty] | 332
333 | [11 empty] | 333
334 | [11 empty] | 334
335 | [11 empty] | 335
336 | [11 empty] | 336
------------------------------------------------
Amendment Decision Package Received by Decision Maker
Create Amendment Decision Milestone Bullet
REMINDER: Create Amendment Decision Milestone Bullet (if not Minister)

## Outcomes
No | TemplateNo | TemplateName | OutcomeName | OutcomeDescription | SortOrder
1 | 7 | EAO's Viewpoint on Submitted Document | Viewpoint is POSITIVE | EAO's Viewpoint is POSITIVE | 1
2 | 7 | EAO's Viewpoint on Submitted Document | Viewpoint is NEGATIVE | EAO's Viewpoint is NEGATIVE | 2
3 | 8 | Holder Withdraws from the Amendment Process | Amendment Withdrawn | Proponent withdraws from the Amendment process | 3
4 | 10 | Choose the "Path" of this Amendment Process | EAO to develop Procedures | Holder has submitted an Amendment PD and EAO will develop Procedures (keep all PHASEs) | 4 | a
5 | 10 | Choose the "Path" of this Amendment Process | Holder to develop Application | Holder has contacted the EAO and is currently developing their Amendment Application (delete the Amendment Procedures PHASE) | 5 | b
6 | 10 | Choose the "Path" of this Amendment Process | Holder to submit Application | Holder will submit the Amendment Application Directly to the EAO (delete the Application Procedures and Amendment Application Development PHASEs) | 6 | c
7 | 10 | Choose the "Path" of this Amendment Process | Application Submitted | Holder has already submitted their Amendment Application without interaction with the EAO (delete this PHASE as well as Application Procedures and Amendment Application Development PHASEs) | 7 | d
8 | 21 | EAO's Viewpoint on Submitted Document | Viewpoint is POSITIVE | EAO's Viewpoint is POSITIVE | 8
9 | 21 | EAO's Viewpoint on Submitted Document | Viewpoint is NEGATIVE | EAO's Viewpoint is NEGATIVE | 9
10 | 22 | Dispute Resolution Triggered | Amendment Withdrawn | Proponent withdraws from the Amendment process | 10
11 | 25 | Holder Withdraws from the Amendment Process | Dispute Resolution Requested | A Matter has been Referred for Dispute Resolution | 11
12 | 32 | EAO's Viewpoint on Submitted Document | Viewpoint is POSITIVE | EAO's Viewpoint is POSITIVE | 12
13 | 32 | EAO's Viewpoint on Submitted Document | Viewpoint is NEGATIVE | EAO's Viewpoint is NEGATIVE | 13
14 | 36 | Holder Withdraws from the Amendment Process | Amendment Withdrawn | Proponent withdraws from the Amendment process | 14
15 | 42 | Amendment Complexity/Fee Decision | Simple Amendment | Amendment is determined to be "Simple" | 15
16 | 42 | Amendment Complexity/Fee Decision | Typical Amendment | Amendment is determined to be "Typical" | 16
17 | 42 | Amendment Complexity/Fee Decision | Complex Amendment | Amendment is determined to be "Complex" | 17
18 | 42 | Amendment Complexity/Fee Decision | s.32(5) Amendment | Amendment under Section 32(5) of the EA Act (2018) | 18
19 | 50 | Dispute Resolution Triggered | Dispute Resolution Requested | A Matter has been Referred for Dispute Resolution | 19
20 | 53 | Amendment Withdrawn | Amendment Withdrawn | Proponent withdraws from the Amendment process | 20
21 | 62 | Delegation of Amendment Decision | ADM's Decision | ADM, EA Operations is delegated to make the Amendment Decision | 21
22 | 62 | Delegation of Amendment Decision | CEAO's Decision | CEAO is delegated to make the Amendment Decision | 22
23 | 62 | Delegation of Amendment Decision | Minister's Decision | Minister to make the Amendment Decision | 23
24 | 65 | EAO's Viewpoint on Submitted Document | Viewpoint is POSITIVE | EAO's Viewpoint is POSITIVE | 24
25 | 65 | EAO's Viewpoint on Submitted Document | Viewpoint is NEGATIVE | EAO's Viewpoint is NEGATIVE | 25
26 | 72 | Dispute Resolution Triggered | Dispute Resolution Requested | A Matter has been Referred for Dispute Resolution | 26
27 | 85 | Amendment Withdrawn | Amendment Withdrawn | Proponent withdraws from the Amendment process | 27
28 | 92 | Delegation of Amendment Decision | ADM's Decision | ADM, EA Operations is delegated to make the Amendment Decision | 28
29 | 92 | Delegation of Amendment Decision | CEAO's Decision | CEAO is delegated to make the Amendment Decision | 29
30 | 92 | Delegation of Amendment Decision | Minister's Decision | Minister to make the Amendment Decision | 30
31 | 96 | EAO's Viewpoint on Submitted Document | Viewpoint is POSITIVE | EAO's Viewpoint is POSITIVE | 31
32 | 96 | EAO's Viewpoint on Submitted Document | Viewpoint is NEGATIVE | EAO's Viewpoint is NEGATIVE | 32
33 | 97 | Dispute Resolution Triggered | Dispute Resolution Requested | A Matter has been Referred for Dispute Resolution | 33
34 | 110 | Amendment Withdrawn | Amendment Withdrawn | Proponent withdraws from the Amendment process | 34
35 | 117 | Delegation of Amendment Decision | ADM's Decision | ADM, EA Operations is delegated to make the Amendment Decision | 35
36 | 117 | Delegation of Amendment Decision | CEAO's Decision | CEAO is delegated to make the Amendment Decision | 36
37 | 117 | Delegation of Amendment Decision | Minister's Decision | Minister to make the Amendment Decision | 37
38 | 121 | EAO's Viewpoint on Submitted Document | Viewpoint is POSITIVE | EAO's Viewpoint is POSITIVE | 38
39 | 121 | EAO's Viewpoint on Submitted Document | Viewpoint is NEGATIVE | EAO's Viewpoint is NEGATIVE | 39
40 | 122 | Dispute Resolution Triggered | Dispute Resolution Requested | A Matter has been Referred for Dispute Resolution | 40
41 | 135 | Amendment Withdrawn | Amendment Withdrawn | Proponent withdraws from the Amendment process | 41
42 | 148 | Delegation of Amendment Decision | ADM's Decision | ADM, EA Operations is delegated to make the Amendment Decision | 42
43 | 148 | Delegation of Amendment Decision | CEAO's Decision | CEAO is delegated to make the Amendment Decision | 43
44 | 148 | Delegation of Amendment Decision | Minister's Decision | Minister to make the Amendment Decision | 44
45 | 151 | EAO's Viewpoint on Submitted Document | Viewpoint is POSITIVE | EAO's Viewpoint is POSITIVE | 45
46 | 151 | EAO's Viewpoint on Submitted Document | Viewpoint is NEGATIVE | EAO's Viewpoint is NEGATIVE | 46
47 | 158 | Dispute Resolution Triggered | Dispute Resolution Requested | A Matter has been Referred for Dispute Resolution | 47
48 | 171 | Amendment Withdrawn | Amendment Withdrawn | Proponent withdraws from the Amendment process | 48
49 | 180 | Amendment Withdrawn | Amendment Withdrawn | Proponent withdraws from the Amendment process | 49
50 | 184 | Amendment Decision | Amendment Granted | Decision Maker Amends the EAC/Exemption Order | 50
51 | 184 | Amendment Decision | Amendment Refused | Decision Maker Refuses to Amend the EAC/Exemption Order | 51
52 |  |  |  |  | 52
53 |  |  |  |  | 53
54 |  |  |  |  | 54
55 |  |  |  |  | 55
56 |  |  |  |  | 56
57 |  |  |  |  | 57
58 |  |  |  |  | 58
59 |  |  |  |  | 59
60 |  |  |  |  | 60
61 |  |  |  |  | 61
62 |  |  |  |  | 62
63 |  |  |  |  | 63
64 |  |  |  |  | 64
65 |  |  |  |  | 65

## Actions
No | OutcomeNo | OutcomeName | ActionName | ActionDescription | AdditionalParams | SortOrder
1 | 1 | Viewpoint is POSITIVE | NONE | No Actions Needed | {} | 1
2 | 2 | Viewpoint is NEGATIVE | NONE | No Actions Needed | {} | 2
3 | 3 | Amendment Withdrawn | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 3
4 | 3 | Amendment Withdrawn | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 4
5 | 3 | Amendment Withdrawn | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 5
6 | 4 | EAO to develop Procedures | NONE | No Actions Needed | {} | 6
7 | 5 | Holder to develop Application | SetPhasesStatus | Set "Procedures Development" PHASE to INACTIVE | [{"phase_name":"Procedures Development","work_type_id": 7, "ea_act_id": 3, "is_active": false }] | 7
8 | 5 | Holder to develop Application | SetEventDate | Set "Amendment Application Development (Proponent Time) ¦ Start of Amendment Application Development (Proponent Time)" ANTICIPATED to thisEventDate +1 | {"phase_name":"Amendment Application Development (Proponent Time)","work_type_id": 7, "ea_act_id": 3, "event_name": "Start of Amendment Application Development (Proponent Time)", "start_at": 1 } | 8
9 | 6 | Holder to submit Application | SetPhasesStatus | Set "Procedures Development" & "Amendment Application Development (Proponent Time)" PHASEs to INACTIVE | [{"phase_name":"Procedures Development","work_type_id": 7, "ea_act_id": 3, "is_active": false },{"phase_name":"Amendment Application Development (Proponent Time)","work_type_id": 7, "ea_act_id": 3, "is_active": false }] | 9
10 | 6 | Holder to submit Application | SetEventDate | Set "Complexity Decision ¦ Amendment Application Received (Start of Review)" ANTICIPATED to thisEventDate +1 | {"phase_name":"Complexity Decision","work_type_id": 7, "ea_act_id": 3, "event_name": "Amendment Application Received (Start of Review)", "start_at": 1 } | 10
11 | 7 | Application Submitted | SetPhasesStatus | Set "Initial Contact", "Procedures Development", & "Amendment Application Development (Proponent Time)" PHASEs to INACTIVE | [{"phase_name":"Initial Contact","work_type_id": 7, "ea_act_id": 3, "is_active": false },{"phase_name":"Procedures Development","work_type_id": 7, "ea_act_id": 3, "is_active": false },{"phase_name":"Amendment Application Development (Proponent Time)","work_type_id": 7, "ea_act_id": 3, "is_active": false }] | 11
12 | 7 | Application Submitted | SetEventDate | Set "Complexity Decision ¦ Amendment Application Received (Start of Review)" ANTICIPATED to thisEventDate +1 | {"phase_name":"Complexity Decision","work_type_id": 7, "ea_act_id": 3, "event_name": "Amendment Application Received (Start of Review)", "start_at": 1 } | 12
13 | 8 | Viewpoint is POSITIVE | NONE | No Actions Needed | {} | 13
14 | 9 | Viewpoint is NEGATIVE | NONE | No Actions Needed | {} | 14
15 | 10 | Amendment Withdrawn | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 15
16 | 10 | Amendment Withdrawn | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 16
17 | 10 | Amendment Withdrawn | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 17
18 | 11 | Dispute Resolution Requested | NONE | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {} | 18
19 | 12 | Viewpoint is POSITIVE | NONE | No Actions Needed | {} | 19
20 | 13 | Viewpoint is NEGATIVE | NONE | No Actions Needed | {} | 20
21 | 14 | Amendment Withdrawn | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 21
22 | 14 | Amendment Withdrawn | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 22
23 | 14 | Amendment Withdrawn | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 23
24 | 15 | Simple Amendment | SetPhasesStatus | Set "Amendment Review (Typical)" PHASE to INACTIVE | [{"phase_name":"Amendment Review (Typical)","work_type_id": 7, "ea_act_id": 3, "is_active": false }] | 24
25 | 15 | Simple Amendment | AddPhase | Set "Amendment Review (Simple)" PHASE to ACTIVE | [{"phase_name":"Amendment Review (Simple)","work_type_id": 7, "ea_act_id": 3, "new_name": "Amendment Review (Simple)", "legislated": false }] | 25
26 | 16 | Typical Amendment | NONE | No Actions Needed | {} | 26
27 | 17 | Complex Amendment | SetPhasesStatus | Set "Amendment Review (Typical)" PHASE to INACTIVE | [{"phase_name":"Amendment Review (Typical)","work_type_id": 7, "ea_act_id": 3, "is_active": false }] | 27
28 | 17 | Complex Amendment | AddPhase | Set "Amendment Review (Complex)" PHASE to ACTIVE | [{"phase_name":"Amendment Review (Complex)","work_type_id": 7, "ea_act_id": 3, "new_name": "Amendment Review (Complex)", "legislated": false }] | 28
29 | 18 | s.32(5) Amendment | SetPhasesStatus | Set "Amendment Review (Typical)" PHASE to INACTIVE | [{"phase_name":"Amendment Review (Typical)","work_type_id": 7, "ea_act_id": 3, "is_active": false }] | 29
30 | 18 | s.32(5) Amendment | AddPhase | Set "Amendment Review (32.5)" PHASE to ACTIVE | [{"phase_name":"Amendment Review (32.5)","work_type_id": 7, "ea_act_id": 3, "new_name": "Amendment Review (32.5)", "legislated": false }] | 30
31 | 19 | Dispute Resolution Requested | NONE | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {} | 31
32 | 20 | Amendment Withdrawn | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 32
33 | 20 | Amendment Withdrawn | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 33
34 | 20 | Amendment Withdrawn | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 34
35 | 21 | ADM's Decision | SetWorkDecisionMaker | Set thisWorkDecisionMaker to currentADM | {"position_id": 2} | 35
36 | 22 | CEAO's Decision | SetWorkDecisionMaker | Set thisWorkDecisionMaker to currentCEAO | {"position_id": 1} | 36
37 | 23 | Minister's Decision | SetWorkDecisionMaker | Set thisWorkDecisionMaker to currentMinisterEnvironment | {"position_id": 8} | 37
38 | 24 | Viewpoint is POSITIVE | NONE | No Actions Needed | {} | 38
39 | 25 | Viewpoint is NEGATIVE | NONE | No Actions Needed | {} | 39
40 | 26 | Dispute Resolution Requested | NONE | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {} | 40
41 | 27 | Amendment Withdrawn | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 41
42 | 27 | Amendment Withdrawn | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 42
43 | 27 | Amendment Withdrawn | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 43
44 | 28 | ADM's Decision | SetWorkDecisionMaker | Set thisWorkDecisionMaker to currentADM | {"position_id": 2} | 44
45 | 29 | CEAO's Decision | SetWorkDecisionMaker | Set thisWorkDecisionMaker to currentCEAO | {"position_id": 1} | 45
46 | 30 | Minister's Decision | SetWorkDecisionMaker | Set thisWorkDecisionMaker to currentMinisterEnvironment | {"position_id": 8} | 46
47 | 31 | Viewpoint is POSITIVE | NONE | No Actions Needed | {} | 47
48 | 32 | Viewpoint is NEGATIVE | NONE | No Actions Needed | {} | 48
49 | 33 | Dispute Resolution Requested | NONE | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {} | 49
50 | 34 | Amendment Withdrawn | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 50
51 | 34 | Amendment Withdrawn | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 51
52 | 34 | Amendment Withdrawn | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 52
53 | 35 | ADM's Decision | SetWorkDecisionMaker | Set thisWorkDecisionMaker to currentADM | {"position_id": 2} | 53
54 | 36 | CEAO's Decision | SetWorkDecisionMaker | Set thisWorkDecisionMaker to currentCEAO | {"position_id": 1} | 54
55 | 37 | Minister's Decision | SetWorkDecisionMaker | Set thisWorkDecisionMaker to currentMinisterEnvironment | {"position_id": 8} | 55
56 | 38 | Viewpoint is POSITIVE | NONE | No Actions Needed | {} | 56
57 | 39 | Viewpoint is NEGATIVE | NONE | No Actions Needed | {} | 57
58 | 40 | Dispute Resolution Requested | NONE | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {} | 58
59 | 41 | Amendment Withdrawn | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 59
60 | 41 | Amendment Withdrawn | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 60
61 | 41 | Amendment Withdrawn | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 61
62 | 42 | ADM's Decision | SetWorkDecisionMaker | Set thisWorkDecisionMaker to currentADM | {"position_id": 2} | 62
63 | 43 | CEAO's Decision | SetWorkDecisionMaker | Set thisWorkDecisionMaker to currentCEAO | {"position_id": 1} | 63
64 | 44 | Minister's Decision | SetWorkDecisionMaker | Set thisWorkDecisionMaker to currentMinisterEnvironment | {"position_id": 8} | 64
65 | 45 | Viewpoint is POSITIVE | NONE | No Actions Needed | {} | 65
66 | 46 | Viewpoint is NEGATIVE | NONE | No Actions Needed | {} | 66
67 | 47 | Dispute Resolution Requested | NONE | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {} | 67
68 | 48 | Amendment Withdrawn | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 68
69 | 48 | Amendment Withdrawn | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 69
70 | 48 | Amendment Withdrawn | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 70
71 | 49 | Amendment Withdrawn | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 71
72 | 49 | Amendment Withdrawn | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 72
73 | 49 | Amendment Withdrawn | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 73
74 | 50 | Amendment Granted | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 74
75 | 51 | Amendment Refused | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 75

## Lookups
WorkType | EA Act | Legislated |  | Event Type | Event Category | Visibility | ActionName | Event Position | Multiple Days | Action Name
Project Notification | EA Act (2018) | TRUE | Milestone | Generic | Milestone | MANDATORY | AllEventsDeactivated | START | TRUE | AddEvent
Minister's Designation | EA Act (2002) | FALSE | Milestone | Meeting | Calendar | SUGGESTED | AllEventsDeleted | INTERMEDIATE | FALSE | AddPhase
CEAO's Designation | EA Act (1996) |  | Milestone | Notification | Decision | OPTIONAL | CloseEverything | END |  | ChangePhaseEndEvent
EAC Assessment |  |  | Milestone | Order | Finance | HIDDEN | CloseWork |  |  | CreateWork
Exemption Request |  |  | Milestone | Referral | PCP |  | CompleteCurrentPhase |  |  | LockWorkStartDate
Dispute Resolution |  |  | Milestone | Report | Extension |  | CreateNewWork |  |  | SetEventDate
EAC/Order Amendment |  |  | Milestone | Request | Suspension |  | DisableWorkStartDate |  |  | SetEventsStatus
Document Review |  |  | Milestone | Submission |  |  | DuplicatePhase |  |  | SetFederalInvolvement
EAC Extension |  |  | Milestone | Other | [5 empty] | SetPhasesStatus
Substantial Start Decision |  |  | Milestone | Date Capture | [5 empty] | SetProjectState
EAC/Order Transfer |  |  | Extension | Time Limit Extension | [5 empty] | SetProjectStatus
EAC/Order Suspension |  |  | Extension | PCP Time Limit Extension | [5 empty] | SetWorkDecisionMaker
EAC/Order Cancellation |  |  | Extension | Interregnum | [5 empty] | SetWorkState
Other |  |  | Suspension | Time Limit Suspension | [5 empty] | NONE
|  |  | Suspension | Time Limit Resumption
|  |  | Decision | EAC Ministers
|  |  | Decision | Minister
|  |  | Decision | CEAO
|  |  | Decision | ADM
|  |  | Decision | EPD
|  |  | Decision | PAD (Lead)
|  |  | Decision | Reviewer
|  |  | Decision | Federal
|  |  | Decision | Other
|  |  | PCP | Comment Period
|  |  | PCP | Open House
|  |  | PCP | Virtual Information Session
|  |  | PCP | Other
|  |  | Calendar | Communications
|  |  | Calendar | Executive
|  |  | Calendar | Financial
|  |  | Calendar | Work
|  |  | Calendar | Other
|  |  | Finance | Capacity Funding
|  |  | Finance | Fee Order
|  |  | Finance | Penalties
|  |  | Finance | Administrative
|  |  | Finance | Other