## Instructions
Cell Colors
This color means that the cell has a picklist Validation constraint.
This color means that the cell has a formula and should not be changed. Change the vLookup source.
This color means the cell is open to user input
Order of Data Entry
You need to do the Phases before Events, Events before Outcomes, and Outcomes before Actions
The No Field and Row Deletion
The No (number field) of each sheet is the Validation list of the next sheet. For example the Events sheet has the heading PhaseNo which pulls from the Phases sheet No cells.
To maintain the Data Validation for all the sheets, make sure you DELETE the Entire Row for every unused row in the sheet you are working on. IE select the entire row(s) and right-click > Delete.

## Phases
No | Name | WorkType | EAAct | NumberOfDays | Legislated | Color | Visibility | SortOrder
1 | Pre-Early Engagement | Assessment | EA Act (2018) | 90 | FALSE | #3eb1d7 | REGULAR | 1
2 | Early Engagement | Assessment | EA Act (2018) | 90 | TRUE | #54858d | REGULAR | 2
3 | DPD Development (Proponent Time) | Assessment | EA Act (2018) | 365 | FALSE | #6d7274 | REGULAR | 3
4 | Readiness Decision | Assessment | EA Act (2018) | 60 | FALSE | #da6d65 | REGULAR | 4
5 | Termination Decision | Assessment | EA Act (2018) | 30 | FALSE | #FFFFFF | HIDDEN | 5
6 | Further Readiness Decision | Assessment | EA Act (2018) | 30 | FALSE | #da6d65 | HIDDEN | 6
7 | Process Planning | Assessment | EA Act (2018) | 120 | TRUE | #043673 | REGULAR | 7
8 | Application Development (Proponent Time) | Assessment | EA Act (2018) | 1096 | FALSE | #6d7274 | REGULAR | 8
9 | Application Review | Assessment | EA Act (2018) | 180 | TRUE | #4d95d0 | REGULAR | 9
10 | Revised Application Development (Proponent Time) | Assessment | EA Act (2018) | 365 | FALSE | #6d7274 | REGULAR | 10
11 | Effects Assessment & Recommendation | Assessment | EA Act (2018) | 150 | TRUE | #e7a913 | REGULAR | 11
12 | Decision | Assessment | EA Act (2018) | 30 | TRUE | #6a54a3 | REGULAR | 12

## Events
No | Parent | PhaseNo | EventName | Phase | EventType | EventCategory | EventPosition | MultipleDays | StartAt | NumberOfDays | Visibility | Mandatory | SortOrder
1 |  | 1 | Initial Contact with Proponent | Pre-Early Engagement | Meeting | Milestone | START | FALSE | 0 | 0 | MANDATORY | TRUE | 1
2 |  | 1 | Project Presentation Meeting | Pre-Early Engagement | Meeting | Milestone | INTERMEDIATE | FALSE | 28 | 0 | MANDATORY | TRUE | 2
3 |  | 1 | Capacity Funding Estimate | Pre-Early Engagement | Capacity Funding | Finance | INTERMEDIATE | FALSE | 60 | 0 | MANDATORY | TRUE | 3
4 | 3 | 1 | Capacity Funding Estimate Due | Pre-Early Engagement | Financial | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 4
5 |  | 1 | Submission of "Draft" Initial Project Description & Engagement Plan | Pre-Early Engagement | Submission | Milestone | INTERMEDIATE | FALSE | 80 | 0 | MANDATORY | TRUE | 5
6 |  | 1 | Draft IPD/EP Approval Milestone Bullet | Pre-Early Engagement | Generic | Milestone | INTERMEDIATE | FALSE | 85 | 0 | MANDATORY | TRUE | 6
7 | 6 | 1 | REMINDER: Draft IPD/EP Approval Milestone Bullet | Pre-Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 7
8 |  | 1 | "Draft" Initial Project Description & Engagement Plan Initial Review | Pre-Early Engagement | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 90 | 0 | MANDATORY | TRUE | 8
9 |  | 1 | Additional Information Submission | Pre-Early Engagement | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 9
10 |  | 1 | Project Transitioning FROM the EA Act (2002) | Pre-Early Engagement | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 10
11 | 10 | 1 | Project Transitions to 2018 Act Announcement & Tweet | Pre-Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 11
12 | 10 | 1 | Project Transitions to 2018 Act Milestone Bullet | Pre-Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 12
13 |  | 1 | Project Withdrawn | Pre-Early Engagement | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 13
14 |  | 1 | Other | Pre-Early Engagement | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 14
15 |  | 1 | Last Day of Pre-Early Engagement (Date Capture Milestone) | Pre-Early Engagement | Date Capture | Milestone | END | FALSE | 90 | 0 | MANDATORY | TRUE | 15
16 |  | 2 | Approval of IPD/EP Submission | Early Engagement | Submission | Milestone | START | FALSE | 0 | 0 | MANDATORY | TRUE | 16
17 | 16 | 2 | Approval of IPD/EP Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 17
18 | 16 | 2 | Approval of IPD/EP Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 18
19 |  | 2 | Notification sent to potential PINs | Early Engagement | Notification | Milestone | INTERMEDIATE | FALSE | 7 | 0 | MANDATORY | TRUE | 19
20 |  | 2 | Comment Period | Early Engagement | Comment Period | PCP | INTERMEDIATE | TRUE | 14 | 30 | MANDATORY | TRUE | 20
21 | 20 | 2 | PCP Coming Soon Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | MANDATORY | TRUE | 21
22 | 20 | 2 | PCP Coming Soon Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | MANDATORY | TRUE | 22
23 | 20 | 2 | PCP Now Open Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 23
24 | 20 | 2 | PCP Ending Soon Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | MANDATORY | TRUE | 24
25 |  | 2 | Early Engagement Capacity Funding Amounts Confirmed | Early Engagement | Capacity Funding | Finance | INTERMEDIATE | FALSE | 21 | 0 | MANDATORY | TRUE | 25
26 | 25 | 2 | Early Engagement Capacity Funding Confirmation Due | Early Engagement | Financial | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 26
27 |  | 2 | Fee Order: Filing of IPD | Early Engagement | Fee Order | Finance | INTERMEDIATE | FALSE | 30 | 0 | MANDATORY | TRUE | 27
28 | 27 | 2 | Filing the IPD Fee Order | Early Engagement | Financial | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 28
29 |  | 2 | PIN Notice of Intent Completed | Early Engagement | Generic | Milestone | INTERMEDIATE | FALSE | 80 | 0 | MANDATORY | TRUE | 29
30 |  | 2 | Draft SoE Milestone Bullet | Early Engagement | Generic | Milestone | INTERMEDIATE | FALSE | 85 | 0 | MANDATORY | TRUE | 30
31 | 30 | 2 | REMINDER: Draft SoE Milestone Bullet Due | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 31
32 |  | 2 | Additional Information Submission | Early Engagement | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 32
33 |  | 2 | Federal Involvement Request | Early Engagement | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 33
34 | 33 | 2 | Federal Involvement Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 34
35 |  | 2 | Dispute Resolution Triggered | Early Engagement | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 35
36 | 35 | 2 | DR Triggered Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 36
37 | 35 | 2 | Dispute Resolution Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 37
38 |  | 2 | Additional Comment Period | Early Engagement | Comment Period | PCP | INTERMEDIATE | TRUE | 0 | 30 | OPTIONAL | FALSE | 38
39 | 38 | 2 | PCP Coming Soon Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | FALSE | 39
40 | 38 | 2 | Additional PCP Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | FALSE | 40
41 | 38 | 2 | PCP Now Open Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 41
42 | 38 | 2 | PCP Ending Soon Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | OPTIONAL | FALSE | 42
43 |  | 2 | Open House | Early Engagement | Open House | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 43
44 |  | 2 | Virtual Information Session | Early Engagement | Virtual Information Session | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 44
45 |  | 2 | Comment Period Time Limit Extension | Early Engagement | PCP Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | FALSE | 45
46 | 45 | 2 | PCP Extended Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 46
47 | 45 | 2 | PCP Extended Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 47
48 |  | 2 | s.38 Extension of Time Limit | Early Engagement | Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | FALSE | 48
49 | 48 | 2 | Extension Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 49
50 | 48 | 2 | Time Limit Extended Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 50
52 | 51 | 2 | EAC Assessment Process Suspension Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 52
53 | 51 | 2 | EAC Assessment Process Suspended Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 53
55 | 54 | 2 | EAC Assessment Process Resumption Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 55
56 | 54 | 2 | EAC Assessment Process Resumed Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 56
57 |  | 2 | EAC Assessment Terminated s.39(d) | Early Engagement | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 57
58 | 57 | 2 | Termination Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 58
59 | 57 | 2 | EAC Assessment Terminated Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 59
60 |  | 2 | Project Withdrawn | Early Engagement | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 60
61 | 60 | 2 | Withdrawal Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 61
62 | 60 | 2 | Project Withdrawn Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 62
63 |  | 2 | Other | Early Engagement | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 63
64 |  | 2 | Summary of Engagement | Early Engagement | Report | Milestone | END | FALSE | 90 | 0 | MANDATORY | TRUE | 64
65 | 64 | 2 | Summary of Engagement Announcement & Tweet | Early Engagement | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 65
66 | 64 | 2 | Summary of Engagement Milestone Bullet | Early Engagement | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 66
67 |  | 3 | Start of Detailed Project Description Development | DPD Development (Proponent Time) | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | TRUE | 67
68 |  | 3 | Submission of Detailed Project Description | DPD Development (Proponent Time) | Submission | Milestone | INTERMEDIATE | FALSE | 355 | 0 | MANDATORY | TRUE | 68
69 |  | 3 | Draft DPD Receipt Milestone Bullet | DPD Development (Proponent Time) | Generic | Milestone | INTERMEDIATE | FALSE | 360 | 0 | MANDATORY | TRUE | 69
70 | 69 | 3 | REMINDER: Draft DPD Receipt Milestone Bullet | DPD Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 70
71 |  | 3 | "Draft" Detailed Project Description Initial Review | DPD Development (Proponent Time) | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 365 | 0 | MANDATORY | TRUE | 71
72 |  | 3 | Additional Information Submission | DPD Development (Proponent Time) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 72
73 |  | 3 | Dispute Resolution Triggered | DPD Development (Proponent Time) | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 73
74 | 73 | 3 | DR Triggered Announcement & Tweet | DPD Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 74
75 | 73 | 3 | Dispute Resolution Milestone Bullet | DPD Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 75
76 |  | 3 | EAC Assessment Terminated s.39(d) | DPD Development (Proponent Time) | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 76
77 | 76 | 3 | Termination Announcement & Tweet | DPD Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 77
78 | 767 | 3 | EAC Assessment Terminated Milestone Bullet | DPD Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 78
79 |  | 3 | Project Withdrawn | DPD Development (Proponent Time) | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 79
80 | 79 | 3 | Withdrawal Announcement & Tweet | DPD Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 80
81 | 79 | 3 | Project Withdrawn Milestone Bullet | DPD Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 81
82 |  | 3 | Other | DPD Development (Proponent Time) | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 82
83 |  | 3 | Last Day of DPD Development (Proponent Time) (Date Capture Milestone) | DPD Development (Proponent Time) | Date Capture | Milestone | END | FALSE | 365 | 0 | MANDATORY | TRUE | 83
84 |  | 4 | Detailed Project Description Received | Readiness Decision | Submission | Milestone | START | FALSE | 0 | 0 | MANDATORY | TRUE | 84
85 | 84 | 4 | DPD Received Announcement & Tweet | Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 85
86 | 84 | 4 | DPD Received Milestone Bullet | Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 86
87 |  | 4 | Fee Order: Submission of DPD | Readiness Decision | Fee Order | Finance | INTERMEDIATE | FALSE | 30 | 0 | MANDATORY | TRUE | 87
88 | 87 | 4 | Fee Order Issued | Readiness Decision | Financial | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 88
89 |  | 4 | Report referred to CEAO | Readiness Decision | Referral | Milestone | INTERMEDIATE | FALSE | 50 | 0 | MANDATORY | TRUE | 89
90 |  | 4 | Draft Readiness Decision Milestone Bullet | Readiness Decision | Generic | Milestone | INTERMEDIATE | FALSE | 55 | 0 | MANDATORY | TRUE | 90
91 | 90 | 4 | REMINDER: Draft Readiness Decision Milestone Bullet | Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 91
92 |  | 4 | Additional Information Submission | Readiness Decision | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 92
93 |  | 4 | Dispute Resolution Triggered | Readiness Decision | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 93
94 | 93 | 4 | DR Triggered Announcement & Tweet | Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 94
95 | 93 | 4 | Dispute Resolution Milestone Bullet | Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 95
96 |  | 4 | EAC Assessment Terminated s.39(d) | Readiness Decision | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 96
97 | 96 | 4 | Termination Announcement & Tweet | Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 97
98 | 96 | 4 | EAC Assessment Terminated Milestone Bullet | Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 98
99 |  | 4 | Project Withdrawn | Readiness Decision | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 99
100 | 99 | 4 | Withdrawal Announcement & Tweet | Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 100
101 | 99 | 4 | Project Withdrawn Milestone Bullet | Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 101
102 |  | 4 | Other | Readiness Decision | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 102
103 |  | 4 | Termination Package Referred to Minister | Readiness Decision | Report | Milestone | INTERMEDIATE | FALSE | 0 | 0 | HIDDEN | FALSE | 103
104 |  | 4 | Last Day of EAC Assessment Readiness Decision (Date Capture Milestone) | Readiness Decision | Date Capture | Milestone | INTERMEDIATE | FALSE | 0 | 0 | HIDDEN | FALSE | 104
105 |  | 4 | Decision: Readiness Decision | Readiness Decision | CEAO | Decision | END | FALSE | 60 | 0 | MANDATORY | TRUE | 105
106 | 105 | 4 | Readiness Decision Announcement & Tweet | Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 106
107 | 105 | 4 | Readiness Decision Milestone Bullet (if Project proceeds to Process Planning) | Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 107
108 |  | 5 | Termination Decision Package Received by Minister | Termination Decision | Referral | Milestone | START | FALSE | 0 | 0 | MANDATORY | TRUE | 108
109 |  | 5 | Additional Information Submission | Termination Decision | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 109
110 |  | 5 | EAC Assessment Terminated s.39(d) | Termination Decision | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 110
111 | 110 | 5 | Termination Announcement & Tweet | Termination Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 111
112 | 110 | 5 | EAC Assessment Terminated Milestone Bullet | Termination Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 112
113 |  | 5 | Project Withdrawn | Termination Decision | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 113
114 | 113 | 5 | Withdrawal Announcement & Tweet | Termination Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 114
115 | 113 | 5 | Project Withdrawn Milestone Bullet | Termination Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 115
116 |  | 5 | Other | Termination Decision | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 116
117 |  | 5 | Minister's Termination Decision | Termination Decision | Minister | Decision | END | FALSE | 30 | 0 | MANDATORY | TRUE | 117
118 | 117 | 5 | Termination Decision Announcement & Tweet (unless return to CEAO) | Termination Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 118
119 |  | 6 | Readiness Decision Report referred to CEAO for Further Decision | Further Readiness Decision | Referral | Milestone | START | FALSE | 0 | 0 | MANDATORY | TRUE | 119
120 |  | 6 | Additional Information Submission | Further Readiness Decision | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 120
121 |  | 6 | EAC Assessment Terminated s.39(d) | Further Readiness Decision | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 121
122 | 121 | 6 | Termination Announcement & Tweet | Further Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 122
123 | 121 | 6 | EAC Assessment Terminated Milestone Bullet | Further Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 123
124 |  | 6 | Project Withdrawn | Further Readiness Decision | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 124
125 | 124 | 6 | Withdrawal Announcement & Tweet | Further Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 125
126 | 124 | 6 | Project Withdrawn Milestone Bullet | Further Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 126
127 |  | 6 | Other | Further Readiness Decision | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 127
128 |  | 6 | Last Day of EAC Assessment Further Readiness Decision (Date Capture Milestone) | Further Readiness Decision | Date Capture | Milestone | INTERMEDIATE | FALSE | 0 | 0 | HIDDEN | FALSE | 128
129 |  | 6 | Decision: Further Readiness Decision | Further Readiness Decision | CEAO | Decision | END | FALSE | 60 | 0 | MANDATORY | TRUE | 129
130 | 129 | 6 | Further Readiness Decision Announcement & Tweet | Further Readiness Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 130
131 | 129 | 6 | Further Readiness Decision Milestone Bullet (if Project proceeds to Process Planning) | Further Readiness Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 131
132 |  | 7 | Start of Process Planning (Date Capture Milestone) | Process Planning | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | TRUE | 132
133 |  | 7 | Federal Involvement Decision | Process Planning | Federal | Decision | INTERMEDIATE | FALSE | 30 | 0 | MANDATORY | TRUE | 133
134 |  | 7 | Federal Involvement Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 134
135 |  | 7 | Federal Involvement Milestone Bullet | Process Planning | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 135
136 |  | 7 | Draft Process Order Shared | Process Planning | Generic | Milestone | INTERMEDIATE | FALSE | 45 | 0 | MANDATORY | TRUE | 136
137 |  | 7 | Comment Period | Process Planning | Comment Period | PCP | INTERMEDIATE | TRUE | 60 | 30 | MANDATORY | TRUE | 137
138 | 137 | 7 | PCP Coming Soon Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | MANDATORY | TRUE | 138
139 | 137 | 7 | PCP Coming Soon Milestone Bullet | Process Planning | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | MANDATORY | TRUE | 139
140 | 137 | 7 | PCP Now Open Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 140
141 | 137 | 7 | PCP Ending Soon Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | MANDATORY | TRUE | 141
142 |  | 7 | Formally Establish TAC | Process Planning | Generic | Milestone | INTERMEDIATE | FALSE | 100 | 0 | MANDATORY | TRUE | 142
143 |  | 7 | Draft Process Order Milestone Bullet | Process Planning | Generic | Milestone | INTERMEDIATE | FALSE | 115 | 0 | MANDATORY | TRUE | 143
144 | 143 | 7 | REMINDER: Process Order Milestone Bullet Due | Process Planning | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 144
145 |  | 7 | Additional Information Submission | Process Planning | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 145
146 |  | 7 | Section 19.4 Assessment - PIN Assessment Request | Process Planning | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 146
147 |  | 7 | Summary of Engagement Report Issued | Process Planning | Report | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 147
148 |  | 7 | Establish CAC(s) | Process Planning | Generic | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 148
149 |  | 7 | Dispute Resolution Triggered | Process Planning | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 149
150 | 149 | 7 | DR Triggered Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 150
151 | 149 | 7 | Dispute Resolution Milestone Bullet | Process Planning | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 151
152 |  | 7 | Additional Comment Period | Process Planning | Comment Period | PCP | INTERMEDIATE | TRUE | 0 | 30 | OPTIONAL | FALSE | 152
153 | 152 | 7 | PCP Coming Soon Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | FALSE | 153
154 | 152 | 7 | Additional PCP Milestone Bullet | Process Planning | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | FALSE | 154
155 | 152 | 7 | PCP Now Open Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 155
156 | 152 | 7 | PCP Ending Soon Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | OPTIONAL | FALSE | 156
157 |  | 7 | Open House | Process Planning | Open House | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 157
158 |  | 7 | Virtual Information Session | Process Planning | Virtual Information Session | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 158
159 |  | 7 | Comment Period Time Limit Extension | Process Planning | PCP Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | FALSE | 159
160 | 159 | 7 | PCP Extended Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 160
161 | 159 | 7 | PCP Extended Milestone Bullet | Process Planning | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 161
162 |  | 7 | s.38 Extension of Time Limit | Process Planning | Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | FALSE | 162
163 | 162 | 7 | Extension Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 163
164 | 162 | 7 | Time Limit Extended Milestone Bullet | Process Planning | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 164
166 | 165 | 7 | EAC Assessment Process Suspension Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 166
167 | 165 | 7 | EAC Assessment Process Suspended Milestone Bullet | Process Planning | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 167
169 | 168 | 7 | EAC Assessment Process Resumption Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 169
170 | 168 | 7 | EAC Assessment Process Resumed Milestone Bullet | Process Planning | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 170
171 |  | 7 | EAC Assessment Terminated s.39(d) | Process Planning | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 171
172 | 171 | 7 | Termination Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 172
173 | 171 | 7 | EAC Assessment Terminated Milestone Bullet | Process Planning | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 173
174 |  | 7 | Project Withdrawn | Process Planning | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 174
175 | 174 | 7 | Withdrawal Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 175
176 | 174 | 7 | Project Withdrawn Milestone Bullet | Process Planning | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 176
177 |  | 7 | Other | Process Planning | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 177
178 |  | 7 | Process Order Issued & Regulatory Coordination Plan Posted | Process Planning | Report | Milestone | END | FALSE | 120 | 0 | MANDATORY | TRUE | 178
179 | 178 | 7 | Process Order Announcement & Tweet | Process Planning | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 179
180 | 178 | 7 | Process Order Milestone Bullet | Process Planning | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 180
181 |  | 8 | Start of Application Development (Date Capture Milestone) | Application Development (Proponent Time) | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | TRUE | 181
182 |  | 8 | Submission of EAC Application | Application Development (Proponent Time) | Submission | Milestone | INTERMEDIATE | FALSE | 1085 | 0 | MANDATORY | TRUE | 182
183 |  | 8 | Draft EAC Application Receipt Milestone Bullet | Application Development (Proponent Time) | Generic | Milestone | INTERMEDIATE | FALSE | 1090 | 0 | MANDATORY | TRUE | 183
184 | 183 | 8 | REMINDER: Draft EAC Application Receipt Milestone Bullet | Application Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 1096 | 0 | MANDATORY | TRUE | 184
185 |  | 8 | "Draft" EAC Application Initial Review | Application Development (Proponent Time) | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 1096 | 0 | MANDATORY | TRUE | 185
186 |  | 8 | Additional Information Submission | Application Development (Proponent Time) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 186
187 |  | 8 | Modification of Process Order | Application Development (Proponent Time) | Order | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 187
188 | 187 | 8 | Modification of Process Order Announcement & Tweet | Application Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 188
189 |  | 8 | Dispute Resolution Triggered | Application Development (Proponent Time) | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 189
190 | 189 | 8 | DR Triggered Announcement & Tweet | Application Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 190
191 | 189 | 8 | Dispute Resolution Milestone Bullet | Application Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 191
192 |  | 8 | EAC Assessment Terminated s.39(d) | Application Development (Proponent Time) | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 192
193 | 192 | 8 | Termination Announcement & Tweet | Application Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 193
194 | 192 | 8 | EAC Assessment Terminated Milestone Bullet | Application Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 194
195 |  | 8 | Project Withdrawn | Application Development (Proponent Time) | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 195
196 | 195 | 8 | Withdrawal Announcement & Tweet | Application Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 196
197 | 195 | 8 | Project Withdrawn Milestone Bullet | Application Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 197
198 |  | 8 | Other | Application Development (Proponent Time) | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 198
199 |  | 8 | Last Day of Application Development (Date Capture Milestone) | Application Development (Proponent Time) | Date Capture | Milestone | END | FALSE | 1096 | 0 | MANDATORY | TRUE | 199
200 |  | 9 | EAC Application Received | Application Review | Submission | Milestone | START | FALSE | 0 | 0 | MANDATORY | TRUE | 200
201 | 200 | 9 | EAC Application Received Announcement & Tweet | Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 201
202 | 200 | 9 | EAC Application Received Milestone Bullet | Application Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 202
203 |  | 9 | Comment Period | Application Review | Comment Period | PCP | INTERMEDIATE | TRUE | 14 | 30 | MANDATORY | TRUE | 203
204 | 203 | 9 | PCP Coming Soon Announcement & Tweet | Application Review | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | MANDATORY | TRUE | 204
205 | 203 | 9 | PCP Coming Soon Milestone Bullet | Application Review | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | MANDATORY | TRUE | 205
206 | 203 | 9 | PCP Now Open Announcement & Tweet | Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 206
207 | 203 | 9 | PCP Ending Soon Announcement & Tweet | Application Review | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | MANDATORY | TRUE | 207
208 |  | 9 | Fee Order: Filing of the EAC Application | Application Review | Fee Order | Finance | INTERMEDIATE | FALSE | 30 | 0 | MANDATORY | TRUE | 208
209 | 208 | 9 | Filing the EAC Application Fee Order | Application Review | Financial | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 209
210 |  | 9 | Draft Revised Application Milestone Bullet | Application Review | Generic | Milestone | INTERMEDIATE | FALSE | 175 | 0 | MANDATORY | TRUE | 210
211 | 210 | 9 | REMINDER: Revised Application Milestone Bullet Due | Application Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 211
212 |  | 9 | Additional Information Submission | Application Review | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 212
213 |  | 9 | Modification of Process Order | Application Review | Order | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 213
214 | 213 | 9 | Modification of Process Order Announcement & Tweet | Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 214
215 |  | 9 | Dispute Resolution Triggered | Application Review | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 215
216 | 215 | 9 | DR Triggered Announcement & Tweet | Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 216
217 | 215 | 9 | Dispute Resolution Milestone Bullet | Application Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 217
218 |  | 9 | Additional Comment Period | Application Review | Comment Period | PCP | INTERMEDIATE | TRUE | 0 | 30 | OPTIONAL | FALSE | 218
219 | 218 | 9 | PCP Coming Soon Announcement & Tweet | Application Review | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | FALSE | 219
220 | 218 | 9 | Additional PCP Milestone Bullet | Application Review | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | FALSE | 220
221 | 218 | 9 | PCP Now Open Announcement & Tweet | Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 221
222 | 218 | 9 | PCP Ending Soon Announcement & Tweet | Application Review | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | OPTIONAL | FALSE | 222
223 |  | 9 | Open House | Application Review | Open House | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 223
224 |  | 9 | Virtual Information Session | Application Review | Virtual Information Session | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 224
225 |  | 9 | Comment Period Time Limit Extension | Application Review | PCP Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | FALSE | 225
226 | 225 | 9 | PCP Extended Announcement & Tweet | Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 226
227 | 225 | 9 | PCP Extended Milestone Bullet | Application Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 227
228 |  | 9 | s.38 Extension of Time Limit | Application Review | Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | FALSE | 228
229 | 228 | 9 | Extension Announcement & Tweet | Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 229
230 | 228 | 9 | Time Limit Extended Milestone Bullet | Application Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 230
232 | 231 | 9 | EAC Assessment Process Suspension Announcement & Tweet | Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 232
233 | 231 | 9 | EAC Assessment Process Suspended Milestone Bullet | Application Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 233
235 | 234 | 9 | EAC Assessment Process Resumption Announcement & Tweet | Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 235
236 | 234 | 9 | EAC Assessment Process Resumed Milestone Bullet | Application Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 236
237 |  | 9 | EAC Assessment Terminated s.39(d) | Application Review | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 237
238 | 237 | 9 | Termination Announcement & Tweet | Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 238
239 | 237 | 9 | EAC Assessment Terminated Milestone Bullet | Application Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 239
240 |  | 9 | Project Withdrawn | Application Review | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 240
241 | 240 | 9 | Withdrawal Announcement & Tweet | Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 241
242 | 240 | 9 | Project Withdrawn Milestone Bullet | Application Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 242
243 |  | 9 | Other | Application Review | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 243
244 |  | 9 | Notice to Proponent to Prepare Revised EAC Application | Application Review | Report | Milestone | END | FALSE | 180 | 0 | MANDATORY | TRUE | 244
245 | 244 | 9 | Notice of Revised EAC Application Announcement & Tweet | Application Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 245
246 | 244 | 9 | Notice of Revised EAC Application Milestone Bullet | Application Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 246
247 |  | 10 | Start of Revised Application Development (Date Capture Milestone) | Revised Application Development (Proponent Time) | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | TRUE | 247
248 |  | 10 | Submission of Revised EAC Application | Revised Application Development (Proponent Time) | Submission | Milestone | INTERMEDIATE | FALSE | 355 | 0 | MANDATORY | TRUE | 248
249 |  | 10 | Draft Revised EAC Application Receipt Milestone Bullet | Revised Application Development (Proponent Time) | Generic | Milestone | INTERMEDIATE | FALSE | 360 | 0 | MANDATORY | TRUE | 249
250 | 249 | 10 | REMINDER: Draft Revised EAC Application Receipt Milestone Bullet | Revised Application Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 250
251 |  | 10 | "Draft" Revised EAC Application Initial Review | Revised Application Development (Proponent Time) | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 365 | 0 | MANDATORY | TRUE | 251
252 |  | 10 | Additional Information Submission | Revised Application Development (Proponent Time) | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 252
253 |  | 10 | Modification of Process Order | Revised Application Development (Proponent Time) | Order | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 253
254 | 253 | 10 | Modification of Process Order Announcement & Tweet | Revised Application Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 254
255 |  | 10 | Dispute Resolution Triggered | Revised Application Development (Proponent Time) | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 255
256 | 255 | 10 | DR Triggered Announcement & Tweet | Revised Application Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 256
257 | 255 | 10 | Dispute Resolution Milestone Bullet | Revised Application Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 257
258 |  | 10 | EAC Assessment Terminated s.39(d) | Revised Application Development (Proponent Time) | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 258
259 | 258 | 10 | Termination Announcement & Tweet | Revised Application Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 259
260 | 258 | 10 | EAC Assessment Terminated Milestone Bullet | Revised Application Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 260
261 |  | 10 | Project Withdrawn | Revised Application Development (Proponent Time) | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 261
262 | 261 | 10 | Withdrawal Announcement & Tweet | Revised Application Development (Proponent Time) | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 262
263 | 261 | 10 | Project Withdrawn Milestone Bullet | Revised Application Development (Proponent Time) | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 263
264 |  | 10 | Other | Revised Application Development (Proponent Time) | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 264
265 |  | 10 | Last Day of Revised Application Development (Date Capture Milestone) | Revised Application Development (Proponent Time) | Date Capture | Milestone | END | FALSE | 365 | 0 | MANDATORY | TRUE | 265
266 |  | 11 | Revised EAC Application Accepted | Effects Assessment & Recommendation | Submission | Milestone | START | FALSE | 0 | 0 | MANDATORY | TRUE | 266
267 | 266 | 11 | Revised EAC Application Accepted Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 267
268 | 266 | 11 | Revised EAC Application Accepted Milestone Bullet | Effects Assessment & Recommendation | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 268
269 |  | 11 | Draft Assessment Report & Draft Certificate Posted | Effects Assessment & Recommendation | Report | Milestone | INTERMEDIATE | FALSE | 90 | 0 | MANDATORY | TRUE | 269
270 |  | 11 | Comment Period | Effects Assessment & Recommendation | Comment Period | PCP | INTERMEDIATE | TRUE | 104 | 30 | MANDATORY | TRUE | 270
271 | 270 | 11 | PCP Coming Soon Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | MANDATORY | TRUE | 271
272 | 270 | 11 | PCP Coming Soon Milestone Bullet | Effects Assessment & Recommendation | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | MANDATORY | TRUE | 272
273 | 270 | 11 | PCP Now Open Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 273
274 | 270 | 11 | PCP Ending Soon Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | MANDATORY | TRUE | 274
275 |  | 11 | Draft Memo to Ministers | Effects Assessment & Recommendation | Generic | Milestone | INTERMEDIATE | FALSE | 130 | 0 | MANDATORY | TRUE | 275
276 | 275 | 11 | REMINDER: Draft Memo to Ministers | Effects Assessment & Recommendation | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 276
277 |  | 11 | Additional Information Submission | Effects Assessment & Recommendation | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 277
278 |  | 11 | Modification of Process Order | Effects Assessment & Recommendation | Order | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 278
279 | 278 | 11 | Modification of Process Order Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 279
280 |  | 11 | Dispute Resolution Triggered | Effects Assessment & Recommendation | Request | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 280
281 | 280 | 11 | DR Triggered Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 281
282 | 280 | 11 | Dispute Resolution Milestone Bullet | Effects Assessment & Recommendation | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 282
283 |  | 11 | Additional Comment Period | Effects Assessment & Recommendation | Comment Period | PCP | INTERMEDIATE | TRUE | 0 | 30 | OPTIONAL | FALSE | 283
284 | 283 | 11 | PCP Coming Soon Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | FALSE | 284
285 | 283 | 11 | Additional PCP Milestone Bullet | Effects Assessment & Recommendation | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | FALSE | 285
286 | 283 | 11 | PCP Now Open Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 286
287 | 283 | 11 | PCP Ending Soon Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | OPTIONAL | FALSE | 287
288 |  | 11 | Open House | Effects Assessment & Recommendation | Open House | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 288
289 |  | 11 | Virtual Information Session | Effects Assessment & Recommendation | Virtual Information Session | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 289
290 |  | 11 | Comment Period Time Limit Extension | Effects Assessment & Recommendation | PCP Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | FALSE | 290
291 | 290 | 11 | PCP Extended Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 291
292 | 290 | 11 | PCP Extended Milestone Bullet | Effects Assessment & Recommendation | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 292
293 |  | 11 | s.38 Extension of Time Limit | Effects Assessment & Recommendation | Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | FALSE | 293
294 | 293 | 11 | Extension Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 294
295 | 293 | 11 | Time Limit Extended Milestone Bullet | Effects Assessment & Recommendation | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 295
297 | 296 | 11 | EAC Assessment Process Suspension Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 297
298 | 296 | 11 | EAC Assessment Process Suspended Milestone Bullet | Effects Assessment & Recommendation | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 298
300 | 299 | 11 | EAC Assessment Process Resumption Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 300
301 | 299 | 11 | EAC Assessment Process Resumed Milestone Bullet | Effects Assessment & Recommendation | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 301
302 |  | 11 | EAC Assessment Terminated s.39(d) | Effects Assessment & Recommendation | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 302
303 | 302 | 11 | Termination Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 303
304 | 302 | 11 | EAC Assessment Terminated Milestone Bullet | Effects Assessment & Recommendation | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 304
305 |  | 11 | Project Withdrawn | Effects Assessment & Recommendation | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 305
306 | 305 | 11 | Withdrawal Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 306
307 | 305 | 11 | Project Withdrawn Milestone Bullet | Effects Assessment & Recommendation | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 307
308 |  | 11 | Other | Effects Assessment & Recommendation | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 308
309 |  | 11 | EAC Referral Package sent to Ministers | Effects Assessment & Recommendation | Referral | Milestone | END | FALSE | 150 | 0 | MANDATORY | TRUE | 309
310 | 309 | 11 | Completion of Assessment and Referral to Minister Announcement & Tweet | Effects Assessment & Recommendation | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 310
311 |  | 12 | Referral Package Received by Ministers | Decision | Report | Milestone | START | FALSE | 0 | 0 | MANDATORY | TRUE | 311
312 |  | 12 | Additional Information Submission | Decision | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 312
313 |  | 12 | Ministers Meeting | Decision | Meeting | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 313
314 |  | 12 | s.38 Extension of Time Limit | Decision | Time Limit Extension | Extension | INTERMEDIATE | TRUE | 0 | 0 | OPTIONAL | FALSE | 314
315 | 314 | 12 | Extension Announcement & Tweet | Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 315
316 | 314 | 12 | Time Limit Extended Milestone Bullet | Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 316
318 | 317 | 12 | EAC Assessment Process Suspension Announcement & Tweet | Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 318
319 | 317 | 12 | EAC Assessment Process Suspended Milestone Bullet | Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 319
321 | 320 | 12 | EAC Assessment Process Resumption Announcement & Tweet | Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 321
322 | 320 | 12 | EAC Assessment Process Resumed Milestone Bullet | Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 322
323 |  | 12 | Project Withdrawn | Decision | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 323
324 | 323 | 12 | Withdrawal Announcement & Tweet | Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 324
325 | 323 | 12 | Project Withdrawn Milestone Bullet | Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 325
326 |  | 12 | Other | Decision | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | FALSE | 326
327 |  | 12 | EAC Ministers Decision | Decision | EAC Ministers | Decision | END | FALSE | 30 | 0 | MANDATORY | TRUE | 327
328 | 327 | 12 | EAC Decision Announcement & Tweet | Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | TRUE | 328

## Outcomes
No | TemplateNo | TemplateName | OutcomeName | SortOrder
1 | 8 | "Draft" Initial Project Description & Engagement Plan Initial Review | Draft Initial Project Description Initial Review is POSITIVE | 1
2 | 8 | "Draft" Initial Project Description & Engagement Plan Initial Review | Draft Initial Project Description Initial Review is NEGATIVE | 2
4 | 10 | Project Transitioning FROM the EA Act (2002) | EAC Assessment Transitions to the EA Act (2018) Readiness Decision PHASE | 4
5 | 10 | Project Transitioning FROM the EA Act (2002) | EAC Assessment Transitions to the EA Act (2018) Process Planning PHASE | 5
6 | 10 | Project Transitioning FROM the EA Act (2002) | EAC Assessment Transitions to the EA Act (2018) Application Review PHASE | 6
7 | 10 | Project Transitioning FROM the EA Act (2002) | EAC Assessment Transitions to the EA Act (2018) Effects Assessment & Recommendation PHASE | 7
8 | 13 | Project Withdrawn | Proponent withdraws Submission from the EAC Assessment process | 8
9 | 16 | Approval of IPD/EP Submission | Starts the "clock" for EAC Assessment | 9
10 | 35 | Dispute Resolution Triggered | Dispute Resolution is started | 10
11 | 57 | EAC Assessment Terminated s.39(d) | EAC Assessment is Terminated under s.39(d) of Act | 11
12 | 60 | Project Withdrawn | Proponent withdraws Project from EA process | 12
13 | 64 | Summary of Engagement | End of EAC Assessment: Early Engagement, start of EAC Assessment: DPD Development (Proponent Time) | 13
14 | 71 | "Draft" Detailed Project Description Initial Review | Draft Detailed Project Description Initial Review is POSITIVE | 14
15 | 71 | "Draft" Detailed Project Description Initial Review | Draft Detailed Project Description Initial Review is NEGATIVE | 15
16 | 73 | Dispute Resolution Triggered | Dispute Resolution is started | 16
17 | 76 | EAC Assessment Terminated s.39(d) | EAC Assessment is Terminated under s.39(d) of Act | 17
18 | 79 | Project Withdrawn | Proponent withdraws Project from EA process | 18
19 | 93 | Dispute Resolution Triggered | Dispute Resolution is started | 19
20 | 96 | EAC Assessment Terminated s.39(d) | EAC Assessment is Terminated under s.39(d) of Act | 20
21 | 99 | Project Withdrawn | Proponent withdraws Project from EA process | 21
22 | 105 | Decision: Readiness Decision | Proponent must submit a Revised DPD | 22
23 | 105 | Decision: Readiness Decision | Project moves to Process Planning | 23
24 | 105 | Decision: Readiness Decision | Project is Referred to Minister for Termination | 24
25 | 105 | Decision: Readiness Decision | Refer for Minister's Process Planning | 25
26 | 110 | EAC Assessment Terminated s.39(d) | EAC Assessment is Terminated under s.39(d) of Act | 26
27 | 113 | Project Withdrawn | Proponent withdraws Project from EA process | 27
28 | 117 | Minister's Termination Decision | Project is Terminated | 28
29 | 117 | Minister's Termination Decision | Refer the Project to the CEAO for Further Decision | 29
30 | 121 | EAC Assessment Terminated s.39(d) | EAC Assessment is Terminated under s.39(d) of Act | 30
31 | 124 | Project Withdrawn | Proponent withdraws Project from EA process | 31
32 | 129 | Decision: Further Readiness Decision | Proponent must submit a Revised DPD | 32
33 | 129 | Decision: Further Readiness Decision | Project moves to Process Planning | 33
34 | 129 | Decision: Further Readiness Decision | Refer for Minister's Process Planning | 34
35 | 133 | Federal Involvement Decision | Set federalInvolvement to "None" | 35
36 | 133 | Federal Involvement Decision | Unknown QQQ (how to set federalInvolvement properly) | 36
37 | 133 | Federal Involvement Decision | Set federalInvolvement to "None" | 37
38 | 149 | Dispute Resolution Triggered | Dispute Resolution is started | 38
39 | 171 | EAC Assessment Terminated s.39(d) | EAC Assessment is Terminated under s.39(d) of Act | 39
40 | 174 | Project Withdrawn | Proponent withdraws Project from EA process | 40
41 | 178 | Process Order Issued & Regulatory Coordination Plan Posted | End of EAC Assessment: Process Planning PHASE, start of EAC Assessment: DPD Development (Proponent Time) PHASE | 41
42 | 185 | "Draft" EAC Application Initial Review | "Draft" EAC Application Initial Review is POSITIVE | 42
43 | 185 | "Draft" EAC Application Initial Review | "Draft" EAC Application Initial Review is NEGATIVE | 43
44 | 189 | Dispute Resolution Triggered | Dispute Resolution is started | 44
45 | 192 | EAC Assessment Terminated s.39(d) | EAC Assessment is Terminated under s.39(d) of Act | 45
46 | 195 | Project Withdrawn | Proponent withdraws Project from EA process | 46
47 | 215 | Dispute Resolution Triggered | Dispute Resolution is started | 47
48 | 237 | EAC Assessment Terminated s.39(d) | EAC Assessment is Terminated under s.39(d) of Act | 48
49 | 240 | Project Withdrawn | Proponent withdraws Project from EA process | 49
50 | 244 | Notice to Proponent to Prepare Revised EAC Application | End of EAC Assessment: Application Review PHASE, start of EAC Assessment: Revised Application Development (Proponent Time) PHASE | 50
51 | 251 | "Draft" Revised EAC Application Initial Review | "Draft" Revised EAC Application Initial Review is POSITIVE | 51
52 | 251 | "Draft" Revised EAC Application Initial Review | "Draft" Revised EAC Application Initial Review is NEGATIVE | 52
53 | 255 | Dispute Resolution Triggered | Dispute Resolution is started | 53
54 | 258 | EAC Assessment Terminated s.39(d) | EAC Assessment is Terminated under s.39(d) of Act | 54
55 | 261 | Project Withdrawn | Proponent withdraws Project from EA process | 55
56 | 280 | Dispute Resolution Triggered | Dispute Resolution is started | 56
57 | 302 | EAC Assessment Terminated s.39(d) | EAC Assessment is Terminated under s.39(d) of Act | 57
58 | 305 | Project Withdrawn | Proponent withdraws Project from EA process | 58
59 | 309 | EAC Referral Package sent to Ministers | End of EAC Assessment: Effects Assessment & Recommendation PHASE, start of EAC Assessment: Decision PHASE | 59
60 | 323 | Project Withdrawn | Proponent withdraws Project from EA process | 60
61 | 327 | EAC Ministers Decision | Environmental Assessment Certificate GRANTED | 61
62 | 327 | EAC Ministers Decision | Environmental Assessment Certificate REFUSED | 62

## Actions
No | OutcomeNo | OutcomeName | ActionName | ActionDescription | AdditionalParams | SortOrder
1 | 1 | Draft Initial Project Description Initial Review is POSITIVE | SetEventDate | Set ANTICIPATED of "Early Engagement ¦ Approval of IPD/EP Submission" to thisEventACTUAL +1 | {"phase_name":"Early Engagement","work_type_id": 6, "ea_act_id": 3, "event_name": "Approval of IPD/EP Submission", "start_at": 1 } | 1
2 | 2 | Draft Initial Project Description Initial Review is NEGATIVE | AddEvent | Add a copy of "Submission of "Draft" Initial Project Description & Engagement Plan, "Draft" Initial Project Description & Engagement Plan Initial Review" to thisPhase at thisEventACTUAL +21 | [{"phase_name":"Pre-Early Engagement","work_type_id": 6, "ea_act_id": 3, "event_name": "Submission of \"Draft\" Initial Project Description & Engagement Plan", "start_at": 21 },{"phase_name":"Pre-Early Engagement","work_type_id": 6, "ea_act_id": 3, "event_name": "\"Draft\" Initial Project Description & Engagement Plan Initial Review", "start_at": 7 }] | 2
5 | 4 | EAC Assessment Transitions to the EA Act (2018) Readiness Decision PHASE | SetPhasesStatus | Set "Early Engagement" PHASE to INACTIVE | [{"phase_name":"Early Engagement","work_type_id": 6, "ea_act_id": 3, "is_active": false }] | 5
6 | 4 | EAC Assessment Transitions to the EA Act (2018) Readiness Decision PHASE | SetEventsStatus | Set "Pre-Early Engagement ¦ Last Day of Pre-Early Engagement" EVENT to INACTIVE | [{"phase_name":"Pre-Early Engagement","work_type_id": 6, "ea_act_id": 3, "event_name": "Last Day of Pre-Early Engagement (Date Capture Milestone)", "is_active": false }] | 6
7 | 4 | EAC Assessment Transitions to the EA Act (2018) Readiness Decision PHASE | ChangePhaseEndEvent | Set "Pre-Early Engagement ¦ Project Transitioning FROM the EA Act (2002)" to PHASE END EVENT | {"phase_name":"Pre-Early Engagement","work_type_id": 6, "ea_act_id": 3, "event_name": "Project Transitioning FROM the EA Act (2002)"} | 7
8 | 4 | EAC Assessment Transitions to the EA Act (2018) Readiness Decision PHASE | SetEventDate | Set "DPD Development (Proponent Time) ¦ Start of Detailed Project Description Development" ACTUAL to thisEventActual +1 | {"phase_name":"DPD Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "event_name": "Start of Detailed Project Description Development", "start_at": 1 } | 8
9 | 5 | EAC Assessment Transitions to the EA Act (2018) Process Planning PHASE | SetPhasesStatus | Set "Early Engagement","DPD Development (Proponent Time),"Readiness Decision" PHASE to INACTIVE | [{"phase_name":"Early Engagement","work_type_id": 6, "ea_act_id": 3, "is_active": false }, {"phase_name":"DPD Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "is_active": false },{"phase_name":"Readiness Decision","work_type_id": 6, "ea_act_id": 3, "is_active": false }] | 9
10 | 5 | EAC Assessment Transitions to the EA Act (2018) Process Planning PHASE | SetEventDate | Set "Pre-Early Engagement ¦ Last Day of Pre-Early Engagement (Date Capture Milestone)" ANTICIPATED to thisEventActual +29 | {"phase_name":"Pre-Early Engagement","work_type_id": 6, "ea_act_id": 3, "event_name": "Last Day of Pre-Early Engagement (Date Capture Milestone)", "start_at": 29 } | 10
11 | 5 | EAC Assessment Transitions to the EA Act (2018) Process Planning PHASE | SetEventDate | Set "Process Planning ¦ Start of Process Planning (Date Capture Milestone)" ANTICIPATED to thisEventActual +30 | {"phase_name":"Process Planning","work_type_id": 6, "ea_act_id": 3, "event_name": "Start of Process Planning (Date Capture Milestone)", "start_at": 30 } | 11
12 | 6 | EAC Assessment Transitions to the EA Act (2018) Application Review PHASE | SetPhasesStatus | Set "Early Engagement","DPD Development (Proponent Time),"Readiness Decision","Process Planning" PHASE to INACTIVE | [{"phase_name":"Early Engagement","work_type_id": 6, "ea_act_id": 3, "is_active": false }, {"phase_name":"DPD Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "is_active": false },{"phase_name":"Readiness Decision","work_type_id": 6, "ea_act_id": 3, "is_active": false },{"phase_name":"Process Planning","work_type_id": 6, "ea_act_id": 3, "is_active": false }] | 12
13 | 6 | EAC Assessment Transitions to the EA Act (2018) Application Review PHASE | SetEventsStatus | Set "Pre-Early Engagement ¦ Last Day of Pre-Early Engagement" EVENT to INACTIVE | [{"phase_name":"Pre-Early Engagement","work_type_id": 6, "ea_act_id": 3, "event_name": "Last Day of Pre-Early Engagement (Date Capture Milestone)", "is_active": false }] | 13
14 | 6 | EAC Assessment Transitions to the EA Act (2018) Application Review PHASE | ChangePhaseEndEvent | Set "Pre-Early Engagement ¦ Project Transitioning FROM the EA Act (2002)" to PHASE END EVENT | {"phase_name":"Pre-Early Engagement","work_type_id": 6, "ea_act_id": 3, "event_name": "Project Transitioning FROM the EA Act (2002)"} | 14
15 | 6 | EAC Assessment Transitions to the EA Act (2018) Application Review PHASE | SetEventDate | Set "Application Development (Proponent Time) ¦ Start of Application Development (Date Capture Milestone)" ACTUAL to thisEventActual +1 | {"phase_name":"Application Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "event_name": "Start of Application Development (Date Capture Milestone)", "start_at": 1 } | 15
16 | 7 | EAC Assessment Transitions to the EA Act (2018) Effects Assessment & Recommendation PHASE | SetPhasesStatus | Set "Early Engagement","DPD Development (Proponent Time),"Readiness Decision","Process Planning" PHASE to INACTIVE | [{"phase_name":"Early Engagement","work_type_id": 6, "ea_act_id": 3, "is_active": false }, {"phase_name":"DPD Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "is_active": false },{"phase_name":"Readiness Decision","work_type_id": 6, "ea_act_id": 3, "is_active": false },{"phase_name":"Process Planning","work_type_id": 6, "ea_act_id": 3, "is_active": false }] | 16
17 | 7 | EAC Assessment Transitions to the EA Act (2018) Effects Assessment & Recommendation PHASE | SetEventsStatus | Set "Pre-Early Engagement ¦ Last Day of Pre-Early Engagement" EVENT to INACTIVE | [{"phase_name":"Pre-Early Engagement","work_type_id": 6, "ea_act_id": 3, "event_name": "Last Day of Pre-Early Engagement (Date Capture Milestone)", "is_active": false }] | 17
18 | 7 | EAC Assessment Transitions to the EA Act (2018) Effects Assessment & Recommendation PHASE | ChangePhaseEndEvent | Set "Pre-Early Engagement ¦ Project Transitioning FROM the EA Act (2002)" to PHASE END EVENT | {"phase_name":"Pre-Early Engagement","work_type_id": 6, "ea_act_id": 3, "event_name": "Project Transitioning FROM the EA Act (2002)"} | 18
19 | 7 | EAC Assessment Transitions to the EA Act (2018) Effects Assessment & Recommendation PHASE | SetEventDate | Set "Revised Application Development (Proponent Time) ¦ Start of Revised Application Development (Date Capture Milestone)" ACTUAL to thisEventActual +1 | {"phase_name":"Revised Application Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "event_name": "Start of Revised Application Development (Date Capture Milestone)", "start_at": 1 } | 19
20 | 8 | Proponent withdraws Submission from the EAC Assessment process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 20
21 | 8 | Proponent withdraws Submission from the EAC Assessment process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 21
22 | 8 | Proponent withdraws Submission from the EAC Assessment process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 22
23 | 8 | Proponent withdraws Submission from the EAC Assessment process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 23
24 | 9 | Starts the "clock" for EAC Assessment | LockWorkStartDate | Set the workStartDate to thisEventACTUAL | {"start_date_locked": true} | 24
25 | 10 | Dispute Resolution is started | CreateWork | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {"work_type": 15} | 25
26 | 11 | EAC Assessment is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 26
27 | 11 | EAC Assessment is Terminated under s.39(d) of Act | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 27
28 | 11 | EAC Assessment is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 28
29 | 11 | EAC Assessment is Terminated under s.39(d) of Act | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 29
30 | 12 | Proponent withdraws Project from EA process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 30
31 | 12 | Proponent withdraws Project from EA process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 31
32 | 12 | Proponent withdraws Project from EA process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 32
33 | 12 | Proponent withdraws Project from EA process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 33
34 | 13 | End of EAC Assessment: Early Engagement, start of EAC Assessment: DPD Development (Proponent Time) | SetEventDate | set "DPD Development (Proponent Time) ¦ Start of Detailed Project Description Development (Date Capture Milestone)" ACTUAL to thisEventActual +1 | {"phase_name":"DPD Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "event_name": "Start of Detailed Project Description Development", "start_at": 1 } | 34
35 | 14 | Draft Detailed Project Description Initial Review is POSITIVE | SetEventDate | Set ANTICIPATED of "Readiness Decision ¦ Detailed Project Description Received" to thisEventACTUAL +1 | {"phase_name":"Readiness Decision","work_type_id": 6, "ea_act_id": 3, "event_name": "Detailed Project Description Received", "start_at": 1 } | 35
36 | 15 | Draft Detailed Project Description Initial Review is NEGATIVE | AddEvent | Add a copy of "Submission of Detailed Project Description,"Draft" Detailed Project Description Initial Review" to thisPhase at thisEventACTUAL +21 | [{"phase_name":"DPD Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "event_name": "Submission of Detailed Project Description", "start_at": 21 },{"phase_name":"DPD Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "event_name": "\"Draft\" Detailed Project Description Initial Review", "start_at": 28 }] | 36
38 | 16 | Dispute Resolution is started | CreateWork | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {"work_type": 15} | 38
39 | 17 | EAC Assessment is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 39
40 | 17 | EAC Assessment is Terminated under s.39(d) of Act | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 40
41 | 17 | EAC Assessment is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 41
42 | 17 | EAC Assessment is Terminated under s.39(d) of Act | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 42
43 | 18 | Proponent withdraws Project from EA process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 43
44 | 18 | Proponent withdraws Project from EA process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 44
45 | 18 | Proponent withdraws Project from EA process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 45
46 | 18 | Proponent withdraws Project from EA process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 46
47 | 19 | Dispute Resolution is started | CreateWork | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {"work_type": 15} | 47
48 | 20 | EAC Assessment is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 48
49 | 20 | EAC Assessment is Terminated under s.39(d) of Act | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 49
50 | 20 | EAC Assessment is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 50
51 | 20 | EAC Assessment is Terminated under s.39(d) of Act | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 51
52 | 21 | Proponent withdraws Project from EA process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 52
53 | 21 | Proponent withdraws Project from EA process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 53
54 | 21 | Proponent withdraws Project from EA process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 54
55 | 21 | Proponent withdraws Project from EA process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 55
56 | 22 | Proponent must submit a Revised DPD | AddPhase | addPhase "DPD Development (Proponent Time)" (copy of the origal PHASE) | [{"phase_name":"DPD Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "new_name": "Revised DPD Development (Proponent Time)", "legislated": false },{"phase_name":"Readiness Decision","work_type_id": 6, "ea_act_id": 3, "new_name": "Revised Readiness Decision", "legislated": false }] | 56
58 | 22 | Proponent must submit a Revised DPD | SetEventDate | Set "DPD Development (Proponent Time) ¦ Start of Detailed Project Description Development" ACTUAL to thisEventActual +1 | {"phase_name":"Revised DPD Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "event_name": "Start of Detailed Project Description Development", "start_at": 1 } | 58
59 | 23 | Project moves to Process Planning | SetEventDate | set "Process Planning ¦ Start of Process Planning (Date Capture Milestone)" ACTUAL to thisEventActual +1 | {"phase_name":"Process Planning","work_type_id": 6, "ea_act_id": 3, "event_name": "Start of Process Planning (Date Capture Milestone)", "start_at": 1 } | 59
60 | 24 | Project is Referred to Minister for Termination | AddPhase | Set "Termination Decision" PHASE to ACTIVE (show it) | [{"phase_name":"Termination Decision","work_type_id": 6, "ea_act_id": 3, "new_name": "Termination Decision", "legislated": false }] | 60
61 | 24 | Project is Referred to Minister for Termination | AddEvent | Set "Readiness Decision ¦ Termination Package Referred to Minister, Last Day of EAC Assessment Readiness Decision (Date Capture Milestone)" EVENT to ACTIVE (show it) | [{"phase_name":"Readiness Decision","work_type_id": 6, "ea_act_id": 3, "event_name": "Termination Package Referred to Minister", "start_at": 1 },{"phase_name":"Readiness Decision","work_type_id": 6, "ea_act_id": 3, "event_name": "Last Day of EAC Assessment Readiness Decision (Date Capture Milestone)", "start_at": 0 }] | 61
63 | 24 | Project is Referred to Minister for Termination | ChangePhaseEndEvent | Set "Readiness Decision ¦ Last Day of EAC Assessment Readiness Decision (Date Capture Milestone)" to PHASE END EVENT | {"phase_name":"Readiness Decision","work_type_id": 6, "ea_act_id": 3, "event_name": "Last Day of EAC Assessment Readiness Decision (Date Capture Milestone)" } | 63
64 | 24 | Project is Referred to Minister for Termination | SetEventDate | Set "Readiness Decision ¦ Termination Package Referred to Minister" ANTICIPATED to thisEventACTUAL +5 | {"phase_name":"Readiness Decision","work_type_id": 6, "ea_act_id": 3, "event_name": "Termination Package Referred to Minister", "start_at": 5 } | 64
65 | 24 | Project is Referred to Minister for Termination | SetEventDate | Set "Readiness Decision ¦ Last Day of EAC Assessment Readiness Decision (Date Capture Milestone)" ANTICIPATED to thisEventACTUAL +7 | {"phase_name":"Readiness Decision","work_type_id": 6, "ea_act_id": 3, "event_name": "Last Day of EAC Assessment Readiness Decision (Date Capture Milestone)", "start_at": 7 } | 65
67 | 26 | EAC Assessment is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 67
68 | 26 | EAC Assessment is Terminated under s.39(d) of Act | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 68
69 | 26 | EAC Assessment is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 69
70 | 26 | EAC Assessment is Terminated under s.39(d) of Act | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 70
71 | 27 | Proponent withdraws Project from EA process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 71
72 | 27 | Proponent withdraws Project from EA process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 72
73 | 27 | Proponent withdraws Project from EA process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 73
74 | 27 | Proponent withdraws Project from EA process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 74
75 | 28 | Project is Terminated | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 75
76 | 28 | Project is Terminated | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 76
77 | 28 | Project is Terminated | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 77
78 | 28 | Project is Terminated | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 78
79 | 29 | Refer the Project to the CEAO for Further Decision | AddPhase | Set "Further Readiness Decision" PHASE to ACTIVE (show it) | [{"phase_name":"Further Readiness Decision","work_type_id": 6, "ea_act_id": 3, "new_name": "Further Readiness Decision", "legislated": false }] | 79
80 | 29 | Refer the Project to the CEAO for Further Decision | SetEventDate | Set "Further Readiness Decision ¦ Readiness Decision Report referred to CEAO for Further Decision" ACTUAL to thisEventACTUAL +1 | {"phase_name":"Further Readiness Decision","work_type_id": 6, "ea_act_id": 3, "event_name": "Readiness Decision Report referred to CEAO for Further Decision", "start_at": 1 } | 80
81 | 30 | EAC Assessment is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 81
82 | 30 | EAC Assessment is Terminated under s.39(d) of Act | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 82
83 | 30 | EAC Assessment is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 83
84 | 30 | EAC Assessment is Terminated under s.39(d) of Act | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 84
85 | 31 | Proponent withdraws Project from EA process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 85
86 | 31 | Proponent withdraws Project from EA process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 86
87 | 31 | Proponent withdraws Project from EA process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 87
88 | 31 | Proponent withdraws Project from EA process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 88
89 | 32 | Proponent must submit a Revised DPD | AddPhase | addPhase "DPD Development (Proponent Time)" (copy of the origal PHASE) | [{"phase_name":"DPD Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "new_name": "Revised DPD Development (Proponent Time)", "legislated": false },{"phase_name":"Readiness Decision","work_type_id": 6, "ea_act_id": 3, "new_name": "Revised Readiness Decision", "legislated": false }] | 89
91 | 32 | Proponent must submit a Revised DPD | SetEventDate | Set "DPD Development (Proponent Time) ¦ Start of Detailed Project Description Development" ACTUAL to thisEventActual +1 | {"phase_name":"Revised DPD Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "event_name": "Start of Detailed Project Description Development", "start_at": 1 } | 91
92 | 33 | Project moves to Process Planning | SetEventDate | Set "Process Planning ¦ Start of Process Planning (Date Capture Milestone)" ACTUAL to thisEventActual +1 | {"phase_name":"Process Planning","work_type_id": 6, "ea_act_id": 3, "event_name": "Start of Process Planning (Date Capture Milestone)", "start_at": 1 } | 92
94 | 35 | Set federalInvolvement to "None" | SetFederalInvolvement | Set federalInvolvement to "None" | {"federal_involvement_id": 2} | 94
96 | 37 | Set federalInvolvement to "None" | SetFederalInvolvement | Set federalInvolvement to "None" | {"federal_involvement_id": 2} | 96
97 | 38 | Dispute Resolution is started | CreateWork | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {} | 97
98 | 39 | EAC Assessment is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 98
99 | 39 | EAC Assessment is Terminated under s.39(d) of Act | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 99
100 | 39 | EAC Assessment is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 100
101 | 39 | EAC Assessment is Terminated under s.39(d) of Act | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 101
102 | 40 | Proponent withdraws Project from EA process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 102
103 | 40 | Proponent withdraws Project from EA process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 103
104 | 40 | Proponent withdraws Project from EA process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 104
105 | 40 | Proponent withdraws Project from EA process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 105
106 | 41 | End of EAC Assessment: Process Planning PHASE, start of EAC Assessment: DPD Development (Proponent Time) PHASE | SetEventDate | Set "Application Development (Proponent Time) ¦ Start of Application Development (Date Capture Milestone)" ACTUAL to thisEventActual +1 | {"phase_name":"Application Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "event_name": "Start of Application Development (Date Capture Milestone)", "start_at": 1 } | 106
107 | 42 | "Draft" EAC Application Initial Review is POSITIVE | SetEventDate | Set ANTICIPATED of "Application Review ¦ EAC Application Received" to thisEventACTUAL +1 | {"phase_name":"Application Review","work_type_id": 6, "ea_act_id": 3, "event_name": "EAC Application Received", "start_at": 1 } | 107
108 | 43 | "Draft" EAC Application Initial Review is NEGATIVE | AddEvent | Add a copy of "Submission of EAC Application,"Draft" EAC Application Initial Review" to thisPhase at thisEventACTUAL +50 | [{"phase_name":"Application Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "event_name": "Submission of EAC Application", "start_at": 50 },{"phase_name":"Application Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "event_name": "\"Draft\" EAC Application Initial Review", "start_at": 10 }] | 108
110 | 44 | Dispute Resolution is started | CreateWork | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {"work_type": 15} | 110
111 | 45 | EAC Assessment is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 111
112 | 45 | EAC Assessment is Terminated under s.39(d) of Act | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 112
113 | 45 | EAC Assessment is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 113
114 | 45 | EAC Assessment is Terminated under s.39(d) of Act | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 114
115 | 46 | Proponent withdraws Project from EA process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 115
116 | 46 | Proponent withdraws Project from EA process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 116
117 | 46 | Proponent withdraws Project from EA process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 117
118 | 46 | Proponent withdraws Project from EA process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 118
119 | 47 | Dispute Resolution is started | CreateWork | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {"work_type": 15} | 119
120 | 48 | EAC Assessment is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 120
121 | 48 | EAC Assessment is Terminated under s.39(d) of Act | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 121
122 | 48 | EAC Assessment is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 122
123 | 48 | EAC Assessment is Terminated under s.39(d) of Act | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 123
124 | 49 | Proponent withdraws Project from EA process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 124
125 | 49 | Proponent withdraws Project from EA process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 125
126 | 49 | Proponent withdraws Project from EA process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 126
127 | 49 | Proponent withdraws Project from EA process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 127
128 | 50 | End of EAC Assessment: Application Review PHASE, start of EAC Assessment: Revised Application Development (Proponent Time) PHASE | SetEventDate | Set "Revised Application Development (Proponent Time) ¦ Start of Revised Application Development (Date Capture Milestone)" ACTUAL to thisEventActual +1 | {"phase_name":"Revised Application Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "event_name": "Start of Revised Application Development (Date Capture Milestone)", "start_at": 1 } | 128
129 | 51 | "Draft" Revised EAC Application Initial Review is POSITIVE | SetEventDate | Set ANTICIPATED of "Effects Assessment & Recommendation ¦ Revised EAC Application Accepted" to thisEventACTUAL +1 | {"phase_name":"Effects Assessment & Recommendation","work_type_id": 6, "ea_act_id": 3, "event_name": "Revised EAC Application Accepted", "start_at": 1 } | 129
130 | 52 | "Draft" Revised EAC Application Initial Review is NEGATIVE | AddEvent | Add a copy of "Submission of Revised EAC Application,"Draft" Revised EAC Application Initial Review" to thisPhase at thisEventACTUAL +50 | [{"phase_name":"Revised Application Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "event_name": "Submission of Revised EAC Application", "start_at": 50 },{"phase_name":"Revised Application Development (Proponent Time)","work_type_id": 6, "ea_act_id": 3, "event_name": "\"Draft\" Revised EAC Application Initial Review", "start_at": 10 }] | 130
132 | 53 | Dispute Resolution is started | CreateWork | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {"work_type": 15} | 132
133 | 54 | EAC Assessment is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 133
134 | 54 | EAC Assessment is Terminated under s.39(d) of Act | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 134
135 | 54 | EAC Assessment is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 135
136 | 54 | EAC Assessment is Terminated under s.39(d) of Act | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 136
137 | 55 | Proponent withdraws Project from EA process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 137
138 | 55 | Proponent withdraws Project from EA process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 138
139 | 55 | Proponent withdraws Project from EA process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 139
140 | 55 | Proponent withdraws Project from EA process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 140
141 | 56 | Dispute Resolution is started | CreateWork | Create a new WORK: "Dispute Resolution" and link to thisWorkLinkedProject | {"work_type": 15} | 141
142 | 57 | EAC Assessment is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 142
143 | 57 | EAC Assessment is Terminated under s.39(d) of Act | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 143
144 | 57 | EAC Assessment is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 144
145 | 57 | EAC Assessment is Terminated under s.39(d) of Act | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 145
146 | 58 | Proponent withdraws Project from EA process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 146
147 | 58 | Proponent withdraws Project from EA process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 147
148 | 58 | Proponent withdraws Project from EA process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 148
149 | 58 | Proponent withdraws Project from EA process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 149
150 | 59 | End of EAC Assessment: Effects Assessment & Recommendation PHASE, start of EAC Assessment: Decision PHASE | SetEventDate | Set "Decision ¦ Referral Package Received by Ministers" ACTUAL to thisEventActual +1 | {"phase_name":"Decision","work_type_id": 6, "ea_act_id": 3, "event_name": "Referral Package Received by Ministers", "start_at": 1 } | 150
151 | 60 | Proponent withdraws Project from EA process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 151
152 | 60 | Proponent withdraws Project from EA process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 152
153 | 60 | Proponent withdraws Project from EA process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 153
154 | 60 | Proponent withdraws Project from EA process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 154
155 | 61 | Environmental Assessment Certificate GRANTED | SetWorkState | Set workState to COMPLETED | {"work_state": "COMPLETED"} | 155
156 | 61 | Environmental Assessment Certificate GRANTED | SetProjectState | Set projectState to "Active: Pre-Construction" | {"project_state": "PRE_CONSTRUCTION"} | 156
157 | 62 | Environmental Assessment Certificate REFUSED | SetWorkState | Set workState to COMPLETED | {"work_state": "COMPLETED"} | 157
158 | 62 | Environmental Assessment Certificate REFUSED | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 158

## Lookups
WorkType | EA Act | Legislated |  | Event Type | Event Category | Mandatory | ActionName | Event Position | Multiple Days
Project Notification | EA Act (2018) | TRUE | Milestone | Generic | Milestone | TRUE | AllEventsDeactivated | START | TRUE
Minister's Designation | EA Act (2002) | FALSE | Milestone | Meeting | Calendar | FALSE | AllEventsDeleted | INTERMEDIATE | FALSE
CEAO's Designation | EA Act (1996) |  | Milestone | Notification | Decision |  | CloseEverything | END
EAC Assessment |  |  | Milestone | Order | Finance |  | CloseWork
Exemption Request |  |  | Milestone | Referral | PCP |  | CompleteCurrentPhase
Dispute Resolution |  |  | Milestone | Report | Extension |  | CreateNewWork
EAC/Order Amendment |  |  | Milestone | Request | Suspension |  | DisableWorkStartDate
Document Review |  |  | Milestone | Submission |  |  | DuplicatePhase
EAC Extension |  |  | Milestone | Other
Substantial Start Decision |  |  | Milestone | Date Capture
EAC/Order Transfer |  |  | Extension | Time Limit Extension
EAC/Order Suspension |  |  | Extension | PCP Time Limit Extension
EAC/Order Cancellation |  |  | Suspension | Time Limit Suspension
Other |  |  | Suspension | Time Limit Resumption
|  |  | Decision | EAC Ministers
|  |  | Decision | Minister
|  |  | Decision | CEAO
|  |  | Decision | ADM
|  |  | Decision | EPD
|  |  | Decision | PAD (Lead)
|  |  | Decision | Reviewer
|  |  | Decision | Federal
|  |  | Decision | Other
|  |  | PCP | Comment Period
|  |  | PCP | Open House
|  |  | PCP | Virtual Information Session
|  |  | PCP | Other
|  |  | Calendar | Communications
|  |  | Calendar | Executive
|  |  | Calendar | Financial
|  |  | Calendar | Work
|  |  | Calendar | Other
|  |  | Finance | Capacity Funding
|  |  | Finance | Fee Order
|  |  | Finance | Penalties
|  |  | Finance | Administrative
|  |  | Finance | Other

## Outcome_Temp
3 | 10 | Project Transitioning FROM the EA Act (2002) | NO ACTION | 3

## Action_Temp
4 | 3 | #N/A | NO ACTION | No Action Needed | {} | 4
66 | 25 | Refer for Minister's Process Planning | NO ACTION | We currently don’t know how to handle this in EPIC.track | {} | 66
93 | 34 | Refer for Minister's Process Planning | NO ACTION | We currently don’t know how to handle this in EPIC.track | {} | 93
95 | 36 | Unknown QQQ (how to set federalInvolvement properly) | NO ACTION | We currently don’t know how to handle this in EPIC.track | {} | 95