## Instructions
Cell Colors
This color means that the cell has a picklist Validation constraint.
This color means that the cell has a formula and should not be changed. Change the vLookup source.
This color means the cell is open to user input
Order of Data Entry
You need to do the Phases before Events, Events before Outcomes, and Outcomes before Actions
The No Field and Row Deletion
The No (number field) of each sheet is the Validation list of the next sheet. For example the Events sheet has the heading PhaseNo which pulls from the Phases sheet No cells.
To maintain the Data Validation for all the sheets, make sure you DELETE the Entire Row for every unused row in the sheet you are working on. IE select the entire row(s) and right-click > Delete.

## Phases
No | Name | WorkType | EAAct | NumberOfDays | Legislated | Color | Visibility | SortOrder
1 | Minister's Designation Intake | Minister's Designation | EA Act (2018) | 28 | FALSE | #FFFFFF | REGULAR | 1
2 | Minister's Designation Review | Minister's Designation | EA Act (2018) | 25 | TRUE | #FFFFFF | REGULAR | 2
3 | Minister's Designation Decision | Minister's Designation | EA Act (2018) | 5 | TRUE | #FFFFFF | REGULAR | 3

## Events
No | Parent | PhaseNo | EventName | Phase | EventType | EventCategory | EventPosition | MultipleDays | StartAt | NumberOfDays | Visibility | SortOrder
1 |  | 1 | Initial Contact with Minister's Designation Applicants | Minister's Designation Intake | Meeting | Milestone | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 1
2 |  | 1 | Submission of Minister's Designation Application | Minister's Designation Intake | Submission | Milestone | INTERMEDIATE | FALSE | 14 | 0 | MANDATORY | 2
3 |  | 1 | Minister's Designation Application Initial Review | Minister's Designation Intake | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 28 | 0 | MANDATORY | 3
4 |  | 1 | Additional Information Submission | Minister's Designation Intake | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 4
5 |  | 1 | Minister's Designation Application Withdrawn | Minister's Designation Intake | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 5
6 |  | 1 | Other | Minister's Designation Intake | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 6
7 |  | 1 | Last Day of Minister's Designation Intake (Date Capture Milestone) | Minister's Designation Intake | Date Capture | Milestone | INTERMEDIATE | FALSE | 28 | 0 | MANDATORY | 7
8 |  | 2 | Minister's Designation Application Received | Minister's Designation Review | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 8
9 |  | 2 | Delegation of Decision | Minister's Designation Review | Minister | Decision | INTERMEDIATE | FALSE | 7 | 0 | MANDATORY | 9
10 |  | 2 | Additional Information Submission | Minister's Designation Review | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 10
11 |  | 2 | Circulate Draft Designation Report | Minister's Designation Review | Report | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 11
12 |  | 2 | Additional Comment Period | Minister's Designation Review | Comment Period | PCP | INTERMEDIATE | TRUE | 0 | 30 | OPTIONAL | 12
13 | 12 | 2 | PCP Coming Soon Announcement & Tweet | Minister's Designation Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 13
14 | 12 | 2 | Additional PCP Milestone Bullet | Minister's Designation Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 14
15 | 12 | 2 | PCP Now Open Announcement & Tweet | Minister's Designation Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 15
16 | 12 | 2 | PCP Ending Soon Announcement & Tweet | Minister's Designation Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 16
17 |  | 2 | Open House | Minister's Designation Review | Open House | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 17
18 |  | 2 | Virtual Information Session | Minister's Designation Review | Virtual Information Session | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 18
19 |  | 2 | Comment Period Time Limit Extension | Minister's Designation Review | PCP Time Limit Extension | Extension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 19
20 | 19 | 2 | PCP Extended Announcement & Tweet | Minister's Designation Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 20
21 | 19 | 2 | PCP Extended Milestone Bullet | Minister's Designation Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 21
22 |  | 2 | s.38 Extension of Time Limit | Minister's Designation Review | Time Limit Extension | Extension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 22
23 | 22 | 2 | Extension Announcement & Tweet | Minister's Designation Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 23
24 | 22 | 2 | Time Limit Extended Milestone Bullet | Minister's Designation Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 24
26 | 25 | 2 | Minister's Designation Process Suspension Announcement & Tweet | Minister's Designation Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 26
27 | 25 | 2 | Minister's Designation Process Suspended Milestone Bullet | Minister's Designation Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 27
29 | 28 | 2 | Minister's Designation Process Resumption Announcement & Tweet | Minister's Designation Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 29
30 | 28 | 2 | Minister's Designation Process Resumed Milestone Bullet | Minister's Designation Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 30
31 |  | 2 | Minister's Designation Process Terminated s.39(d) | Minister's Designation Review | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 31
32 | 31 | 2 | Termination Announcement & Tweet | Minister's Designation Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 32
33 | 31 | 2 | Minister's Designation Terminated Milestone Bullet | Minister's Designation Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 33
34 |  | 2 | Minister's Designation Application Withdrawn | Minister's Designation Review | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 34
35 | 34 | 2 | Withdrawal Announcement & Tweet | Minister's Designation Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 35
36 | 34 | 2 | Minister's Designation Application Withdrawn Milestone Bullet | Minister's Designation Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 36
37 |  | 2 | Other | Minister's Designation Review | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 37
38 |  | 2 | Complete Minister's Designation Report | Minister's Designation Review | Report | Milestone | INTERMEDIATE | FALSE | 25 | 0 | MANDATORY | 38
39 |  | 3 | Minister's Designation Report referred to Decision Maker | Minister's Designation Decision | Referral | Milestone | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 39
40 |  | 3 | Draft Designation Decision Milestone Bullets | Minister's Designation Decision | Generic | Milestone | INTERMEDIATE | FALSE | 5 | 0 | MANDATORY | 40
41 | 40 | 3 | REMINDER: Draft Designation Decision Milestone Bullet Due (only if Decision: CEAO) | Minister's Designation Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 41
42 |  | 3 | Additional Information Submission | Minister's Designation Decision | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 42
43 |  | 3 | s.38 Extension of Time Limit | Minister's Designation Decision | Time Limit Extension | Extension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 43
44 | 43 | 3 | Extension Announcement & Tweet | Minister's Designation Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 44
45 | 43 | 3 | Time Limit Extended Milestone Bullet | Minister's Designation Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 45
46 |  | 3 | Minister's Designation Process Terminated s.39(d) | Minister's Designation Decision | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 46
47 | 46 | 3 | Termination Announcement & Tweet | Minister's Designation Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 47
48 | 46 | 3 | Minister's Designation Terminated Milestone Bullet | Minister's Designation Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 48
49 |  | 3 | Minister's Designation Application Withdrawn | Minister's Designation Decision | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 49
50 | 49 | 3 | Withdrawal Announcement & Tweet | Minister's Designation Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 50
51 | 49 | 3 | Minister's Designation Application Withdrawn Milestone Bullet | Minister's Designation Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 51
52 |  | 3 | Other | Minister's Designation Decision | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 52
53 |  | 3 | Minister's Designation Decision | Minister's Designation Decision | Minister | Decision | INTERMEDIATE | FALSE | 5 | 0 | MANDATORY | 53
54 | 53 | 3 | Minister's Designation Decision Announcement & Tweet | Minister's Designation Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 54
55 | 53 | 3 | Designation Decision Milestone Bullet (only if Decision: CEAO) | Minister's Designation Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 55

## Outcomes
No | TemplateNo | TemplateName | OutcomeName | SortOrder
1 | 3 | Minister's Designation Application Initial Review | Draft Minister's Designation Application is "incomplete" | 1
2 | 3 | Minister's Designation Application Initial Review | Draft Minister's Designation Application is for an "eligible" project | 2
3 | 3 | Minister's Designation Application Initial Review | Project submitted exceeds RPR threshold(s) | 3
4 | 3 | Minister's Designation Application Initial Review | Project submitted exceeds RPR threshold(s) and is Substantially Started | 4
5 | 5 | Minister's Designation Application Withdrawn | Applicant withdraws Submission from the Minister's Designation process | 5
6 | 8 | Minister's Designation Application Received | Starts the "clock" for Minister's Designation | 6
7 | 9 | Delegation of Decision | Minister is delegated to make the final Minister's Designation Decision | 7
8 | 9 | Delegation of Decision | CEAO is delegated to make the final Minister's Designation Decision | 8
9 | 31 | Minister's Designation Process Terminated s.39(d) | Assessment is Terminated under s.39(d) of Act | 9
10 | 34 | Minister's Designation Application Withdrawn | Proponent withdraws Project from EA process | 10
11 | 46 | Minister's Designation Process Terminated s.39(d) | Assessment is Terminated under s.39(d) of Act | 11
12 | 49 | Minister's Designation Application Withdrawn | Proponent withdraws Project from EA process | 12
13 | 53 | Minister's Designation Decision | Decision Maker Designates Project as Reviewable | 13
14 | 53 | Minister's Designation Decision | Decision Maker Declines to Designate Project as Reviewable | 14

## Actions
No | OutcomeNo | OutcomeName | ActionName | ActionDescription | AdditionalParams | SortOrder
1 | 1 | Draft Minister's Designation Application is "incomplete" | AddEvent | Add a copy of Minister's Designation Intake ¦ Submission of Minister's Designation Application, Minister's Designation Application Initial Review" to thisPhase at thisEventACTUAL +28 | [{"phase_name":"Minister's Designation Intake","work_type_id": 2, "ea_act_id": 3, "event_name": "Submission of Minister's Designation Application", "start_at": 28 },{"phase_name":"Minister's Designation Intake","work_type_id": 2, "ea_act_id": 3, "event_name": "Minister's Designation Application Initial Review", "start_at": 7 }] | 1
3 | 2 | Draft Minister's Designation Application is for an "eligible" project | SetEventDate | Set ANTICIPATED of "Minister's Designation Review ¦ Minister's Designation Application Received" to thisEventACTUAL +1 | {"phase_name":"Minister's Designation Review","work_type_id": 2, "ea_act_id": 3, "event_name": "Minister's Designation Application Received", "start_at": 1 } | 3
4 | 3 | Project submitted exceeds RPR threshold(s) | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 4
5 | 3 | Project submitted exceeds RPR threshold(s) | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 5
6 | 3 | Project submitted exceeds RPR threshold(s) | SetWorkState | Set workState to CLOSED | {"work_state": "CLOSED"} | 6
7 | 3 | Project submitted exceeds RPR threshold(s) | CreateWork | Create a new WORK: "EAC Assessment" and link to thisWorkLinkedProject | {"work_type":6} | 7
8 | 4 | Project submitted exceeds RPR threshold(s) and is Substantially Started | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 8
9 | 4 | Project submitted exceeds RPR threshold(s) and is Substantially Started | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 9
10 | 4 | Project submitted exceeds RPR threshold(s) and is Substantially Started | SetWorkState | Set workState to CLOSED | {"work_state": "CLOSED"} | 10
11 | 5 | Applicant withdraws Submission from the Minister's Designation process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 11
12 | 5 | Applicant withdraws Submission from the Minister's Designation process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 12
13 | 5 | Applicant withdraws Submission from the Minister's Designation process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 13
14 | 5 | Applicant withdraws Submission from the Minister's Designation process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 14
15 | 6 | Starts the "clock" for Minister's Designation | LockWorkStartDate | Set the workStartDate to thisEventACTUAL | {"start_date_locked": true} | 15
16 | 7 | Minister is delegated to make the final Minister's Designation Decision | SetWorkDecisionMaker | Set the workDecisionMaker to currentMinisterEnvironment | {"position_id": 8} | 16
17 | 8 | CEAO is delegated to make the final Minister's Designation Decision | SetWorkDecisionMaker | Set the workDecisionMaker to currentCEAO | {"position_id": 1} | 17
18 | 9 | Assessment is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 18
19 | 9 | Assessment is Terminated under s.39(d) of Act | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 19
20 | 9 | Assessment is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 20
21 | 9 | Assessment is Terminated under s.39(d) of Act | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 21
22 | 10 | Proponent withdraws Project from EA process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 22
23 | 10 | Proponent withdraws Project from EA process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 23
24 | 10 | Proponent withdraws Project from EA process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 24
25 | 10 | Proponent withdraws Project from EA process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 25
26 | 11 | Assessment is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 26
27 | 11 | Assessment is Terminated under s.39(d) of Act | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 27
28 | 11 | Assessment is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 28
29 | 11 | Assessment is Terminated under s.39(d) of Act | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 29
30 | 12 | Proponent withdraws Project from EA process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 30
31 | 12 | Proponent withdraws Project from EA process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"is_active": false} | 31
32 | 12 | Proponent withdraws Project from EA process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 32
33 | 12 | Proponent withdraws Project from EA process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 33
34 | 13 | Decision Maker Designates Project as Reviewable | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 34
35 | 13 | Decision Maker Designates Project as Reviewable | CreateWork | Create a new WORK: "EAC Assessment" and link to thisWorkLinkedProject | {"work_type":6} | 35
36 | 14 | Decision Maker Declines to Designate Project as Reviewable | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 36
37 | 14 | Decision Maker Declines to Designate Project as Reviewable | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 37

## Lookups
WorkType | EA Act | Legislated |  | Event Type | Event Category | Mandatory | ActionName | Event Position | Multiple Days
Project Notification | EA Act (2018) | TRUE | Milestone | Generic | Milestone | TRUE | AllEventsDeactivated | START | TRUE
Minister's Designation | EA Act (2002) | FALSE | Milestone | Meeting | Calendar | FALSE | AllEventsDeleted | INTERMEDIATE | FALSE
CEAO's Designation | EA Act (1996) |  | Milestone | Notification | Decision |  | CloseEverything | END
EAC Assessment |  |  | Milestone | Order | Finance |  | CloseWork
Exemption Request |  |  | Milestone | Referral | PCP |  | CompleteCurrentPhase
Dispute Resolution |  |  | Milestone | Report | Extension |  | CreateNewWork
EAC/Order Amendment |  |  | Milestone | Request | Suspension |  | DisableWorkStartDate
Document Review |  |  | Milestone | Submission |  |  | DuplicatePhase
EAC Extension |  |  | Milestone | Other
Substantial Start Decision |  |  | Milestone | Date Capture
EAC/Order Transfer |  |  | Extension | Time Limit Extension
EAC/Order Suspension |  |  | Extension | PCP Time Limit Extension
EAC/Order Cancellation |  |  | Suspension | Time Limit Suspension
Other |  |  | Suspension | Time Limit Resumption
|  |  | Decision | EAC Ministers
|  |  | Decision | Minister
|  |  | Decision | CEAO
|  |  | Decision | ADM
|  |  | Decision | EPD
|  |  | Decision | PAD (Lead)
|  |  | Decision | Reviewer
|  |  | Decision | Federal
|  |  | Decision | Other
|  |  | PCP | Comment Period
|  |  | PCP | Open House
|  |  | PCP | Virtual Information Session
|  |  | PCP | Other
|  |  | Calendar | Communications
|  |  | Calendar | Executive
|  |  | Calendar | Financial
|  |  | Calendar | Work
|  |  | Calendar | Other
|  |  | Finance | Capacity Funding
|  |  | Finance | Fee Order
|  |  | Finance | Penalties
|  |  | Finance | Administrative
|  |  | Finance | Other