## Phases
No | Name | WorkType | EAAct | NumberOfDays | Legislated | Color | Visibility | SortOrder
1 | Pre-Application | Material Alteration | EA Act (2018) | 90 | FALSE | #FFFFFF | REGULAR | 1
2 | Application Review | Material Alteration | EA Act (2018) | 150 | FALSE | #FFFFFF | REGULAR | 2
3 | Consent Decision | Material Alteration | EA Act (2018) | 30 | FALSE | #FFFFFF | REGULAR | 3

## Events
No | Parent | PhaseNo | EventName | Phase | EventType | EventCategory | EventPosition | MultipleDays | StartAt | NumberOfDays | Visibility | SortOrder
1 |  | 1 | Initial Contact with Holder or MinMCM | Pre-Application | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 1
2 |  | 1 | Minister of MinMCM makes "Material Alteration" Determination | Pre-Application | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 30 | 0 | SUGGESTED | 2
3 |  | 1 | Additional Information Submission | Pre-Application | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 3
4 |  | 1 | Meeting with Holder | Pre-Application | Meeting | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 4
5 |  | 1 | Direct Submission of CMA Application/Request - DELETE this Pre-Application PHASE! | Pre-Application | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 5
6 |  | 1 | Document Submitted to EAO for "Initial Review" | Pre-Application | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 6
7 | 6 | 1 | EAO's Viewpoint on Submitted Document | Pre-Application | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 7
8 |  | 1 | CMA Application Withdrawn | Pre-Application | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 8
9 |  | 1 | Other | Pre-Application | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 9
10 |  | 1 | Day before the CMA Application/Request Submitted | Pre-Application | Date Capture | Milestone | END | FALSE | 90 | 0 | MANDATORY | 10
11 |  | 2 | CMA Application/Request Received | Application Review | Submission | Milestone | START | FALSE | 0 | 0 | MANDATORY | 11
12 |  | 2 | FN Notification Letters Sent | Application Review | Notification | Milestone | INTERMEDIATE | FALSE | 14 | 0 | SUGGESTED | 12
13 |  | 2 | Draft CMA Report/Decision Note | Application Review | Report | Milestone | INTERMEDIATE | FALSE | 100 | 0 | SUGGESTED | 13
14 |  | 2 | Draft CMA Report/Decision Note Circulated to FNs | Application Review | Generic | Milestone | INTERMEDIATE | FALSE | 110 | 0 | SUGGESTED | 14
15 |  | 2 | Additional Information Submission | Application Review | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 15
16 |  | 2 | Meeting with Holder | Application Review | Meeting | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 16
17 |  | 2 | Minister of MinMCM makes "Material Alteration" Determination | Application Review | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 17
18 |  | 2 | Material Alteration Application Withdrawn | Application Review | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 18
19 |  | 2 | Other | Application Review | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 19
20 |  | 2 | CMA Decision Package Referred to Ministers | Application Review | Referral | Milestone | END | FALSE | 150 | 0 | MANDATORY | 20
21 | 20 | 2 | Decision Package Referred to Ministers | Application Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 21
22 |  | 3 | CMA Decision Package Received by Ministers | Consent Decision | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 22
23 |  | 3 | Consent for Material Alteration Decision | Consent Decision | EAC Ministers | Decision | END | FALSE | 30 | 0 | MANDATORY | 23
24 | 23 | 3 | Consent for Material Alteration Decision Announcement & Tweet | Consent Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 24
25 |  | 3 | Additional Information Submission | Consent Decision | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 25
26 |  | 3 | Meet with Minster(s) | Consent Decision | Meeting | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 26
27 |  | 3 | Other | Consent Decision | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 27

## Outcomes
No | TemplateNo | TemplateName | OutcomeName | OutcomeDescription | SortOrder
1 | 2 | Minister of MinMCM makes "Material Alteration" Determination | Alteration is Material | MinMCM determines the Alteration is Material | 1
2 | 2 | Minister of MinMCM makes "Material Alteration" Determination | Alteration is NOT Material | MinMCM determines the Alteration is NOT Material | 2
3 | 5 | Direct Submission of CMA Application/Request - DELETE this Pre-Application PHASE! | Delete the Pre-Application PHASE | Delete this "Pre-Application Phase" and go directly to "Application Review" | 3
4 | 6 | Document Submitted to EAO for "Initial Review" | EAO's Viewpoint is POSITIVE | EAO's Viewpoint is POSITIVE | 4
5 | 6 | Document Submitted to EAO for "Initial Review" | EAO's Viewpoint is NEGATIVE | EAO's Viewpoint is NEGATIVE | 5
6 | 8 | CMA Application Withdrawn | CMA Application Withdrawn | Proponent withdraws from the Consent for Material Alteration process | 6
7 | 17 | Minister of MinMCM makes "Material Alteration" Determination | Alteration is Material | MinMCM determines the Alteration is Material | 7
8 | 17 | Minister of MinMCM makes "Material Alteration" Determination | Alteration is NOT Material | MinMCM determines the Alteration is NOT Material | 8
9 | 18 | Material Alteration Application Withdrawn | CMA Application Withdrawn | Proponent withdraws from the Consent for Material Alteration process | 9
10 | 23 | Consent for Material Alteration Decision | Consent for MA GRANTED | Consent for Material Alteration GRANTED | 10
11 | 23 | Consent for Material Alteration Decision | Consent for MA REFUSED | Consent for Material Alteration REFUSED | 11

## Actions
No | OutcomeNo | OutcomeName | ActionName | ActionDescription | AdditionalParams | SortOrder
1 | 1 | Alteration is Material | NONE | No Action | {} | 1
2 | 2 | Alteration is NOT Material | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 2
3 | 2 | Alteration is NOT Material | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 3
4 | 2 | Alteration is NOT Material | SetWorkState | Set workState to CLOSED | {"work_state": "CLOSED"} | 4
5 | 3 | Delete the Pre-Application PHASE | SetEventDate | Set "Application Review¦ CMA Application Received" ANTICIPATED to thisWorkStartDate | {"phase_name":"Application Review","work_type_id": 15, "ea_act_id": 3, "event_name": "CMA Application/Request Received", "start_at": 0 } | 5
6 | 3 | Delete the Pre-Application PHASE | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 6
7 | 3 | Delete the Pre-Application PHASE | SetPhasesStatus | Set thisPhase to INACTIVE | [{"phase_name":"Pre-Application","work_type_id": 15, "ea_act_id": 3, "is_active": false }] | 7
8 | 4 | EAO's Viewpoint is POSITIVE | NONE | No Action | {} | 8
9 | 5 | EAO's Viewpoint is NEGATIVE | NONE | No Action | {} | 9
10 | 6 | CMA Application Withdrawn | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 10
11 | 6 | CMA Application Withdrawn | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 11
12 | 6 | CMA Application Withdrawn | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 12
13 | 7 | Alteration is Material | NONE | No Action | {} | 13
14 | 8 | Alteration is NOT Material | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 14
15 | 8 | Alteration is NOT Material | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 15
16 | 8 | Alteration is NOT Material | SetWorkState | Set workState to CLOSED | {"work_state": "CLOSED"} | 16
17 | 9 | CMA Application Withdrawn | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases":false} | 17
18 | 9 | CMA Application Withdrawn | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events":false} | 18
19 | 9 | CMA Application Withdrawn | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 19
20 | 10 | Consent for MA GRANTED | SetWorkState | Set workState to COMPLETED | {"work_state": "COMPLETED"} | 20
21 | 11 | Consent for MA REFUSED | SetWorkState | Set workState to COMPLETED | {"work_state": "COMPLETED"} | 21

## Lookups
WorkType | EA Act | Legislated |  | Event Type | Event Category | Visibility | ActionName | Event Position | Multiple Days | Action Name
Project Notification | EA Act (2018) | TRUE | Milestone | Generic | Milestone | MANDATORY | AllEventsDeactivated | START | TRUE | AddEvent
Minister's Designation | EA Act (2002) | FALSE | Milestone | Meeting | Calendar | SUGGESTED | AllEventsDeleted | INTERMEDIATE | FALSE | AddPhase
CEAO's Designation | EA Act (1996) |  | Milestone | Notification | Decision | OPTIONAL | CloseEverything | END |  | ChangePhaseEndEvent
EAC Assessment |  |  | Milestone | Order | Finance | HIDDEN | CloseWork |  |  | CreateWork
Exemption Request |  |  | Milestone | Referral | PCP |  | CompleteCurrentPhase |  |  | LockWorkStartDate
Dispute Resolution |  |  | Milestone | Report | Extension |  | CreateNewWork |  |  | SetEventDate
EAC/Order Amendment |  |  | Milestone | Request | Suspension |  | DisableWorkStartDate |  |  | SetEventStatus
Document Review |  |  | Milestone | Submission |  |  | DuplicatePhase |  |  | SetFederalInvolvement
EAC Extension |  |  | Milestone | Other | [5 empty] | SetPhaseStatus
Substantial Start Decision |  |  | Milestone | Date Capture | [5 empty] | SetProjectState
Substantial Start Decision |  |  | Extension | Time Limit Extension | [5 empty] | SetProjectStatus
EAC/Order Transfer |  |  | Extension | PCP Time Limit Extension | [5 empty] | SetWorkDecisionMaker
Material Alteration |  |  | Extension | Interregnum | [5 empty] | SetWorkState
EAC/Order Cancellation |  |  | Suspension | Time Limit Suspension | [5 empty] | NONE
Other |  |  | Suspension | Time Limit Resumption
|  |  | Decision | EAC Ministers
|  |  | Decision | Minister
|  |  | Decision | CEAO
|  |  | Decision | ADM
|  |  | Decision | EPD
|  |  | Decision | PAD (Lead)
|  |  | Decision | Reviewer
|  |  | Decision | Federal
|  |  | Decision | Other
|  |  | PCP | Comment Period
|  |  | PCP | Open House
|  |  | PCP | Virtual Information Session
|  |  | PCP | Other
|  |  | Calendar | Communications
|  |  | Calendar | Executive
|  |  | Calendar | Financial
|  |  | Calendar | Work
|  |  | Calendar | Other
|  |  | Finance | Capacity Funding
|  |  | Finance | Fee Order
|  |  | Finance | Penalties
|  |  | Finance | Administrative
|  |  | Finance | Other