## Phases
No | Name | WorkType | EAAct | NumberOfDays | Legislated | Color | Visibility | SortOrder
1 | Notification Intake | Project Notification | EA Act (2018) | 21 | FALSE | #3eb1d7 | REGULAR | 1
2 | Notification Review | Project Notification | EA Act (2018) | 56 | TRUE | #3eb1d7 | REGULAR | 2
3 | Notification Decision | Project Notification | EA Act (2018) | 4 | TRUE | #3eb1d7 | REGULAR | 3

## Events
No | Parent | PhaseNo | EventName | Phase | EventType | EventCategory | EventPosition | MultipleDays | StartAt | NumberOfDays | Visibility | SortOrder
1 |  | 1 | Start of Intake Phase (e.g. Initial Contact, Draft Sharing, or PN Submission) | Notification Intake | Date Capture | Milestone | START | FALSE | 0 | 0 | MANDATORY | 1
2 |  | 1 | Meeting with Proponent | Notification Intake | Meeting | Milestone | INTERMEDIATE | FALSE | 7 | 0 | SUGGESTED | 2
3 |  | 1 | Additional Information Submission | Notification Intake | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 3
4 |  | 1 | Document Submitted to EAO for "Initial Review" | Notification Intake | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 4
5 | 4 | 1 | EAO's Viewpoint on Submitted Document | Notification Intake | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 7 | 0 | OPTIONAL | 5
6 |  | 1 | Project Notification Withdrawn | Notification Intake | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 6
7 |  | 1 | Direct Submission of Project Notification - DELETE this Intake Phase! | Notification Intake | PAD (Lead) | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 7
8 |  | 1 | Other | Notification Intake | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 8
9 |  | 1 | Last Day of Intake Phase (day before formal submission) | Notification Intake | Date Capture | Milestone | END | FALSE | 21 | 0 | MANDATORY | 9
10 |  | 2 | Project Notification Submission Received (Day Zero) | Notification Review | Submission | Milestone | START | FALSE | 0 | 0 | MANDATORY | 10
11 |  | 2 | Delegation of PN Decision | Notification Review | Minister | Decision | INTERMEDIATE | FALSE | 7 | 0 | MANDATORY | 11
12 |  | 2 | Comment Period | Notification Review | Comment Period | PCP | INTERMEDIATE | TRUE | 14 | 21 | SUGGESTED | 12
13 | 12 | 2 | PCP Coming Soon Announcement & Tweet | Notification Review | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | MANDATORY | 13
14 | 12 | 2 | PCP Coming Soon Milestone Bullet | Notification Review | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | MANDATORY | 14
15 | 12 | 2 | PCP Now Open Announcement & Tweet | Notification Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 15
16 | 12 | 2 | PCP Ending Soon Announcement & Tweet | Notification Review | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | MANDATORY | 16
17 |  | 2 | Additional Information Submission | Notification Review | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 17
18 |  | 2 | GHG Threshold Information Note | Notification Review | Report | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 18
19 | 18 | 2 | REMINDER: GHG Minister's Information Note | Notification Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 19
20 |  | 2 | Additional Comment Period | Notification Review | Comment Period | PCP | INTERMEDIATE | TRUE | 0 | 30 | OPTIONAL | 20
21 | 20 | 2 | PCP Coming Soon Announcement & Tweet | Notification Review | Communications | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | 21
22 | 20 | 2 | Additional PCP Milestone Bullet | Notification Review | Executive | Calendar | INTERMEDIATE | FALSE | -7 | 0 | OPTIONAL | 22
23 | 20 | 2 | PCP Now Open Announcement & Tweet | Notification Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 23
24 | 20 | 2 | PCP Ending Soon Announcement & Tweet | Notification Review | Communications | Calendar | INTERMEDIATE | FALSE | number_of_days-2 | 0 | OPTIONAL | 24
25 |  | 2 | Open House | Notification Review | Open House | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 25
26 |  | 2 | Virtual Information Session | Notification Review | Virtual Information Session | PCP | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 26
27 |  | 2 | Comment Period Time Limit Extension | Notification Review | PCP Time Limit Extension | Extension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 27
28 | 27 | 2 | PCP Extended Announcement & Tweet | Notification Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 28
29 | 27 | 2 | PCP Extended Milestone Bullet | Notification Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 29
30 |  | 2 | s.38 Extension of Time Limit | Notification Review | Time Limit Extension | Extension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 30
31 | 30 | 2 | Extension Announcement & Tweet | Notification Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 31
32 | 30 | 2 | Time Limit Extended Milestone Bullet | Notification Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 32
33 |  | 2 | s.45 Suspension of the Project Notification Process | Notification Review | Time Limit Suspension | Suspension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 33
34 | 33 | 2 | Project Notification Process Suspension Announcement & Tweet | Notification Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 34
35 | 33 | 2 | Project Notification Process Suspended Milestone Bullet | Notification Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 35
36 |  | 2 | s.45 Resumption of the Project Notification Process | Notification Review | Time Limit Resumption | Suspension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 36
37 | 36 | 2 | Project Notification Process Resumption Announcement & Tweet | Notification Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 37
38 | 36 | 2 | Project Notification Process Resumed Milestone Bullet | Notification Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 38
39 |  | 2 | Project Notification Terminated s.39(d) | Notification Review | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 39
40 | 39 | 2 | Termination Announcement & Tweet | Notification Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 40
41 | 39 | 2 | Project Notification Terminated Milestone Bullet | Notification Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 41
42 |  | 2 | Project Withdrawn | Notification Review | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 42
43 | 42 | 2 | Withdrawal Announcement & Tweet | Notification Review | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 43
44 | 42 | 2 | Project Withdrawn Milestone Bullet | Notification Review | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 44
45 |  | 2 | Other | Notification Review | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 45
46 |  | 2 | Project Notification Report referred to Decision Maker | Notification Review | Referral | Milestone | END | FALSE | 56 | 0 | MANDATORY | 46
47 |  | 3 | Project Notification Report Received by Decision Maker | Notification Decision | Report | Milestone | START | FALSE | 0 | 0 | MANDATORY | 47
48 |  | 3 | Create PN Decision Milestone Bullet | Notification Decision | Generic | Milestone | INTERMEDIATE | FALSE | 0 | 0 | SUGGESTED | 48
49 | 48 | 3 | REMINDER: Create PN Decision Milestone Bullet | Notification Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | SUGGESTED | 49
50 |  | 3 | Additional Information Submission | Notification Decision | Submission | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 50
51 |  | 3 | s.38 Extension of Time Limit | Notification Decision | Time Limit Extension | Extension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 51
52 | 51 | 3 | Extension Announcement & Tweet | Notification Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 52
53 | 51 | 3 | Time Limit Extended Milestone Bullet | Notification Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 53
54 |  | 3 | s.45 Suspension of the Project Notification Process | Notification Decision | Time Limit Suspension | Suspension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 54
55 | 54 | 3 | Project Notification Process Suspension Announcement & Tweet | Notification Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 55
56 | 54 | 3 | Project Notification Process Suspended Milestone Bullet | Notification Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 56
57 |  | 3 | s.45 Resumption of the Project Notification Process | Notification Decision | Time Limit Resumption | Suspension | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 57
58 | 57 | 3 | Project Notification Process Resumption Announcement & Tweet | Notification Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 58
59 | 57 | 3 | Project Notification Process Resumed Milestone Bullet | Notification Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 59
60 |  | 3 | Project Notification Terminated s.39(d) | Notification Decision | CEAO | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 60
61 | 60 | 3 | Termination Announcement & Tweet | Notification Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 61
62 | 60 | 3 | Project Notification Terminated Milestone Bullet | Notification Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 62
63 |  | 3 | Project Withdrawn | Notification Decision | EPD | Decision | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 63
64 | 63 | 3 | Withdrawal Announcement & Tweet | Notification Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 64
65 | 63 | 3 | Project Withdrawn Milestone Bullet | Notification Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 65
66 |  | 3 | Other | Notification Decision | Other | Milestone | INTERMEDIATE | FALSE | 0 | 0 | OPTIONAL | 66
67 |  | 3 | Decision: Project Notification | Notification Decision | Minister | Decision | END | FALSE | 4 | 0 | MANDATORY | 67
68 | 67 | 3 | Notification Decision Announcement & Tweet | Notification Decision | Communications | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 68
69 | 67 | 3 | Notification Decision Milestone Bullet | Notification Decision | Executive | Calendar | INTERMEDIATE | FALSE | 0 | 0 | MANDATORY | 69

## Outcomes
No | TemplateNo | TemplateName | OutcomeName | OutcomeDescription | SortOrder
1 | 5 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is POSITIVE |  | 1
2 | 5 | EAO's Viewpoint on Submitted Document | EAO's Viewpoint is NEGATIVE |  | 2
3 | 6 | Project Notification Withdrawn | Proponent withdraws Submission from the Project Notification process |  | 3
4 | 7 | Direct Submission of Project Notification - DELETE this Intake Phase! | Delete this "Intake Phase" and go directly to "Notification Review" |  | 4
5 | 10 | Project Notification Submission Received (Day Zero) | Starts the 60-Day Legislated Time Period for Project Notification |  | 5
6 | 11 | Delegation of PN Decision | Minister to make the Project Notification Decision |  | 6
7 | 11 | Delegation of PN Decision | CEAO is delegated to make the Project Notification Decision |  | 8
8 | 39 | Project Notification Terminated s.39(d) | Project Notification is Terminated under s.39(d) of Act |  | 9
9 | 42 | Project Withdrawn | Proponent withdraws Submission from the Project Notification process |  | 10
10 | 60 | Project Notification Terminated s.39(d) | Project Notification is Terminated under s.39(d) of Act |  | 11
11 | 63 | Project Withdrawn | Proponent withdraws Submission from the Project Notification process |  | 12
12 | 67 | Decision: Project Notification | No Further Review Required |  | 13
13 | 67 | Decision: Project Notification | A Revised Project Notification Submission is Needed |  | 14
14 | 67 | Decision: Project Notification | Project Referred to Minister for Designation (s.11) |  | 15
15 | 11 | Delegation of PN Decision | Deputy CEAO is delegated to make the Project Notification Decision |  | 7

## Actions
No | OutcomeNo | OutcomeName | ActionName | ActionDescription | AdditionalParams | SortOrder
1 | 3 | Proponent withdraws Submission from the Project Notification process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases": false} | 1
2 | 3 | Proponent withdraws Submission from the Project Notification process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events": false} | 2
3 | 3 | Proponent withdraws Submission from the Project Notification process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 3
4 | 3 | Proponent withdraws Submission from the Project Notification process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 4
5 | 4 | Delete this "Intake Phase" and go directly to "Notification Review" | SetEventDate | Set "Notification Review ¦ Project Notification Submission Received (Day Zero)" ANTICIPATED to thisActual + 0 | {"phase_name":"Notification Review","work_type_id": 1, "ea_act_id": 3, "event_name": "Project Notification Submission Received (Day Zero)", "start_at": 0 } | 5
6 | 4 | Delete this "Intake Phase" and go directly to "Notification Review" | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events": false} | 6
7 | 4 | Delete this "Intake Phase" and go directly to "Notification Review" | SetPhasesStatus | Set thisPhase to INACTIVE | [{"phase_name":"Notification Intake","work_type_id": 1, "ea_act_id": 3, "is_active": false }] | 7
8 | 5 | Starts the 60-Day Legislated Time Period for Project Notification | LockWorkStartDate | Set thisWorkStartDate to thisEventACTUAL | {"start_date_locked": true} | 8
9 | 6 | Minister to make the Project Notification Decision | SetWorkDecisionMaker | Set thisWorkDecisionMaker to currentMinisterEnvironment | {"position_id": 8} | 9
10 | 7 | CEAO is delegated to make the Project Notification Decision | SetWorkDecisionMaker | Set thisWorkDecisionMaker to currentCEAO | {"position_id": 1} | 10
11 | 8 | Project Notification is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases": false} | 12
12 | 8 | Project Notification is Terminated under s.39(d) of Act | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events": false} | 13
13 | 8 | Project Notification is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 14
14 | 8 | Project Notification is Terminated under s.39(d) of Act | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 15
15 | 9 | Proponent withdraws Submission from the Project Notification process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases": false} | 16
16 | 9 | Proponent withdraws Submission from the Project Notification process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events": false} | 17
17 | 9 | Proponent withdraws Submission from the Project Notification process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 18
18 | 9 | Proponent withdraws Submission from the Project Notification process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 19
19 | 10 | Project Notification is Terminated under s.39(d) of Act | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases": false} | 20
20 | 10 | Project Notification is Terminated under s.39(d) of Act | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events": false} | 21
21 | 10 | Project Notification is Terminated under s.39(d) of Act | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 22
22 | 10 | Project Notification is Terminated under s.39(d) of Act | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 23
23 | 11 | Proponent withdraws Submission from the Project Notification process | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases": false} | 24
24 | 11 | Proponent withdraws Submission from the Project Notification process | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events": false} | 25
25 | 11 | Proponent withdraws Submission from the Project Notification process | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 26
26 | 11 | Proponent withdraws Submission from the Project Notification process | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 27
27 | 12 | No Further Review Required | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 28
28 | 12 | No Further Review Required | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 29
29 | 13 | A Revised Project Notification Submission is Needed | AddPhase | addPhase "Revised Project Notification Development" (this is a renamed copy of "Notification Intake"), addPhase "Revised Notification Review" and set phaseLegislated to FALSE (this is a renamed copy of "Notification Review"), addPhase "Revised Notification Decision" and set phaseLegislated to FALSE (this is a renamed copy of "Notification Decision") | [{"phase_name":"Notification Intake","work_type_id": 1, "ea_act_id": 3, "new_name": "Revised Project Notification Development", "legislated": false },{"phase_name":"Notification Review","work_type_id": 1, "ea_act_id": 3, "new_name": "Revised Notification Review", "legislated": false }, {"phase_name":"Notification Decision","work_type_id": 1, "ea_act_id": 3, "new_name": "Revised Notification Decision", "legislated": false }] | 30
30 | 13 | A Revised Project Notification Submission is Needed | SetEventsStatus | Set "Revised Project Notification Development ¦ Meeting with Proponent" to INACTIVE | [{"phase_name":"Revised Project Notification Development","work_type_id": 1, "ea_act_id": 3, "event_name": "Meeting with Proponent", "is_active": false }] | 31
31 | 13 | A Revised Project Notification Submission is Needed | SetEventDate | Set "Revised Project Notification Development ¦ Start of Intake Phase" to thisEventACTUAL +1 (this is a renamed copy of "Start of Intake Phase (e.g. Initial Contact, Draft Sharing, or PN Submission)") | {"phase_name":"Revised Project Notification Development","work_type_id": 1, "ea_act_id": 3, "event_name": "Start of Intake Phase (e.g. Initial Contact, Draft Sharing, or PN Submission)", "start_at": 1 } | 32
32 | 14 | Project Referred to Minister for Designation (s.11) | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 33
33 | 14 | Project Referred to Minister for Designation (s.11) | CreateWork | createWork: "Minister's Designation" and link to thisWorkLinkedProject | {"work_type": 2} | 34
34 | 15 | Deputy CEAO is delegated to make the Project Notification Decision | SetWorkDecisionMaker | Set the workDecisionMaker to currentADM | {"position_id": 2} | 11

## Lookups
WorkType | EA Act | Legislated |  | Event Type | Event Category | Visibility | ActionName | Event Position | Multiple Days | Action Name
Project Notification | EA Act (2018) | TRUE | Milestone | Generic | Milestone | MANDATORY | AllEventsDeactivated | START | TRUE | AddEvent
Minister's Designation | EA Act (2002) | FALSE | Milestone | Meeting | Calendar | SUGGESTED | AllEventsDeleted | INTERMEDIATE | FALSE | AddPhase
CEAO's Designation | EA Act (1996) |  | Milestone | Notification | Decision | OPTIONAL | CloseEverything | END |  | ChangePhaseEndEvent
EAC Assessment |  |  | Milestone | Order | Finance | HIDDEN | CloseWork |  |  | CreateWork
Exemption Request |  |  | Milestone | Referral | PCP |  | CompleteCurrentPhase |  |  | LockWorkStartDate
Dispute Resolution |  |  | Milestone | Report | Extension |  | CreateNewWork |  |  | SetEventDate
EAC/Order Amendment |  |  | Milestone | Request | Suspension |  | DisableWorkStartDate |  |  | SetEventStatus
Document Review |  |  | Milestone | Submission |  |  | DuplicatePhase |  |  | SetFederalInvolvement
EAC Extension |  |  | Milestone | Other | [5 empty] | SetPhaseStatus
Substantial Start Decision |  |  | Milestone | Date Capture | [5 empty] | SetProjectState
EAC/Order Transfer |  |  | Extension | Time Limit Extension | [5 empty] | SetProjectStatus
EAC/Order Suspension |  |  | Extension | PCP Time Limit Extension | [5 empty] | SetWorkDecisionMaker
EAC/Order Cancellation |  |  | Suspension | Time Limit Suspension | [5 empty] | SetWorkState
Other |  |  | Suspension | Time Limit Resumption
|  |  | Decision | EAC Ministers
|  |  | Decision | Minister
|  |  | Decision | CEAO
|  |  | Decision | ADM
|  |  | Decision | EPD
|  |  | Decision | PAD (Lead)
|  |  | Decision | Reviewer
|  |  | Decision | Federal
|  |  | Decision | Other
|  |  | PCP | Comment Period
|  |  | PCP | Open House
|  |  | PCP | Virtual Information Session
|  |  | PCP | Other
|  |  | Calendar | Communications
|  |  | Calendar | Executive
|  |  | Calendar | Financial
|  |  | Calendar | Work
|  |  | Calendar | Other
|  |  | Finance | Capacity Funding
|  |  | Finance | Fee Order
|  |  | Finance | Penalties
|  |  | Finance | Administrative
|  |  | Finance | Other