## Phases
No | Name | WorkType | EAAct | NumberOfDays | Legislated | Color | Visibility | SortOrder
1 | Notification Intake | Project Notification | EA Act (2018) | 21 | 0 | #FFFFFF | REGULAR | 1
2 | Notification Review | Project Notification | EA Act (2018) | 56 | 1 | #FFFFFF | REGULAR | 2
3 | Notification Decision | Project Notification | EA Act (2018) | 4 | 1 | #FFFFFF | REGULAR | 3

## Events
No | Parent | PhaseNo | EventName | Phase | EventType | EventCategory | EventPosition | MultipleDays | StartAt | NumberOfDays | Visibility | SortOrder
1 |  | 1 | Start of Intake Phase (e.g. Initial Contact, Draft Sharing, or PN Submission) | Notification Intake | Date Capture | Milestone | START | 0 | 0 | 0 | MANDATORY | 1
2 | 1 | 1 | Executive Calendar Notification | Notification Intake | Executive | Calendar | INTERMEDIATE | 0 | 0 | 0 | MANDATORY | 2
3 |  | 1 | Meeting with Proponent | Notification Intake | Meeting | Milestone | INTERMEDIATE | 0 | 7 | 0 | SUGGESTED | 3
4 |  | 1 | Additional Information Submission | Notification Intake | Submission | Milestone | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 4
5 |  | 1 | Document Submitted to EAO for "Initial Review" | Notification Intake | Submission | Milestone | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 5
6 | 5 | 1 | EAO's Viewpoint on Submitted Document | Notification Intake | PAD (Lead) | Decision | INTERMEDIATE | 0 | 7 | 0 | OPTIONAL | 6
7 |  | 1 | Delegation of PN Decision | Notification Intake | Minister | Decision | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 7
8 |  | 1 | Project Notification Withdrawn | Notification Intake | EPD | Decision | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 8
9 |  | 1 | Direct Submission of Project Notification - DELETE this Intake Phase! | Notification Intake | PAD (Lead) | Decision | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 9
10 |  | 1 | Other | Notification Intake | Other | Milestone | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 10
11 |  | 1 | Last Day of Intake Phase (day before formal submission) | Notification Intake | Date Capture | Milestone | END | 0 | 21 | 0 | MANDATORY | 11
12 |  | 2 | Project Notification Submission Received (Day Zero) | Notification Review | Submission | Milestone | START | 0 | 0 | 0 | MANDATORY | 12
13 | 12 | 2 | Executive Calendar Notification | Notification Review | Executive | Calendar | INTERMEDIATE | 0 | 0 | 0 | MANDATORY | 13
14 |  | 2 | Delegation of PN Decision | Notification Review | Minister | Decision | INTERMEDIATE | 0 | 7 | 0 | OPTIONAL | 14
15 |  | 2 | Comment Period | Notification Review | Comment Period | PCP | INTERMEDIATE | 1 | 14 | 15 | OPTIONAL | 15
16 | 15 | 2 | PCP Coming Soon Announcement & Tweet | Notification Review | Communications | Calendar | INTERMEDIATE | 0 | -7 | 0 | OPTIONAL | 16
17 | 15 | 2 | PCP Now Open Announcement & Tweet | Notification Review | Communications | Calendar | INTERMEDIATE | 0 | -7 | 0 | OPTIONAL | 17
18 | 15 | 2 | Executive Calendar Notification | Notification Review | Executive | Calendar | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 18
19 | 15 | 2 | PCP Ending Soon Announcement & Tweet | Notification Review | Communications | Calendar | INTERMEDIATE | 0 | number_of_days-2 | 0 | OPTIONAL | 19
20 |  | 2 | Additional Information Submission | Notification Review | Submission | Milestone | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 20
21 |  | 2 | GHG Threshold Information Note | Notification Review | Report | Milestone | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 21
22 | 21 | 2 | Executive Calendar Notification | Notification Review | Executive | Calendar | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 22
23 |  | 2 | Additional Comment Period | Notification Review | Comment Period | PCP | INTERMEDIATE | 1 | 0 | 30 | OPTIONAL | 23
24 | 23 | 2 | PCP Coming Soon Announcement & Tweet | Notification Review | Communications | Calendar | INTERMEDIATE | 0 | -7 | 0 | OPTIONAL | 24
25 | 23 | 2 | PCP Now Open Announcement & Tweet | Notification Review | Communications | Calendar | INTERMEDIATE | 0 | -7 | 0 | OPTIONAL | 25
26 | 23 | 2 | Executive Calendar Notification | Notification Review | Executive | Calendar | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 26
27 | 23 | 2 | PCP Ending Soon Announcement & Tweet | Notification Review | Communications | Calendar | INTERMEDIATE | 0 | number_of_days-2 | 0 | OPTIONAL | 27
28 |  | 2 | Open House | Notification Review | Open House | PCP | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 28
29 |  | 2 | Virtual Information Session | Notification Review | Virtual Information Session | PCP | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 29
30 |  | 2 | Comment Period Time Limit Extension | Notification Review | PCP Time Limit Extension | Extension | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 30
31 | 30 | 2 | PCP Extended Announcement & Tweet | Notification Review | Communications | Calendar | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 31
32 | 30 | 2 | Executive Calendar Notification | Notification Review | Executive | Calendar | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 32
33 |  | 2 | s.38 Extension of Time Limit | Notification Review | Time Limit Extension | Extension | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 33
34 | 33 | 2 | Extension Announcement & Tweet | Notification Review | Communications | Calendar | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 34
35 | 33 | 2 | Executive Calendar Notification | Notification Review | Executive | Calendar | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 35
36 |  | 2 | Project Notification Terminated s.39(d) | Notification Review | CEAO | Decision | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 36
37 | 36 | 2 | Termination Announcement & Tweet | Notification Review | Communications | Calendar | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 37
38 | 36 | 2 | Executive Calendar Notification | Notification Review | Executive | Calendar | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 38
39 |  | 2 | Project Notification Withdrawn | Notification Review | EPD | Decision | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 39
40 | 39 | 2 | Withdrawal Announcement & Tweet | Notification Review | Communications | Calendar | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 40
41 | 39 | 2 | Executive Calendar Notification | Notification Review | Executive | Calendar | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 41
42 |  | 2 | Other | Notification Review | Other | Milestone | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 42
43 |  | 2 | Project Notification Report referred to Decision Maker | Notification Review | Referral | Milestone | END | 0 | 56 | 0 | MANDATORY | 43
44 |  | 2 | Decision: Project Notification | Notification Review | CEAO | Decision | END | 0 | 56 | 0 | HIDDEN | 44
45 | 44 | 2 | Notification Decision Announcement & Tweet | Notification Review | Communications | Calendar | INTERMEDIATE | 0 | 0 | 0 | HIDDEN | 45
46 | 44 | 2 | Executive Calendar Notification | Notification Review | Executive | Calendar | INTERMEDIATE | 0 | 0 | 0 | HIDDEN | 46
47 |  | 3 | Project Notification Report Received by Decision Maker | Notification Decision | Report | Milestone | START | 0 | 0 | 0 | MANDATORY | 47
48 |  | 3 | Additional Information Submission | Notification Decision | Submission | Milestone | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 48
49 |  | 3 | s.38 Extension of Time Limit | Notification Decision | Time Limit Extension | Extension | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 49
50 | 49 | 3 | Extension Announcement & Tweet | Notification Decision | Communications | Calendar | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 50
51 | 49 | 3 | Executive Calendar Notification | Notification Decision | Executive | Calendar | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 51
52 |  | 3 | Project Notification Terminated s.39(d) | Notification Decision | CEAO | Decision | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 52
53 | 52 | 3 | Termination Announcement & Tweet | Notification Decision | Communications | Calendar | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 53
54 | 52 | 3 | Executive Calendar Notification | Notification Decision | Executive | Calendar | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 54
55 |  | 3 | Project Notification Withdrawn | Notification Decision | EPD | Decision | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 55
56 | 55 | 3 | Withdrawal Announcement & Tweet | Notification Decision | Communications | Calendar | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 56
57 | 55 | 3 | Executive Calendar Notification | Notification Decision | Executive | Calendar | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 57
58 |  | 3 | Other | Notification Decision | Other | Milestone | INTERMEDIATE | 0 | 0 | 0 | OPTIONAL | 58
59 |  | 3 | Decision: Project Notification | Notification Decision | Minister | Decision | END | 0 | 4 | 0 | MANDATORY | 59
60 | 59 | 3 | Notification Decision Announcement & Tweet | Notification Decision | Communications | Calendar | INTERMEDIATE | 0 | 0 | 0 | MANDATORY | 60
61 | 59 | 3 | Executive Calendar Notification | Notification Decision | Executive | Calendar | INTERMEDIATE | 0 | 0 | 0 | MANDATORY | 61

## Outcomes
No | TemplateNo | TemplateName | OutcomeName | OutcomeDescription | SortOrder
1 | 6 | EAO's Viewpoint on Submitted Document | Viewpoint is POSITIVE | EAO's Viewpoint is POSITIVE | 1
2 | 6 | EAO's Viewpoint on Submitted Document | Viewpoint is NEGATIVE | EAO's Viewpoint is NEGATIVE | 2
3 | 7 | Delegation of PN Decision | Minister's Decision | Minister to make the Project Notification Decision | 3
4 | 7 | Delegation of PN Decision | CEAO's Decision | CEAO is delegated to make the Project Notification Decision | 4
5 | 8 | Project Notification Withdrawn | PN Submission Withdrawn | Proponent withdraws Submission from the Project Notification process | 5
6 | 9 | Direct Submission of Project Notification - DELETE this Intake Phase! | Delete the Intake Phase | Delete this "Intake Phase" and go directly to "Notification Review" | 6
7 | 12 | Project Notification Submission Received (Day Zero) | Start the Review Period | Starts the 60-Day Legislated Time Period for Project Notification | 7
8 | 14 | Delegation of PN Decision | Minister's Decision | Minister to make the Project Notification Decision | 8
9 | 14 | Delegation of PN Decision | CEAO's Decision | CEAO is delegated to make the Project Notification Decision | 9
10 | 36 | Project Notification Terminated s.39(d) | PN is Terminated (s.39) | Project Notification is Terminated under s.39(d) of Act | 10
11 | 39 | Project Notification Withdrawn | PN Submission Withdrawn | Proponent withdraws Submission from the Project Notification process | 11
12 | 44 | Decision: Project Notification | No Further Review Required | No Further Review Required | 12
13 | 44 | Decision: Project Notification | Revised PN Submission Required | A Revised Project Notification Submission is Needed | 13
14 | 44 | Decision: Project Notification | Referred for Minister's Designation | Project Referred to Minister for Designation (s.11) | 14
15 | 52 | Project Notification Terminated s.39(d) | PN is Terminated (s.39) | Project Notification is Terminated under s.39(d) of Act | 15
16 | 55 | Project Notification Withdrawn | PN Submission Withdrawn | Proponent withdraws Submission from the Project Notification process | 16
17 | 59 | Decision: Project Notification | No Further Review Required | No Further Review Required | 17
18 | 59 | Decision: Project Notification | Revised PN Submission Required | A Revised Project Notification Submission is Needed | 18
19 | 59 | Decision: Project Notification | Referred for Minister's Designation | Project Referred to Minister for Designation (s.11) | 19
20 |  |  |  |  | 20
21 |  |  |  |  | 21
22 |  |  |  |  | 22
23 |  |  |  |  | 23
24 |  |  |  |  | 24
25 |  |  |  |  | 25
26 |  |  |  |  | 26
27 |  |  |  |  | 27
28 |  |  |  |  | 28
29 |  |  |  |  | 29
30 |  |  |  |  | 30
31 |  |  |  |  | 31
32 |  |  |  |  | 32
33 |  |  |  |  | 33
34 |  |  |  |  | 34
35 |  |  |  |  | 35
36 |  |  |  |  | 36
37 |  |  |  |  | 37
38 |  |  |  |  | 38
39 |  |  |  |  | 39
40 |  |  |  |  | 40
41 |  |  |  |  | 41
42 |  |  |  |  | 42
43 |  |  |  |  | 43
44 |  |  |  |  | 44
45 |  |  |  |  | 45
46 |  |  |  |  | 46
47 |  |  |  |  | 47
48 |  |  |  |  | 48
49 |  |  |  |  | 49
50 |  |  |  |  | 50
51 |  |  |  |  | 51
52 |  |  |  |  | 52
53 |  |  |  |  | 53
54 |  |  |  |  | 54
55 |  |  |  |  | 55
56 |  |  |  |  | 56
|  |  | PN Submission Withdrawn | Proponent withdraws Submission from the Project Notification process
|  |  | Delete the Intake Phase | Delete this "Intake Phase" and go directly to "Notification Review"
|  |  | Start the Review Period | Starts the 60-Day Legislated Time Period for Project Notification
|  |  | Deputy CEAO's Decision | Deputy CEAO is delegated to make the Project Notification Decision
|  |  | PN is Terminated (s.39) | Project Notification is Terminated under s.39(d) of Act
|  |  | PN Submission Withdrawn | Proponent withdraws Submission from the Project Notification process
|  |  | PN is Terminated (s.39) | Project Notification is Terminated under s.39(d) of Act
|  |  | PN Submission Withdrawn | Proponent withdraws Submission from the Project Notification process
|  |  | No Further Review Required | No Further Review Required
|  |  | Revised PN Submission Required | A Revised Project Notification Submission is Needed

## Actions
No | OutcomeNo | OutcomeName | ActionName | ActionDescription | AdditionalParams | SortOrder
1 | 3 | Minister's Decision | SetWorkDecisionMaker | Set thisWorkDecisionMaker to currentMinisterEnvironment | {"position_id": 8} | 1
2 | 4 | CEAO's Decision | SetWorkDecisionMaker | Set thisWorkDecisionMaker to currentCEAO | {"position_id": 1} | 2
3 | 4 | CEAO's Decision | AddEvent | addEvent "Notification Review ¦ Decision: Project Notification" (copy of "Decision: Project Notification" ) | {"phase_name":"Notification Review","work_type_id": 1, "ea_act_id": 3, "event_name": "Decision: Project Notification", "new_name": "Decision: Project Notification" } | 3
4 | 4 | CEAO's Decision | AddEvent | addEvent "Notification Review ¦ Notification Decision Announcement & Tweet" (copy of "Notification Decision Announcement & Tweet" ) | {"phase_name":"Notification Review","work_type_id": 1, "ea_act_id": 3, "event_name": "Notification Decision Announcement & Tweet", "new_name": "Notification Decision Announcement & Tweet" } | 4
5 | 4 | CEAO's Decision | AddEvent | addEvent "Notification Review ¦ Executive Calendar Notification" (copy of "Executive Calendar Notification" ) | {"phase_name":"Notification Review","work_type_id": 1, "ea_act_id": 3, "event_name": "Executive Calendar Notification", "new_name": "Executive Calendar Notification" } | 5
6 | 4 | CEAO's Decision | SetEventsStatus | Set “Notification Review ¦ Project Notification Report referred to Decision Maker” to INACTIVE | [{"phase_name":"Notification Review","work_type_id": 1, "ea_act_id": 3, "event_name": "Project Notification Report referred to Decision Maker", "is_active": false }] | 6
7 | 4 | CEAO's Decision | SetPhasesStatus | Set finalPhase “Notification Decision” to INACTIVE | [{"phase_name":"Notification Decision","work_type_id": 1, "ea_act_id": 3, "is_active": false }] | 7
8 | 5 | PN Submission Withdrawn | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases": false} | 8
9 | 5 | PN Submission Withdrawn | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events": false} | 9
10 | 5 | PN Submission Withdrawn | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 10
11 | 5 | PN Submission Withdrawn | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 11
12 | 6 | Delete the Intake Phase | SetEventDate | Set "Notification Review ¦ Project Notification Submission Received (Day Zero)" ANTICIPATED to thisWorkStartDate | {"phase_name":"Notification Review","work_type_id": 1, "ea_act_id": 3, "event_name": "Project Notification Submission Received (Day Zero)", "start_at": 0 } | 12
13 | 6 | Delete the Intake Phase | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events": false} | 13
14 | 6 | Delete the Intake Phase | SetPhasesStatus | Set thisPhase to INACTIVE | [{"phase_name":"Notification Intake","work_type_id": 1, "ea_act_id": 3, "is_active": false }] | 14
15 | 7 | Start the Review Period | LockWorkStartDate | Set thisWorkStartDate to thisEventACTUAL | {"start_date_locked": true} | 15
16 | 8 | Minister's Decision | SetWorkDecisionMaker | Set thisWorkDecisionMaker to currentMinisterEnvironment | {"position_id": 8} | 16
17 | 9 | CEAO's Decision | SetWorkDecisionMaker | Set thisWorkDecisionMaker to currentCEAO | {"position_id": 1} | 17
18 | 9 | CEAO's Decision | AddEvent | addEvent "Notification Review ¦ Decision: Project Notification" (copy of "Decision: Project Notification" ) | {"phase_name":"Notification Review","work_type_id": 1, "ea_act_id": 3, "event_name": "Decision: Project Notification", "new_name": "Decision: Project Notification" } | 18
19 | 9 | CEAO's Decision | AddEvent | addEvent "Notification Review ¦ Notification Decision Announcement & Tweet" (copy of "Notification Decision Announcement & Tweet" ) | {"phase_name":"Notification Review","work_type_id": 1, "ea_act_id": 3, "event_name": "Notification Decision Announcement & Tweet", "new_name": "Notification Decision Announcement & Tweet" } | 19
20 | 9 | CEAO's Decision | AddEvent | addEvent "Notification Review ¦ Executive Calendar Notification" (copy of "Executive Calendar Notification" ) | {"phase_name":"Notification Review","work_type_id": 1, "ea_act_id": 3, "event_name": "Executive Calendar Notification", "new_name": "Executive Calendar Notification" } | 20
21 | 9 | CEAO's Decision | SetEventsStatus | Set “Notification Review ¦ Project Notification Report referred to Decision Maker” to INACTIVE | [{"phase_name":"Notification Review","work_type_id": 1, "ea_act_id": 3, "event_name": "Project Notification Report referred to Decision Maker", "is_active": false }] | 21
22 | 9 | CEAO's Decision | SetPhasesStatus | Set finalPhase “Notification Decision” to INACTIVE | [{"phase_name":"Notification Decision","work_type_id": 1, "ea_act_id": 3, "is_active": false }] | 22
23 | 14 | Referred for Minister's Designation | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases": false} | 23
24 | 10 | PN is Terminated (s.39) | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases": false} | 24
25 | 10 | PN is Terminated (s.39) | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events": false} | 25
26 | 10 | PN is Terminated (s.39) | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 26
27 | 10 | PN is Terminated (s.39) | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 27
28 | 11 | PN Submission Withdrawn | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases": false} | 28
29 | 11 | PN Submission Withdrawn | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events": false} | 29
30 | 11 | PN Submission Withdrawn | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 30
31 | 11 | PN Submission Withdrawn | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 31
32 | 12 | No Further Review Required | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 32
33 | 12 | No Further Review Required | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 33
34 | 13 | Revised PN Submission Required | AddPhase | addPhases "Revised Project Notification Development" (this is a renamed copy of "Notification Intake"), addPhase "Revised Notification Review" and set phaseLegislated to FALSE (this is a renamed copy of "Notification Review") | [{"phase_name":"Notification Intake","work_type_id": 1, "ea_act_id": 3, "new_name": "Revised Project Notification Development", "legislated": false },{"phase_name":"Notification Review","work_type_id": 1, "ea_act_id": 3, "new_name": "Revised Notification Review", "legislated": false }, {"phase_name":"Notification Decision","work_type_id": 1, "ea_act_id": 3, "new_name": "Revised Notification Decision", "legislated": false }] | 34
35 | 13 | Revised PN Submission Required | SetEventDate | Set "Revised Project Notification Development ¦ Start of Revised PN Development" to thisEventACTUAL +1 (this is a renamed copy of "Start of Intake Phase (e.g. Initial Contact, Draft Sharing, or PN Submission)") | {"phase_name":"Revised Project Notification Development","work_type_id": 1, "ea_act_id": 3, "event_name": "Start of Intake Phase (e.g. Initial Contact, Draft Sharing, or PN Submission)", "start_at": 1 } | 35
36 | 13 | Revised PN Submission Required | SetEventName | Rename "Start of Intake Phase (e.g. Initial Contact, Draft Sharing, or PN Submission)" to "Start of Revised PN Development" | {"phase_name":"Revised Project Notification Development","work_type_id": 1, "ea_act_id": 3, "event_name": "Start of Intake Phase (e.g. Initial Contact, Draft Sharing, or PN Submission)", "new_name": "Start of Revised PN Development" } | 36
37 | 13 | Revised PN Submission Required | SetEventName | Rename "Last Day of Intake Phase (day before formal submission)" to "Last Day of Revised PN Development Phase (day before re-submission)" | {"phase_name":"Revised Project Notification Development","work_type_id": 1, "ea_act_id": 3, "event_name": "Last Day of Intake Phase (day before formal submission)", "new_name": "Last Day of Revised PN Development Phase (day before re-submission)" } | 37
38 | 13 | Revised PN Submission Required | SetEventsStatus | Set "Revised Project Notification Development ¦ Meeting with Proponent" to INACTIVE | [{"phase_name":"Revised Project Notification Development","work_type_id": 1, "ea_act_id": 3, "event_name": "Meeting with Proponent", "is_active": false }] | 38
39 | 13 | Revised PN Submission Required | SetEventName | Rename "Project Notification Submission Received (Day Zero)" to "Revised PN Submission Received" | {"phase_name":"Revised Notification Review","work_type_id": 1, "ea_act_id": 3, "event_name": "Project Notification Submission Received (Day Zero)", "new_name": "Revised PN Submission Received" } | 39
40 | 13 | Revised PN Submission Required | SetEventName | Rename "Project Notification Report referred to Decision Maker" to "Revised PN Report referred to Decision Maker" | {"phase_name":"Revised Notification Review","work_type_id": 1, "ea_act_id": 3, "event_name": "Project Notification Report referred to Decision Maker", "new_name": "Revised PN Report referred to Decision Maker" } | 40
41 | 13 | Revised PN Submission Required | SetEventName | Rename "Project Notification Report Received by Decision Maker" to "Revised PN Report Received by Decision Maker" | {"phase_name":"Revised Notification Decision","work_type_id": 1, "ea_act_id": 3, "event_name": "Project Notification Report Received by Decision Maker", "new_name": "Revised PN Report Received by Decision Maker" } | 41
42 | 13 | Revised PN Submission Required | AddEvent | AddEvent "Revised Notification Review ¦ Comment Period" and set visibility to SUGGESTED (copy of Comment Period) | {"phase_name":"Revised Notification Review","work_type_id": 1, "ea_act_id": 3, "event_name": "Comment Period","visibility": "SUGGESTED" } | 42
43 | 13 | Revised PN Submission Required | AddEvent | AddEvent "Revised Notification Review ¦ Delegation of PN Decision" and set visibility to SUGGESTED (renamed copy of Delegation of Decision) | {"phase_name":"Revised Notification Review","work_type_id": 1, "ea_act_id": 3, "event_name": "Delegation of PN Decision", "new_name": "Delegation of PN Decision","visibility": "SUGGESTED", "start_at": 1 } | 43
44 | 14 | Referred for Minister's Designation | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 44
45 | 15 | PN is Terminated (s.39) | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases": false} | 45
46 | 15 | PN is Terminated (s.39) | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events": false} | 46
47 | 15 | PN is Terminated (s.39) | SetWorkState | Set workState to TERMINATED | {"work_state": "TERMINATED"} | 47
48 | 15 | PN is Terminated (s.39) | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 48
49 | 16 | PN Submission Withdrawn | SetPhasesStatus | Set all "future" PHASEs to INACTIVE | {"all_future_phases": false} | 49
50 | 16 | PN Submission Withdrawn | SetEventsStatus | Set all "future" EVENTs in thisPhase to INACTIVE | {"all_future_events": false} | 50
51 | 16 | PN Submission Withdrawn | SetWorkState | Set workState to WITHDRAWN | {"work_state": "WITHDRAWN"} | 51
52 | 16 | PN Submission Withdrawn | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 52
53 | 17 | No Further Review Required | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 53
54 | 17 | No Further Review Required | SetProjectStatus | Set projectActive to FALSE | {"is_active": false} | 54
55 | 18 | Revised PN Submission Required | AddPhase | addPhases "Revised Project Notification Development" (this is a renamed copy of "Notification Intake"), addPhase "Revised Notification Review" and set phaseLegislated to FALSE (this is a renamed copy of "Notification Review") | [{"phase_name":"Notification Intake","work_type_id": 1, "ea_act_id": 3, "new_name": "Revised Project Notification Development", "legislated": false },{"phase_name":"Notification Review","work_type_id": 1, "ea_act_id": 3, "new_name": "Revised Notification Review", "legislated": false }, {"phase_name":"Notification Decision","work_type_id": 1, "ea_act_id": 3, "new_name": "Revised Notification Decision", "legislated": false }] | 55
56 | 18 | Revised PN Submission Required | SetEventDate | Set "Revised Project Notification Development ¦ Start of Revised PN Development" to thisEventACTUAL +1 (this is a renamed copy of "Start of Intake Phase (e.g. Initial Contact, Draft Sharing, or PN Submission)") | {"phase_name":"Revised Project Notification Development","work_type_id": 1, "ea_act_id": 3, "event_name": "Start of Intake Phase (e.g. Initial Contact, Draft Sharing, or PN Submission)", "start_at": 1 } | 56
57 | 18 | Revised PN Submission Required | SetEventName | Rename "Start of Intake Phase (e.g. Initial Contact, Draft Sharing, or PN Submission)" to "Start of Revised PN Development" | {"phase_name":"Revised Project Notification Development","work_type_id": 1, "ea_act_id": 3, "event_name": "Start of Intake Phase (e.g. Initial Contact, Draft Sharing, or PN Submission)", "new_name": "Start of Revised PN Development" } | 57
58 | 18 | Revised PN Submission Required | SetEventName | Rename "Last Day of Intake Phase (day before formal submission)" to "Last Day of Revised PN Development Phase (day before re-submission)" | {"phase_name":"Revised Project Notification Development","work_type_id": 1, "ea_act_id": 3, "event_name": "Last Day of Intake Phase (day before formal submission)", "new_name": "Last Day of Revised PN Development Phase (day before re-submission)" } | 58
59 | 18 | Revised PN Submission Required | SetEventsStatus | Set "Revised Project Notification Development ¦ Meeting with Proponent" to INACTIVE | [{"phase_name":"Revised Project Notification Development","work_type_id": 1, "ea_act_id": 3, "event_name": "Meeting with Proponent", "is_active": false }] | 59
60 | 18 | Revised PN Submission Required | SetEventName | Rename "Project Notification Submission Received (Day Zero)" to "Revised PN Submission Received" | {"phase_name":"Revised Notification Review","work_type_id": 1, "ea_act_id": 3, "event_name": "Project Notification Submission Received (Day Zero)", "new_name": "Revised PN Submission Received" } | 60
61 | 18 | Revised PN Submission Required | SetEventName | Rename "Project Notification Report referred to Decision Maker" to "Revised PN Report referred to Decision Maker" | {"phase_name":"Revised Notification Review","work_type_id": 1, "ea_act_id": 3, "event_name": "Project Notification Report referred to Decision Maker", "new_name": "Revised PN Report referred to Decision Maker" } | 61
62 | 18 | Revised PN Submission Required | SetEventName | Rename "Project Notification Report Received by Decision Maker" to "Revised PN Report Received by Decision Maker" | {"phase_name":"Revised Notification Decision","work_type_id": 1, "ea_act_id": 3, "event_name": "Project Notification Report Received by Decision Maker", "new_name": "Revised PN Report Received by Decision Maker" } | 62
63 | 18 | Revised PN Submission Required | AddEvent | AddEvent "Revised Notification Review ¦ Comment Period" and set visibility to SUGGESTED (copy of Comment Period) | {"phase_name":"Revised Notification Review","work_type_id": 1, "ea_act_id": 3, "event_name": "Comment Period","visibility": "SUGGESTED" } | 63
64 | 18 | Revised PN Submission Required | AddEvent | AddEvent "Revised Notification Review ¦ Delegation of PN Decision" and set visibility to SUGGESTED (renamed copy of Delegation of Decision) | {"phase_name":"Revised Notification Review","work_type_id": 1, "ea_act_id": 3, "event_name": "Delegation of PN Decision", "new_name": "Delegation of PN Decision","visibility": "SUGGESTED", "start_at": 1 } | 64
65 | 19 | Referred for Minister's Designation | SetWorkState | Set workState to COMPLETE | {"work_state": "COMPLETED"} | 65
66 | [5 empty] | 66
67 | [5 empty] | 67
68 | [5 empty] | 68
69 | [5 empty] | 69
70 | [5 empty] | 70
71

## Lookups
WorkType | EA Act | Legislated |  | Event Type | Event Category | Visibility | ActionName | Event Position | Multiple Days | Action Name
Project Notification | EA Act (2018) | 1 | Milestone | Generic | Milestone | MANDATORY | AllEventsDeactivated | START | 1 | AddEvent
Minister's Designation | EA Act (2002) | 0 | Milestone | Meeting | Calendar | SUGGESTED | AllEventsDeleted | INTERMEDIATE | 0 | AddPhase
CEAO's Designation | EA Act (1996) |  | Milestone | Notification | Decision | OPTIONAL | CloseEverything | END |  | ChangePhaseEndEvent
EAC Assessment |  |  | Milestone | Order | Finance | HIDDEN | CloseWork |  |  | CreateWork
Exemption Request |  |  | Milestone | Referral | PCP |  | CompleteCurrentPhase |  |  | LockWorkStartDate
Dispute Resolution |  |  | Milestone | Report | Extension |  | CreateNewWork |  |  | SetEventDate
EAC/Order Amendment |  |  | Milestone | Request | Suspension |  | DisableWorkStartDate |  |  | SetEventStatus
Document Review |  |  | Milestone | Submission |  |  | DuplicatePhase |  |  | SetFederalInvolvement
EAC Extension |  |  | Milestone | Other | [5 empty] | SetPhaseStatus
Substantial Start Decision |  |  | Milestone | Date Capture | [5 empty] | SetProjectState
EAC/Order Transfer |  |  | Extension | Time Limit Extension | [5 empty] | SetProjectStatus
EAC/Order Suspension |  |  | Extension | PCP Time Limit Extension | [5 empty] | SetWorkDecisionMaker
EAC/Order Cancellation |  |  | Suspension | Time Limit Suspension | [5 empty] | SetWorkState
Other |  |  | Suspension | Time Limit Resumption | [5 empty] | SetEventName
|  |  | Decision | EAC Ministers
|  |  | Decision | Minister
|  |  | Decision | CEAO
|  |  | Decision | ADM
|  |  | Decision | EPD
|  |  | Decision | PAD (Lead)
|  |  | Decision | Reviewer
|  |  | Decision | Federal
|  |  | Decision | Other
|  |  | PCP | Comment Period
|  |  | PCP | Open House
|  |  | PCP | Virtual Information Session
|  |  | PCP | Other
|  |  | Calendar | Communications
|  |  | Calendar | Executive
|  |  | Calendar | Financial
|  |  | Calendar | Work
|  |  | Calendar | Other
|  |  | Finance | Capacity Funding
|  |  | Finance | Fee Order
|  |  | Finance | Penalties
|  |  | Finance | Administrative
|  |  | Finance | Other